## Kalender
notizen |  | Hochstrom
... |  |  |  | SIS18 |  |  | UNILAC
2024-04-28 | Ar |  |  | Experiments 40-Ar ESR/CryRing and X8, 170-Er HFS
| EZR | Nord | Süd | FS | SS | NS | FS | SS | NS
2024-04-29 | Ar | Ar |  | Einstellung Hochstrom, HTA |  | T. Sieber: Test of the FAIR-CCC Prototype (superconducting Beam Intensity Diagnostics) , HTA
2024-04-30 | Ar | Ar |  | M. Frey: Barrier Bucket Cavity in ESR | Winters: Bunched beam experiments at the ESR
[5 empty] | T. Sieber: Test of the FAIR-CCC Prototype (superconducting Beam Intensity Diagnostics) , HTA | T. Sieber: Test of the FAIR-CCC Prototype (superconducting Beam Intensity Diagnostics) , HTA
2024-05-01 | Ar | Ar |  | Chorni: FCT measurements | Lorentz: ESR beam optics | Lorentz: ESR beam optics
[5 empty] | T. Sieber: Test of the FAIR-CCC Prototype (superconducting Beam Intensity Diagnostics) , HTA | T. Sieber: Test of the FAIR-CCC Prototype (superconducting Beam Intensity Diagnostics) , HTA
2024-05-02 | Ar | Ar |  | Chorni: Novel excitation hardware for tune measurement in ESR | Franchetti: Characterization of Beam Loss during Deceleration at ESR | Franchetti: Characterization of Beam Loss during Deceleration at ESR | Trafotest X2 | Trafotest X2
|  |  |  | B. Galnander: Slow extraction using COSE | B. Galnander: Slow extraction using COSE |  | R. Singh, W. Barth, S. Lauber: Inbetriebnahme Fast Farady Cup, US3 (4h)
2024-05-03 | Ar | Ar |  | Umstellung SIS18->SIS12 Oeftiger: Turn-by-turn Profiles for Optimising Multi-turn Injection | Kornilov: Beam losses related to the high-intensity | B. Galnander: Beam Based Alignment | Trafotest X2/ BSM: UN6 und UCW | Trafotest X2/ BSM: UN6 und UCW
2024-05-04 | Ar | Ar |  | Oeftiger: Electrostatic Radio-Frequency Quadrupole for Landau damping of Head-tail Instabilities | Kornilov: Bunch compression with high-intensity | B. Galnander: Scraper Protection | BSM: UN6 und UCW | BSM: UN6 und UCW
2024-05-05 | Ar | Ar |  | D. Ondreka: SIS18 Booster Mode | D. Ondreka: SIS18 Booster Mode | D. Ondreka: SIS18 Booster Mode
2024-05-06 | Ar | Ar |  | Umstellung SIS12->SIS18 Herfurth: Direct transfer of soft beams from SIS18 to CRYRING | Herfurth, Direct transfer of soft beams from SIS18 to CRYRING | Herfurth, Direct transfer of soft beams from SIS18 to CRYRING
....
... |  | U |  | SIS18 |  |  | UNILAC
| EZR | Nord | Süd | FS | SS | NS | FS | SS | NS
2024-06-03 |  | U |  | Umstellung SIS18->SIS12 | SIS18 Booster Mode | SIS18 Booster Mode | Barth: Uranium Front to End
2024-06-04 |  | U |  | SIS18 Booster Mode | SIS18 Booster Mode | SIS18 Booster Mode | Barth: Multi-Charge states
2024-06-05 |  | U |  | SIS18 Booster Mode | SIS18 Booster Mode | SIS18 Booster Mode
2024-06-06 |  | U |  | Umstellung SIS12->SIS18 Hessler: Commissioning of BPMs in TE beamline and related extensions of BENNO application. | Hessler: Commissioning of BPMs in TE beamline and related extensions of BENNO application. | Pietri, E. Kazantseva: Testing of framework for Machine Learning to optimize Super-FRS operation, HFS |  | R.Singh: Measurement of bunch length of non-relativistic LINAC beams, X2
2024-06-07 |  | U |  | K. Gross: SIS18 Micro Spill Cavity | K. Gross: SIS18 Micro Spill Cavity | R. Singh: Macrospill feedback for Quad driven slow extraction
2024-06-08 |  | U |  | Walasek-Hoehne: Study of the OTR screen for spill structure and profile measurements with high intensity | Walasek-Hoehne: Study of the OTR screen for spill structure and profile measurements with high intensity, HTP | R. Singh: Macrospill feedback for Quad driven slow extraction
2024-06-09 |  | U |  | T. Radon: Dosimetry with Uranium beams, HTA | T. Radon: Dosimetry with Uranium beams | Boutachkov: Study of the ZnO(Ga) powder screen, HTP