## Slide 1
Straw Production: Status, Plans, Timelines
Peter Wintz (IKP - FZ Jülich)
(A. Cebulla, I. Georgadze, V. Kozlov, S. Orfanitski)
PANDA Tracking Meeting,
Oct-10, 2013, Jülich

## Slide 2
STT layout
Straw tubes
Straw modules
Straw production
Risk factors
Timelines
Outline Straw Production

## Slide 3
4636 straw tubes in 2 separated semi-barrels
6 hexagonal sectors (A-F)
23-27 planar layers in radial direction
  15-19 axial layers (green) in beam direction
  4 stereo double-layers: ±3° skew angle (blue/red)
STT dimensions
  Rinner/Router: 150/418 mm
  Length: ~ 1500 + 150 mm
  Inner / outer walls (~ 1mm kevlar  Dario)
Material budget: X/X0 = 1.23 % (radial)
STT Layout
STT x-y view
STT 3-D view
A
B
C
D
E
F

## Slide 4
Basic parameter list
STT inner/outer radius
Straw length
    Skew angle of stereo layers
    Straw pitch
  Straw positions
Straw module layout (gas sectors)
Attachment points to mechanical frame
STT Layout Parameters
straw pitch

## Slide 5
Straw length = cut length of mylar film tube
1400 mm length for axial straws (1418 mm incl. endplugs)
Stereo layers
      6 shorter straws with different length: L= i200mm -15mm, i = 1..6
      -15 (20) mm gap for electric/gas connection
Skew angle:  = 2.90(5)° ( z ~ 2.9 mm)
Straw Length

## Slide 6
New straw diameter (pressurized) for new mylar film tubes (LAMINA specs.)
New straw pitch in layout
    Pitch = straw diameter + 20µm gap (glue), straws pressurized to p=1 bar
    Diameter meas. method developed & approved, ~1-2µm precision (Artur)
    Change (prelim.): 10.10  10.14(5) mm
  Small change in radial STT dimension (Rmax~1.3mm)
    Few mm safety margin in layout still left
  Re-calculation of all straw positions
    CAD & text file for MC input (Artur/Peter)
    Mechanical frame adaption
  New reference plate for layer gluing neccessary
  Final decision of straw pitch in Nov/Dec 2013
Straw Pitch
Change of radial dimensions by larger straw diameter
R  1.3 mm

## Slide 7
Straw materials
New mylar film tubes
Repeat orders necessary
    All materials for 10.000 straws
    No redesigns (or only minor changes)
    Endplugs, crimp pins, grounding springs, ..
Straw Tubes

## Slide 8
Straw Tube Materials
Straw components
Minimised number of materials and material budget (thickness)
Al-mylar film, d=27µm, ID=10mm, L=1400mm
20µm sense wire (W/Re, gold-plated)
    Wire tension 50g at 1 bar overpressure
End plug (ABS thermo-plastic)
Crimp pin (Cu, gold-plated)
Gas tube (PVCmed, OD=0.8mm, 150µm wall)
Cathode spring (Cu/Be, gold-plated)
Attachment strip (GFK), locator ring (POM)
All materials radiation-hard
(p-beam tested)
Element | Material | X [mm] | X0 [cm] | X/X0
Film Tube | Mylar, 27µm | 0.085 | 28.7 | 3.0 10-4
Coating | Al, 2 0.1µm | 6.3 10-4 | 8.9 | 7.0 10-6
Gas (2bar) | Ar/CO2 (10%) | 7.85 | 6131 | 1.3 10-4
Wire | W/Re, 20µm | 3 10-5 | 0.35 | 8.6 10-6
 |  |  | Straw | 4.46 10-4

## Slide 9
Specifications:
    Mylar film, 10.00mm ID, 27µm wall (LAMINA, UK)
    2 12µm mylar strips, + ~3µm glue
    2 0.1µm aluminisation (3 higher than before)
      At inner side + outer side of tube
  Two different specifications of inner strip layer winding
      w/ 1mm self-overlap  single tube with higher rigidity
      w/o self-overlap  minimal wall (27µm)
Mylar Film Tube
    Reminder:
    straw tube = 2 long Al-mylar
    film strips, helically wound around mandrel and glued together
Short history summary (2011-2012):
  1st delivery: excess glue at straw inner side caused broken wires inside assembled straws
  2nd delivery: new specification with self-overlapping inner strip, same spec as COSY-STT
  straws, there only ~1% broken wires
  We found stronger leakage (>10 permeation level) at winding spiral
  Explanation: too much! glue, inhomogenous glue layer
Former straw leakage
at winding gap (2012)

## Slide 10
  Close co-operation with LAMINA
    Setup of our proposed leakage test bench at LAMINA, test sample tested ok by us
    Quick new mass production, charge-free
    1st replacement order (both specs 2500+2500 straws) received in Jun-2013
  Both straw types tested sucessfully up to p ~ 2bar
    No leakage observed anymore
    Elongation ok, L/p ~ 0.9mm/1bar
    Twisting negligible , /p < 2°/1bar
    Diameter rise still to be measured, R/p
Decision between both specs after precise diameter measurement
Mylar Film Tube Tests

## Slide 11
Axial layer modules
Stereo layer modules
Gas manifolds & sectors
3-D gauge of straw modules
Alignment structures
Mechanical frame attachment
Straw Modules

## Slide 12
Axial quad-layer module
    4 close-packed planar layers, (dot) glued together
    Increased rigidity compared to double-layer
    Replacement of faulty single straws still possible (from outer to inner layer)
    Even number of straws and gas lines per module
    Only 1 inlet + 1 outlet gas pipe for one module
    In-/outlet at same end by connecting 2 straws in series at far end
Outer axial module
    3-7 close-packed planar layers
    Outer circular shape
Axial Straw Modules
Axial straw
modules

## Slide 13
Stereo quad-layer module
    2 closed-packed double-layers with opposite skew angle (± 2.9° to axial)
    Even number of straws
    Gas in-/outlet at same end
    Shorter tubes at corners, connected (gas+electric) to next skewed double-layer in same module
Stereo Straw Modules
Stereo layers
Connection scheme of shorter straws in skewed double-layers
+2.9° -2.9° view from top

## Slide 14
Straw Modules Layout
Semi-barrel, length 1.2 m, final radial dimensions, reduced mech. frame
Hexagon sector, mounting brackets to fix modules in mechanical frame
STT sector consisting of 6 straw modules:
2 inner axial + 2 stereo + 2 outer axial
STT prototype, one semi-barrel

## Slide 15
Stainless steel pipes
     = 4  0.1 mm (OD  wall)
    10mm long end pieces with thicker wall (0.4 mm)
    Capillary pins ( = 0.55mm) for individual straws
  1 inlet pipe + 1 outlet pipe per straw module
  Inlet + outlet pipe at same end
Gas Manifolds

## Slide 16
1
2
3a
3b
4a
4b
Per semi-barrel: 12 gas lines, 212 gas pipes (in-/outlet)
Arrangement of 4 parallel gas lines per hexagon sector
  Proposed scheme: lines 1, 2, 3a+b, 4a+b
    Similar number (=gas flux) of straws per gas line: #205, 196, 190, 142
    Still 3d tracking possible with momentum reso. in each sector if one line failures
    Still 3d-online track recognition possible
No hints for serious gas failures (leakage)
    from COSY-STT, 4yrs in vacuum,
    leakage at permeation level
Gas Sectors

## Slide 17
Task:
Measure absolute straw positions, define reference points in hexagon sector
Check gas overpressure / temperature effects
Define full assembly method
Check minimal support / alignment structures (forw/backw connecting tubes)
Define attachment points of straw modules to mechanical frame
Method:
Assembly (step-by-step) of one complete hexagon sector
3D gauge arm measurement, ~ 1.8m volume length
Input to CAD file
Is important step: final positioning/alignment check, to be finished by end 2014
3-D Gauge of Straw Modules

## Slide 18
Status
Quality assurance
Timelines
Straw Mass Production

## Slide 19
Pilot straw mass production run (~ 600 straws) was done in 2012
Quality criteria & assurance approved
      Leakage test & wire tension check of each assembled straw
    Mylar tube quality checked last month (Sep-2013), ok!
All straw materials available for first few 1000 straws
Repeat order for some parts neccessary during 2014
Clean room set up for straw production
Clean storage of assembled straws outside in preparation
Final straw mass production has started (Oct-2013)
Straw Mass Production Preparations

## Slide 20
Final mass production of 10.000 straws:
      1000 straws for hexagon sector setup
      5000 straws for STT construction
      3000 - 4000 spare (fully assembled) straws to avoid new production cycle later
    During 2013 – 2017
Straw Mass Production Plan

## Slide 21
Quality control during straw mass production
    Wire tension measurement & leakage test of each single straw (also long-term)
    Criteria (sensitivity) approved (prototype productions, COSY-STT)
    Assembly in clean room, storage in clean containers
Straw operation, avoid/reduce aging by
    Contamination of straws and gas system, e.g. SiO2  destruction of straws
    Gas gain limit, 5104 (LSM few %)
STT assembly
    Pre-mounting foreseen (pre-series test)
    One complete hexagon sector
Risk factors under control
Straw Related Risk Factors

## Slide 22
Funding period 2012-2016 (BMBF, Germany)
2013 (Q4): Final straw design freeze
2013-2017: Straw mass production & assurance tests (3-4 years)
2014 (Q4): 3-D gauge of straw modules (absolute positioning)
2015/16: Pre-series test
      Full STT Hexagon sector assembled
      Equipped with readout (~ 800 channels), DAQ
      Beam tests at COSY
  2017: Completion of STT assembly
Timelines Straw Production

## Slide 23
Funding period 2012-2016 (BMBF), timelines for straw constructions
2013 (Q4): Final design freeze
2013-2017: Straw mass production & assurance tests (3-4 years)
2014 (Q4): 3-D gauge of straw modules (absolute positioning)
2015: Final mechanical frame design & manufacturing
2015/16: Pre-series test
      Full STT Hexagon sector assembled
      Equipped with readout (~ 800 channels), DAQ
      Beam tests at COSY
Timelines Straw Production

## Slide 24
Funding period 2012-2016 (BMBF), timelines for straw constructions
2013 (Q4): Final design freeze
2013-2017: Straw mass production & assurance tests (3-4 years)
2014 (Q4): 3-D gauge of straw modules (absolute positioning)
2015: Final mechanical frame design & manufacturing
2015: Final frontend electronic readout design
2015/16: Pre-series test
      Full STT Hexagon sector assembled
      Equipped with readout (~ 800 channels), DAQ
Timelines Straw Production