## Slide 1: Progress toward a New Control Room for the SLAC Accelerators
Michael Stanek
27-October-2014
WAO 2014

## Slide 2: SLAC National Accelerator Laboratory
A multi-discipline laboratory operated by Stanford University for the US Department of Energy since 1962.
  Originally created for high energy particle physics
  3 km electron Linac
  Fixed target end stations
  Colliding beam storage rings (SPEAR, PEP, PEP2)
  Linear collider arcs & final focus (SLC)
  Synchrotron light source (SPEAR3 - SSRL)
  X-Ray FEL (LCLS)
    Photon beams for material science, biological science, atomic & molecular physics
  Advance electron accelerator physics (FACET, NLCTA)

## Slide 3: Facilities operated by Accelerator Operations & Safety Division
  1 km Linac for LCLS X-ray FEL
  2 km Linac for FACET Accelerator R & D
  SPEAR3 for SSRL
  Test beams from LCLS Linac to End Station A
  Future: LCLS-II
    1 km Superconducting RF Linac for X-ray FEL
  Goal – Operate all from one control room

## Slide 4: Existing Main Control Center Needs more space & more workstations!

## Slide 5: MCC during Accelerator Physics studies

## Slide 6: A New Accelerator Control Room would help…
More space to operate 3 accelerators
  LCLS, FACET, SPEAR3
Space for commissioning and operation of future accelerators (LCLS-II, FACET-II)
Add capacity for monitoring of Conventional Facilities
Future Cryogenic plant (LCLS-II)?

## Slide 7: Unique Opportunity…
SLAC Research Support Building and Infrastructure Modernization Project (2010 through 2014)
  DOE funding available (Economic recovery “stimulus”)
  Renovate 2 large office buildings
  Upgrade the 230 kV Electrical infrastructure
  Build 1 new office building for the Accelerator Directorate (~300 people)

## Slide 8: Can we put a new Control Room in the new building?
    Head of Accelerator Directorate (Norbert Holtkamp) advocated for space in the new RSB office building for a future control room.
    End of 2010, approval to allocate space.
    Proceed with Office building construction, but leave an unfinished “shell” on the first floor. (24m x 13m)
    Funding level for Control Room = “to be decided”, based on how much is left from the projects listed above
    Start planning!

## Slide 9
New Building
Space for New Control Room
Existing Main Control
Center
Accelerator

## Slide 10: Design inputs
Existing SLAC Main Control Center was remodeled in 2008
  Displays & console design based on ergonomic analysis
  New Control Room should preserve popular features
  Address remaining problems
    Noise
    Not enough space for each accelerator
    Temperature control & Air flow
    Dark ‘cave-like’ room
    Lacking Aesthetic appeal
Operations group –
  brainstorming & design meetings

## Slide 11: Learn from other Labs
Review Past WAO presentations
  CERN – Rossano Giachino at WAO 2005
  WAO 2012 Control Room overview session – Jim Morel
    http://www-conf.slac.stanford.edu/wao2012/agenda.asp
Review other Accelerator Control Room layouts
  Brookhaven
  TJNAF
  SNS at Oak Ridge
  Fermilab

## Slide 12: Plan, Review, Revise, repeat…
SLAC Internal review (July 2011)
  System Managers, Controls Engineers, Accelerator Physicists
External review (August 2011)
  WAO 2012 Program Committee meeting
Formal Requirements Document (November 2011)
Rough cost estimates
Refine Design Details & wait (2012)
  Wait for main building construction to finish
  Coordinate to make sure building services will support control room design
  Wait for funding

## Slide 13: Control Room ‘shell’ during RSB construction

## Slide 14: Conceptual Design

## Slide 15
Graphic of ACR layout
LCLS
FACET/LCLS II
SPEAR 3
Support
(ICD, Facilities)
Window
Network
Room
(ANR)
Conduits (16) to manhole, then to Bldg 5, 50
Northeast foyer of 52

## Slide 16: Artist Rendering (early 2013)

## Slide 17: Key Design Features
Separate Heating, Ventilation & Air Conditioning systems for Control Room & Network Room
Raised computer floor, cable trays, “in-wall” conduits
All power circuits on backup generator
  many with UPS
5 adjustable lighting zones
Conduits to existing MCC & SPEAR3

## Slide 18: Under Construction (September 2014)

## Slide 19: Key features (2)
Separate work areas for 4 Accelerator programs
Workstation computers are rack-mounted in a separate Network room for sound & temperature isolation
  KVM extenders (USB) to each keyboard location
  DVI video cable repeaters (CAT6) to each monitor
  Tested in existing MCC
Overhead Display Monitors mounted on a track system
  34 large (55”) monitors, 68 smaller (24”) monitors
Improved Air flow
  Supply air in the center of the room, Return on the edges
Large window for tour groups
  Allows some direct outdoor light

## Slide 20
More than 2 times the space.

## Slide 21: Final Design & Construction
End of 2012, initial funds available
  Contractor hired to formalize conceptual design & drawings
End of 2013, more funds available
  Feb 2014 – Contract signed for ‘Design & Build’ (outside company)
June 2014 Civil Construction started
October 2014 Civil Construction complete
October 2014 – August 2015
  Network cables will be installed
  IT equipment will be purchased & installed
August 2015 Accelerator shutdown
  Move Operations to the new Control Room

## Slide 22: Current Status: Civil Construction completed Oct 14, 2014

## Slide 23: Adjacent Network room

## Slide 24: Ready for SLAC Cable & Controls installation Starting October 27 (today!)

## Slide 25: Budget
Civil Construction
  Design & Build contract (outside company)
  $3.7 Million (US)
IT Equipment, Cabling, Instrumentation & Controls
  ~$ 0.8 M Materials
  ~$ 0.3 M SLAC Labor

## Slide 26: Concerns
Completion of custom Safety System interface electronics in time for Aug 2015 move-in.
Time window for final migration & testing is short.
  6 week Accelerator shutdown Aug-Sept 2015
  Difficult to ‘fall back’
New ACR location is more accessible for non-Operations personnel.
  Door locks with RF ID Card readers.
  Database of persons approved for entry.
Limited Parking!

## Slide 27
We are very satisfied with the results so far.
Looking forward to Operation in September 2015!
Thank you for your attention.
Questions?

## Slide 28: Backup slides

## Slide 29: Original Project schedule (completion Aug 2014)
Delays
Oct 2014
Compression