## Slide 1
ITER Status of In-Kind Procurement
Helium (3,5 MeV)
Neutron (14,1 MeV)
Deuterium
Tritium
Ken Blackler Construction Management
Notes: This template can be used as a starter file for a photo album.

## Slide 2: ITER Key Facts
Introducing
Chart: 
| EU | Japan | China | RF | India | USA | Korea
EU | 45.4545 | 9.0909 | 9.0909 | 9.0909 | 9.0909 | 9.0909 | 9.0909
Japan | 9.0909
China | 9.0909
RF | 9.0909
India | 9.0909
USA | 9.0909
Korea | 9.0909
European Union
CN
IN
RF
KO
JP
US
7 Members: China, EU, India, Japan, Korea, Russia & US
Designed to produce 500MW of fusion power for an extended period of time
10 years construction, 20 years operation
Cost reported to be 15 billion Euros*
* TGV line from Marseille to Nice (16bn€)
London Olympics 2012 (14bn€)

## Slide 3
ITER Project
CN
ITER: an integrated project:
Central Team & Seven Domestic Agencies
IO
RF
EU
KO
JA
IN
The 7 ITER Members make cash and in-kind contributions (90%) to the ITER Project. They have established Domestic Agencies to handle the contracts to industry.
The ITER Organization Central Team manages the ITER Project in close collaboration with the 7 Domestic Agencies.
The ITER Members share all intellectual Property generated by the Project.
US

## Slide 4
ITER: Demonstrate the technological feasibility of fusion as an energy source
DEMO: The next step will be to demonstrate commercial power generation
Path Towards Fusion

## Slide 5
In kind Contributions
Almost all of the components will be provided to the ITER Organization through in-kind contributions from the seven Members
China, India, Japan, Korea, Russia and the United States have responsibility for ~ 9% of procurement packages.
Europe’s share, as Host Member, is ~ 45% (construction and manufacturing).

## Slide 6: ITER Currency
ITER has defined an ITER Unit of Account (IUA)
  Project uses EURO for financial accounts/cash
  Member contributions, lifecycle expressed in kIUA (1IUA ≈ 1700 €2014)
  Avoid multiple currencies with fluctuations and eliminate inflation
  Members do not report actual cost, nor does the IO manage their costs
Parties provide 84% in-kind, 16% in-cash
Real cost may be several times kIUA cost….

## Slide 7: Procurement Arrangement
“Contractual-like” document between ITER Organisation and Member’s Domestic Agency
  DA is procurement body within Member state
  Contractual body for in-kind supplies
Main -> General & Special Conditions
Annex A -> Management Conditions
Annex B -> Technical Specifications

## Slide 8
ITER Machine

## Slide 9
Central solenoid
Toroidal field coils (18)
Cryostat
Blanket modules
Thermal shield
Correction coils (18)
Internal coils
Poloidal field coils (6)
Vacuum vessel
Divertor
Cooling water system
Who Manufactures What?

## Slide 10
Conductor
China
South Korea
Japan
Russia
United States
Europe
TF Coil
Japan
TF coil cases
Japan
Europe

## Slide 11
PF Coils Building
ITER HQ
Subcontractors Area
Tokamak Complex
(Under construction)
Assembly Hall
(Under construction)
400 kV Switchyard
Cryostat Workshop
HQ Extension
Storage Area 2
Storage Area 3
Storage Area 1
Batching Plant
Worksite Progress
Under Installation
Transformers
Preparatory Works
Cryogenics Building
Preparatory Works
Cooling Water Building
Preparatory Works
Control Building
Preparatory Works
RF Heating Building
August 2015

## Slide 12
Assembly Hall
Components will be pre-assembled in this 60-metre high building prior to their integration into the machine. Lifting operations for the 730-ton roof were completed on 10 Sep. 2015

## Slide 13
China is responsible for the procurement of 14 poloidal field AC/DC converter units that will provide reliable, controlled DC power to the ITER poloidal field magnetic coils. In February 2015, a prototype converter unit was successfully tested, opening the way to future batch production.
Manufacturing Progress
China

## Slide 14
Europe is responsible for delivering remote handling systems for the divertor, the neutral beam system, in-vessel viewing and metrology, and the cask transfer system for activated components—in all, about EUR 250 million of investment. At the Divertor Test Platform facility hosted by the VTT Technical Research Centre in Finland, the final demonstration of the divertor cassette remote handling system was carried out in February 2015.
Manufacturing Progress
Europe

## Slide 15
India is responsible for the fabrication and the assembly of the 30 x 30 m. ITER cryostat. Pictured, six 60° base plates are temporarily assembled at the factory in order to check tolerances prior to shipment to ITER. The first cryostat elements are scheduled to arrive at ITER in November 2015.
Manufacturing Progress
India

## Slide 16
The US is responsible for the design, R&D, and manufacturing of the main central solenoid magnet (using conductor supplied by Japan), as well as the associated structure and tooling. At General Atomics’ Magnet Technologies Center in Poway, California, winding operations began in April 2015 on a mockup module.
Manufacturing Progress
USA

## Slide 17
Door-to-door Delivery
14 January 2015: First of four 90-ton transformers procured by the US and manufactured in Korea
20 March 2015: Detritiation tank (20 tons), procured by Europe
2 April 2015: Detritiation tank (20 tons), procured by Europe
20 April 2015: Second of four 90-ton transformers procured by the US and manufactured in Korea
7 May 2015 (pictured): Two 80-ton, 61,000-gallon drain tanks for the tokamak cooling water system, procured by the US

## Slide 18
Baseline Schedule
Buildings and Infrastructure
1st Plasma
Assembly and testing

## Slide 19
Establishing a New Schedule
Assembly: 2015 - …
First Plasma: …
DT Operations : …
An updated reliable schedule
to build the Tokamak till
First plasma, with the detail
of the necessary resources,
will be presented, for validation,
to ITER Council on November 2015
Notes: Investigatiing the impact on ITER construction of the earthquake and tsunami in Japan
the Capped Value

## Slide 20: 2015 Changes
New senior management team appointed
  DG and 2 Deputies (COO and RCO)
  Simpler departmental organization
Action plan approved by ITER Council
  Project Management improvements
  Greater flexibility in re-organization
  Increased authority of DG over DA
  Mitigation actions for in-kind complexities

## Slide 21: Mitigation - Project Team
Large success factor is efficiency of multiple party decision making (Supplier, DA, IO)
In key areas Project Teams created
  Buildings and Vacuum Vessel
  Combine IO and DA resources
  Formal letters of assignments from home organization
  Delegated management authority for PA activities
IO and DA
Contractor
ITER
DA
Contractor

## Slide 22: Mitigation – Reserve Fund
IO baseline includes no contingency
Decisions to solve technical and procurement issues often imply cost increases for Domestic Agencies
Creation of Reserve Fund with decision making powers given to IO DG
  Allows technical decisions affecting cost to be implemented without delay
  Strict allocation rules, for changes, missing scope and recovery actions
  Not for “cost increases”

## Slide 23: Mitigation - Centralization
Key areas of in-kind complexity identified
Centralization by return scope to IO Central Team
  Tokamak Cooling Water System (large number of interfaces)
  Standard Piping (between services and each client)
  Cabling (procurement and installation)
  Nuclear Safety System (central design, licencing and procurement)
  Installation activities (where DA agrees)

## Slide 24: Other Issues Lessons Learnt
Control of Deliveries
  Global Logistics Provider
  Multi-party procurement rules
Customs/Duties/Taxes
  Location of clearance
  International organization privileges
Transfer of Responsibility, Ownership
  Complications of commitments as Member vs. responsibilities as supplier
Warrantees
  Longer schedules means warrantees expire before operations
CE Marking
  Education of industry, and identification of “manufacturer”

## Slide 25: Construction
New Construction Department created in 2015
  Construction Management as Agent
  Contract strategy approved and procurement process started

## Slide 26: Contract Map
ITER Organization
Construction Manager-as-Agent
Domestic Agency
Works Contractors
Machine Assembly Works
Mechanical & Piping
Works
Specialized Works
Super Conducting Joints
Cryogenics
Special Techniques
Lifting & Handling
Tokamak
Works Contracts
Support Contracts
Access, Plant Hire
Civils & Finishing
Balance of Plant
Electrical, I&C Works
Scaffolding
CMA
ASY
MCP
EIC
SPx
LFT
SCF
APH
CIV

## Slide 27: Industry Fair - Construction
Information Day held in May 2015
Over 200 representatives from 160 companies
Purpose: Inform and motivate industry to participate in upcoming tenders
Following this, the IO has met companies (market survey):
  Opportunity to listen to the companies’ feedback and lessons learned from similar contracts, for example regarding organization and site management;
  Meetings held throughout June and July;
  The IO has included the market survey outcome in the technical specifications as well as in the contract.

## Slide 28: Market Survey – Construction Manager as Agent (CMa)
Main discussion related to:
  Lessons learned, success factors
  Contract type, major risks and risk sharing
  Proposed organizational structure, roles and responsibilities
  Mobilization period, early engagement
  Core team, continuity of key staff, flexibility
  Payment scheme, incentivisation, key performance indicator (KPI)
  Information required to prepare clear and comparable tender offer, such as policies, schedule, scope and volume of work to be managed.
40 companies nominated for tender
Companies combined to make consortia
Pre-qualification complete. Tender launch end of November

## Slide 29: Market Survey - Works
Good industrial capacity for conventional works (electrical, cabling, mechanical & piping)
Market conditions favourable at this time
Support to centralization of cabling, combining pre-manufacturing with installation of piping;
Main discussion related to:
  Information required to prepare clear and comparable tender offer, bills of quantity, definition of scope;
  Contract form and pricing structures (Lump Sum, Rates, Cost Plus);
  Methods of reimbursement, incentivization, KPI;
  In-house and local industrial workshop facilities;
  Centralization of cable procurement, pre-manufacturing;
  Mobilization strategy, early engagement.
Tenders early 2016

## Slide 30: Conclusions
ITER has experienced many challenges due to in-kind nature of project
Highly complex procurement allocation has increased challenges
Separation of Domestic Agencies from Central Team has led to slower decision making
Mitigation Actions driven by new management implemented and Updated Schedule prepared to reflect new strategy