## Slide 1: CBM Timeline
Walter F.J. Müller, FAIR, Darmstadt
CBM-STAR joint Workshop 18 March 2017

## Slide 2: FAIR – Conceptual View
CR
2
SIS18
HESR
Compressed Baryonic Matter
Super Fragment-Separator:
Nuclear Structure and Astrophysics
Anti-Proton Physics
p-Linac
1012/s; 1.5 GeV/u; 238U28+
1010/s 238U92+ up to 11 (35) GeV/u
3x1013/s 30 (90) GeV protons
radioactive beams up to 1.5 - 2 GeV/u;
1011 antiprotons 1.5 - 15 GeV/c
Primary Beams
Secondary Beams
FAIR phase 1
FAIR phase 2
SIS100/300

## Slide 3: GSI/FAIR Project Re-Organization
GSI and FAIR were two separate organizations
starting 2014 joint managing directors were appointed
  Nov 2014: Ursula Weyrich (Administrative)
  Feb 2016: Jörg Blaurock (Technical)
  Jan 2017: Paolo Guibellino (Scientific)
in 2016 GSI/FAIR were re-organized
GSI/FAIR is today one single organization.
They are still two separate legal entities, but this is mostly relevant for lawyers and accountants, but otherwise not relevant anymore.
The legal merger will come.

## Slide 4: GSI/FAIR Project Re-Organization
The new joint GSI/FAIR organization, for a first time, provides proper communication paths between - civil construction - accelerator - experiments
Some initial phases of civil construction were done - construction area cleared - foundation pillars build but stalled afterwards
Civil construction is now back on track
  new construction manager: Uwe Kreische
  persons involved in CC are concentrated in one ‘task force’

## Slide 5: FAIR – Many Engineer Years Later

## Slide 6: Tunnel for SIS100 and (later) SIS300(+)

## Slide 7: G014 – Home for CBM and HADES

## Slide 8: Status Civil Construction
New tendering concept was accepted by BMBF
a funding pre-release of 203 M€ for CC approved by BMBF on September 13th 2016
1st CC lot went for tender on September 26th 2016 (water management and excavation)
2nd CC lot went for tender in November 22nd 2016 (shell construction ‘north area’, includes SIS100 and CBM)
start of excavation: mid-2017
start of shell construction: late 2017 / early 2018
The ball is rolling !! No project slippage anymore !!

## Slide 9: CBM Technical Design Report Status

## Slide 10: FAIR Baseline Schedule
Major consolidation of all planning done in 2016
Goal of the management was
  to create a conservative planning (“done not later than ”)
  to have, for a first time, an integrated planning
    civil construction
    accelerator
    experiments
  covering construction, installation and commissioning phases
  for GSI campus based activities also resource loaded
  which serves as baseline
  to substantiate the earlier statements
    buildings finished 2022
    FAIR operational 2025

## Slide 11: Planning Structure: CBM part
CBM_installation
STS_construction
TOF_construction
Contract 1a
Contract 1b
Contract 2a
Contract 2b
Level2_CBM
Management overview
Installation and
commissioning w/o beam
 CBM ready for beam
Detector construction  ready for installation
Contracting and procurement
FAIR CC PdR

## Slide 12: Planning Structure: Full Picture
Level2 CBM
Level1_FAIR
Level2 SIS100
Level2 HESR
shown to council
material for council
CBM_installation
STS_construction
TOF_construction
Contract 1a
Contract 1b
Contract 2a
Contract 2b
FAIR CC PdR
lots of planning for each sub-project
....

## Slide 13: FAIR Schedule
Major effort
Presented to FAIR council on December 6th, 2016
Very positive reception

## Slide 14: FAIR Schedule: SIS100 and CBM
The CBM bottom line:
  Dec 2021 to Jul 2022 1st installation window
  Dec 2022 Building acceptance
  Dec 2022 to Jun 2024 Installation & commissioning w/o beam
  Jun 2024 to Mar 2025 Commissioning beam from SIS100

## Slide 15: CBM Schedule: TOF Installation
The CBM bottom line (reminder):
  Dec 2022 to Jun 2024 Installation & commissioning w/o beam
  Jun 2024 to Mar 2025 Commissioning beam from SIS100
The CBM TOF bottom line:
  Apr 2023 to Jul 2023 Installation
There should be no schedule conflict with STAR-BES-II

## Slide 16: Little Heavy Detail: Beam Dump Iron

## Slide 17: The End
Thanks for your attention

## Slide 18
Backup Slides