## Slide 1: The Status of the CBM Experiment
Walter F.J. Müller, FAIR, Darmstadt
CBM Magnet CDR 22-24 May 2017

## Slide 2: CBM Technical Design Report Status

## Slide 3: FAIR Integrated Schedule
The integrated FAIR schedule
  covers civil construction, accelerator and experiments
  is based on a conservative planning (with buffers)
  for GSI activities also resource loaded
  serves as baseline
  key dates
    most building shells completed 2021
    all buildings fully commissioned 2022 (incl. services)
    FAIR operational 2025
Installation vs. Commissioning
  Installation window after building shell finished  only very basic services (crane ect)
  Commissioning window after building fully commissioned  all HVAC services available (Cryo comes later!)

## Slide 4: FAIR Schedule
Major effort
Presented to FAIR council on December 6th, 2016
Very positive reception

## Slide 5: FAIR Schedule: SIS100 and CBM
The CBM bottom line:
  Dec ‘21 to Jul ‘22 1st installation window
  Dec ‘22 Building acceptance
  Dec ‘22 to Jun ‘24 Installation & commissioning w/o beam
  Mar ’23 Cryo: DB2 cold; ready for cool down CBM
  Jun ‘24 to Mar ‘25 Commissioning beam from SIS100

## Slide 6: G014 – Home for CBM and HADES

## Slide 7: Full HADES+CBM Setup in CBM Cave
Dipol
Magnet
Time of
Flight
Projectile
Spectator
Detector
Silicon
Tracking
System
Micro
Vertex
Detector
Ring
Imaging
Cherenkov
Transition
Radiation
Detector
Muon
Detector
Electromagnetic Calorimeter
HADES
p+p, p+A
A+A (low mult.)
CBM
p+A, A+A

## Slide 8: CBM Cave – Cryogenic Distribution

## Slide 9: Superconducting Dipole Magnet
Large-acceptance superconducting dipole magnet.
The pole gap is 144 cm, the bending power 1 Tm.
Participating institutes: JINR Dubna, BINP Novosibirsk, GSI Darmstadt

## Slide 10: Silicon Tracking System
The STS consists of about 1000 double-sided silicon micro-strip sensors arranged in 8 detector arrays located inside the dipole magnet. The detector provides track reconstruction and momentum determination for up to 1000 particles per event. The detector is operated at about -10°C, heat dissipation of the front-end electronics 40 kW, bi-phase CO2 cooling system
Participating institutes: GSI, Darmstadt, JINR Dubna, KIT, INR Kiev, AGH and UJ Krakow, Univ. Tübingen, Warsaw UT
Silicon microstrip sensors CiS (Germany), Hamamatsu (Japan)

## Slide 11: Ring-imaging Cherenkov (RICH) Detector
The RICH is used for the identification of electrons with momenta below 8 GeV/c (pion suppression factor of > 500).
Participating institutes: Gießen, Univ., Wuppertal, PNPI Gatchina

## Slide 12: Muon Chamber (MuCh) System
The MUCH consists of a combination of 15 detector stations sandwiched between one carbon and 4 iron absorber layers for hadron suppression. The MUCH provides the identification of muons with momenta above 1.5 GeV/c.
  Tracking station 1+2: Two Gas-Electron-Multiplier (GEM) detector triplets
  Tracking station 3+4: two low-resistivity trigger RPC triplets
  Tracking station 5: four Transition Radiator Detectors (used only as trackers)
Participating institutes: VECC Kolkata + 12 Indian Inst., PNPI Gatchina
Full size GEM detectors tested with free-streaming read-out electronics at the CERN-SPS Nov.-Dec. 2016

## Slide 13: CBM Geometry
STS must fit in Magnet
  height: 1440 mm
  width: 3000 mm
  support rails !!
RICH
  sensitive to stray field
   field clamps
MUCH
  very close to yoke
   field clamps must be removed

## Slide 14: CBM Magnet – Geo to STS I

## Slide 15: CBM Magnet – Geo to STS II

## Slide 16: The End
Thanks for your attention

## Slide 17
Backup Slides

## Slide 18: CBM: Installation Plan I

## Slide 19: CBM: Installation Plan II

## Slide 20: CBM: Installation Plan III

## Slide 21: CBM: Installation Plan IV

## Slide 22: Little Heavy Detail: Beam Dump Iron