## System Overview
PSP code | Component | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.02 | Cluster Jet Target |  | Full setup of cluster generator & beam dump | Target beam adjustment, optimisation of target thickness and vacuum conditions. |  | on time | ok
Please mark changes in blue

## Pellet
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.01.5.1 | Pellet tracking system | Setup of one complete tracking section | TDR approved. Design performance proven by prototype measurements and by detailed system simulations. | Prototype running at UPTS. Preparing a complete tracking section (upper). Preparing for test of measurement modules for cluster-jet monitoring (see PSP 1.4.1.02.1.5). | funding | Risk of delay (lack of funding)
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks

## Cluster
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.02.1.1 | Cluster target generator (A. Khoukaz, WWU Münster) | Long-duration measurements; systematic target optimisation; test of highest target thickness and vacuum situation | Full vertical setup and operation with scattering chamber and final beam dump. Stable target beams. Setup and routine operation of a Mach-Zehnder interferometer for jet beam studies. | Target beam adjustment, vacuum and beam optimisation studies. Development of new nozzle production processes. Tests with different nozzles. Jet beams studies using a new Mach-Zehnder interferometer. Preparation of a Mie-setup for cluster size determination. | Very recently broken hydrogen purifyer. | on time
1.4.1.02.1.2 | Roots Pumping system (A. Khoukaz, WWU Münster) | Development of a remote control solution. | Fully in operation | routine operation |  | on time
1.4.1.02.1.3 | Electronic rack for cluster generator (A. Khoukaz, WWU Münster) |  | Installation of main components |  |  | on time
1.4.1.02.1.4 | Communication line between cluster target components (A. Khoukaz, WWU Münster) |  | Full direct and remote control of target devices |  |  | on time
1.4.1.02.1.5 | Test of the cluster target at the internal COSY beam (A. Khoukaz, WWU Münster) | Installation at COSY | Work loads defined; Proposal for beam time at COSY accepted | Preparation for installation at WASA-at-COSY target place | Delay due to broken hydrogen purifier and nozzle blocking. | risk of delay
1.4.1.02.1.6 | Slow control for local cluster target tests in Münster (A. Khoukaz, WWU Münster) | Full direct and remote/automatic control of target devices | Full access to all target devices | Programming of an user interface |  | on time
1.4.1.02.2.1 | Gas supply system (J. Zmeskal, SMI Vienna) | Prototype of a hydrogen purifier for high gas pressures and high gas flows | Cluster target in operation with a test gas supply system in Münster (gas flow/pressure limitation) | Design of the final PANDA gas supply system | Funding by Austria. Broken purifier in Münster | on time
1.4.1.02.3.1 | Beam dump (A. Khoukaz, WWU Münster) | Adaption to PANDA: design studies on vacuum chamber + frame modification; installation of monitoring devices | First version of cluster beam dump available and in routine operation | Tests with cluster beam at Münster | One turbo pump broken (no spare device) | on time
1.4.1.02.4.1 | Slow control system (B. Zwieglinski, NCBJ Warsaw) | Signing tripartite In-Kind Contract FAIR-NCBJ-JU Krakow for the Slow control system | In-Kind Contract submitted, signed by FAIR GmbH and NCBJ, stalled at JU-Krakow. Progress achieved in questions raised by JU-Krakow | Negotiations on the modified work schedule caused by the delay in project's starting date. | Mediation of the FAIR lawyer to come to an amendment of the contract satisfying all parties and opening the way to its signing | on time
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
Vacuum Situation at the PANDA Interaction Point | possible (po) <20% | moderate (mo) | Residual gas at the PANDA interaction point, originating from both the target source as well as from the target beam dump due to back streaming, must be reduced as much as possible. A too high gas background can introduce antiproton beam losses and background events. | Residual gas at the IP reduces the antiproton beam lifetime and gives parasitic interactions with the accelerator beam increasing the experimental background. | Test of the beam dump at the PANDA cluster target generator. Improvement of the pumping speed and/or reduction of orifice diameters. Introduction of additional pumping stages.

## MVD
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.03. | WP1-strip-sensors |  | strip sensors for the barrel 3-validation |  |  | done !
1.4.1.03 | WP2-strip-electronics on det. |  | Validation of the first PASTA prototype | PASTA test ongoing | radiation damage hardness to be verified | on time for Installation in 2023
1.4.1.03. | WP3-strip-supermodule mounting |  |  | under design | there is not enough space for the services | on time for Installation in 2023
1.4.1.03 | WP4-strip-cooling |  |  | under design |  | on time for Installation in 2023
1.4.1.03. | WP5-pixel-sensors |  |  | stand-by |  | on time for Installation in 2023
1.4.1.03 | WP6-pixel-electronics on det |  |  | Analysis of alternative technologies for ToPix | Limited space for the optoelectronics boards and the routing and cooling piping. Stand-by of Torino group | on time for Installation in 2023
1.4.1.03. | WP7-pixel-bump bonding |  |  | stand-by |  | on time for Installation in 2023
1.4.1.03 | WP8-pixel-supermodule mounting |  |  | stand-by | the pixel modules S6 near the cone in the barrel2 must be replaced with S5 because the routing with supply lines and hybrids it is not possible. There is not enough space for the services. | on time for Installation in 2023
1.4.1.03 | WP9-pixel-cooling |  |  | stand-by |  | on time for Installation in 2023
1.4.1.03. | WP10-MVD assembly |  |  | integration design underway | project design -man power lack | on time for Installation in 2023
1.4.1.03 | WP11-cooling plant |  |  | stand-by |  | on time for Installation in 2023
1.4.1.03 | WP12-power supplies |  |  | under evaluation |  | on time
1.4.1.03 | WP13-counting room electronics |  | change of responsible | collection of information | Lack of manpower | on time for Installation in 2023
1.4.1.03 | WP14-DCS |  |  |  | Lack of manpower | on time for Installation in 2023
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
Pixel part | Likely | Severe | Critical situation of the MVD group of Torino in a stand-by position in the INFN. Lack of man power and expertise. | The pixel detector components cannot be produced and the pixel detector cannot be built. Although the Turin group will restart the job, delays have to be taken into account. | The finalization of the FAIR problems. Subsequent contact with the INFN management for a recovery of the critical situation of the MVD group of Torino. Alternative solution: new/additional manpower and expertise; involvement of new groups
MVD mechanics | Likely | Severe | As before. In addition retirements of two mechanics designers, pillars of the project | Lack of man power and expertise. Delay in the service design | New manpower/ expert people
MVD cooling system | Likely | Severe | As before for the Torino group. Retirement of the expert person for the strip part cooling | Lack of man power and expertise. Delay in the construction | New manpower/ expert people
Slow control | Likely | Severe | The person of Julich responsible of the slow control has been moved to an othe r business. | Lack of man power and expertise. Delay in the construction | New/additional manpower/ involvement of new groups
Electronics off-detector | Likely | Severe | The person of Julich responsible of the slow control has been moved to an othe r business. Limited manpower | Lack of man power and expertise. Delay | New/additional manpower/ involvement of new groups
Strip readout | Likely | Severe | Absence of electronic designers of PASTA in the future (Julich and Giessen). As before for the Torino group. | Lack of man power and expertise. Delay | New/additional manpower
MVD services | Likely | Severe | Interference with BWE | we cannot operate the whole MVD | the volume around the beam pipe has to be revised

## STT
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.04.1 | Mechanical system | Q2/2018 |  | Set up pre-series system (in prototype mechanical frame) |  | delayed
1.4.1.04.1.1 | Mechanics - Straw series production |  | Pre-series straw production finished | Series production ongoing, long-term QA |  | on time
1.4.1.04.1.2 | Mechanics - Straw module construction |  | First straw test modules assembled | Positioning of all straw modules, layout of stereo layer modules | Final dimensions of STT have to be granted | on time
1.4.1.04.1.3 | Mechanics - Mechanical frame system |  | General layout and installation scheme | Frozen due to lacking manpower and funding | Manpower and funding not existing | delayed, plan to resume in 2017 seems unrealistic
1.4.1.04.1.4 | Mechanics - Prototype frame system |  | Available | Preparation of test mounting |  | on time
1.4.1.04.2 | Electronic readout | M8 Q1/2018 |  | Set up pre-series system
1.4.1.04.2.1 | Electronics - ASIC/TRB readout (time-over-threshold) | ASIC performance tests, pre-series system set up | PASTTRECv1 & TRB3 readout system (144ch) tested in-beam, dE/dx separation power by time-over-threshold demonstrated with beam | Set up pre-series system, re-design ASIC-FEB bonding by company ongoing (manually done before) | Man power situation very critical | on time
1.4.1.04.2.1.1 | Electronics - ASIC |  | PASTTRECv1-ASIC design verified over large dE/dx range, no design iteration required (pre-lim) | Tests of ASIC performance, improvements of ToT-resolution |  | on time
1.4.1.04.2.1.2 | Electronics - Frontend boards |  | ASIC on FEB machine bonding done by company, re-adjust QA for FEBs, | Cooling concept, iteration of FEB design for smaller board size |  | on time
1.4.1.04.2.1.3 | Electronics - TRB3 time readout system |  | ASIC control via TRBv3 system. TRBv3 system tested and prepared for preseries tests. TDC with time resolution <1 ns achieved. | Reliability tests | TRB3 readout at full PANDA luminosity will require new TRB HW design (data rate).TRB3 readout sufficient for the starting years with lower luminosity. | on time
1.4.1.04.2.2 | Electronics - ADC/FPGA readout (pulse shape sampling) | Pre-series system in Q1/2017 | Conceptual design approved by 14ch test board | Work plan for pre-series system set up, ADC board in production | Man power situation for full system design, FPGA readout at high rates | delayed
1.4.1.04.2.2.1 | Electronics - Transimpedance amplifier |  |  | Design of transimpedance amplifier, integration in ADC system, tests in-beam (Nov. 2017) |  | delayed
1.4.1.04.2.2.2 | Electronics - High voltage distribution |  |  | Design |  | delayed
1.4.1.04.2.2.3 | Electronics - ADC/FPGA readout system |  | Final ADC chip (pipeline ADC) and FPGA chip defined (testboard) |  |  | delayed
1.4.1.04.3 | Supplies - Gas system |  | Basic layout scheme completed | Front-end supply layout (manifolds) |  | on time
1.4.1.04.4 | Supplies - High voltage system |  | Basic layout scheme completed | Components identified |  | on time
1.4.1.04.5 | Control - Detector control system |  | Basic layout scheme completed | List of sensors, detailed scheme after STT readout decision |  | on time
1.4.1.04.6 | Tests - In-beam |  |  |  |  | on time
1.4.1.04.7 | Tests - Pre-series | M8 Q2/2018 |  |  | Critical man power for pre-series tests & data analysis | high risk of delay
1.4.1.04.8 | Software - Developments |  | STT pattern recognition and tracking included in PANDARoot | Further developments frozen due to man power situation | Man power not existing | high risk of delay
1.4.1.04.9 | Phase-0 test system
1.4.1.04.9.1 | Straw series production, straw double-layers |  | Straw length defined, preparations for straw series production done | Planning & preparations started, 640 straws for STS1 (possible use for PANDA-FT4 later)
1.4.1.04.9.2 | Electronic readout system |  |  | ASIC/TRB readout system after STT pre-series tests completed
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
Lacking manpower for STT mechanical frame system design | Severe | Severe (se): essential objective of pillar not realized | Mechanical system design and installation scheme workout frozen due to lacking manpower and funding | Final STT mechanical system design and installation scheme postponed | First system test will be based on prototype frame
Time-over-threshold technique not sufficient for PID | Possible | Moderate (mo): several objectives affected | dE/dx resolution for PID not sufficient by time-over-threshold (ToT) technique or ASIC performance | Extra costs | Dedicated in-beam tests to optimize ToT methods. Backup solution with analog output and ADC readout. Results from 2016 beam tests demonstrate dE/dx separation capability
Lacking manpower for ADC-based readout system | Likely | Moderate (mo): several objectives affected | Design of non-standard high-voltage distribution/amplifier/ADC integration. FPGA programming for pulse analysis and readout at high signal rates. Data analysis of in-beam tests. | Delay, extra costs | Additional cooperation to increase man power in progress
Lacking manpower for PANDARoot software developments | Severe | Marginal (ma): sub-goal affected or only partly reached | STT-related software developments for PANDARoot, debugging of detailed detector geometry (materials), time based simulation | Delay
Lacking manpower for pre-series test data analysis | Likely | Marginal (ma): sub-goal affected or only partly reached | Dedicated in-beam test campaign and analysis of the test data to verify mech. setup and electronic readout system | Delay of pre-series test results and delayed decision for final electronic readout system

## GEM
Sub PSP-code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status | WP | Main-Task Item | Sub-Task Item | Detail | 1.4.1.4.2
1.4.1.4.2.01 | WP01_ProjectManagement |  | General design available | update, contact to Thai group | too small group and parallel activities | delayed | 1 | ProjectManagement |  |  | 0
1.4.1.4.2.02 | WP02_Design-System (General) |  | General design available | small updates | no support by other qualified personnel | delayed | 2 | Design | System | General | 0
1.4.1.4.2.03 | WP03_Demonstrator-Detector |  | design ready, funding aquired, first GEMs & PadPlanes (Demonstrator) delivered | waiting for next GEMs | GEM foils by polish in-kind partners, no personnel for tests, R & D funding critical | delayed | 3 | Demonstrator | Detector
1.4.1.4.2.04 | WP04_Prototype-Detector (full-size) |  | conceptual design | parts preparation, postponed until demonstrator finished |  | delayed | 4 | Prototype | Detector | full-size
1.4.1.4.2.05 | WP05_Finaltype-System (full-size) |  | conceptual design | CAD consolidation pending |  | delayed | 5 | Finaltype | System | full-size
1.4.1.4.2.06 | WP06_Mechanics-Detector (Body) |  |  |  |  | risk of delay | 6 | Mechanics | Detector | Body | 3
1.4.1.4.2.07 | WP07_Mechanics-Detector (Interaction(Shielding,Cathode)) |  |  | set up of production infrastructure |  | risk of delay | 7 | Mechanics | Detector | Interaction(Shielding,Cathode) | 3
1.4.1.4.2.08 | WP08_Mechanics-Detector (Amplification(GEM-Stack)) |  |  | planning of QA infrastructure, trying to gain synnergies between competing projects | lab-space constraints, budget constraints, other large-scale productions competing | delayed | 8 | Mechanics | Detector | Amplification(GEM-Stack) | 3
1.4.1.4.2.09 | WP09_Mechanics-Detector (Projection(Padplane)) |  |  | assembly pending | large area double sided multilayered PCB | delayed | 9 | Mechanics | Detector | Projection(Padplane) | 3
1.4.1.4.2.10 | WP10_Mechanics-Detector (Cooling) |  | proof of principle done | none |  | risk of delay | 10 | Mechanics | Detector | Cooling | 3
1.4.1.4.2.11 | WP11_Mechanics-Supplies (SuppliesConduit) |  | Demonstrator partially built and tested | none | optical links / interfaces | delayed | 11 | Mechanics | Supplies | SuppliesConduit | 3
1.4.1.4.2.12 | WP12_Mechanics-Support (Riddle) |  | Demonstrator partially built and functional | Adaptation to changed boundary conditions, CAM/CAM revision pending, market search started | efficent know-how transfer to industry, budget not assigned | risk of delay | 12 | Mechanics | Support | Riddle | 3
1.4.1.4.2.13 | WP13_Electronics-FrontEndChip (Development a/o selection) |  |  | none | no read-out chip available | delayed | 13 | Electronics | FrontEndChip | Development a/o selection | 3
1.4.1.4.2.14 | WP14_Electronics-FrontEndBoards (Digitizer) |  | XYTER based, version V4 under tested sucessfully (06,07/2016) | calibration test-stand & procedures | radiation hard version, overall size | delayed | 14 | Electronics | FrontEndBoards | Digitizer | 3
1.4.1.4.2.15 | WP15_Electronics-FrontEndBoards (Concentrator) |  | FPGA based FEB built & tested sucessfully | small series production (25 pcs) | radiation hard version, overall size | delayed | 15 | Electronics | FrontEndBoards | Concentrator | 3
1.4.1.4.2.16 | WP16_Electronics-FrontEndBoards (Synchronization) |  | external reference available | none | Interfaces to SODA and PANDA-DAQ | delayed | 16 | Electronics | FrontEndBoards | Synchronization | 3
1.4.1.4.2.17 | WP17_Electronics-ElectronicsRoom |  |  | none |  | risk of delay | 17 | Electronics | ElectronicsRoom |  | 3
1.4.1.4.2.18 | WP18_DetectorControlSystem-Hardware |  |  | trying to achieve external comittment (Thai collaboration) | no qualified personnel available, no R&D budget available | stalled | 18 | DetectorControlSystem | Hardware |  | 0
1.4.1.4.2.19 | WP19_DetectorControlSystem-Software |  |  | trying to achieve external comittment (Thai collaboration) | no qualified personnel available, no R&D budget available | stalled | 19 | DetectorControlSystem | Software |  | 0
1.4.1.4.2.20 | WP20_Infrastructure&Tooling |  |  | none | lack of personnel | stalled | 20 | Infrastructure&Tooling
1.4.1.4.2.21 | WP21_Supplies-electrical (HV, LV, Sensors) |  | Modules purchased | Assembly and tests of modules slowly progressing | More prototyping steps necessary than expected | risk of delay | 21 | Supplies | electrical | HV, LV, Sensors | 3
1.4.1.4.2.22 | WP22_Supplies (Gas) |  |  | none | lack of personnel | on time | 22 | Supplies |  | Gas | 3
1.4.1.4.2.23 | WP23_Supplies (Cooling) |  |  | none | lack of personnel | on time | 23 | Supplies |  | Cooling | 3
1.4.1.4.2.24 | WP24_Infrastructure-Cleaning (large-size US-bath) |  | Assembly slowly progressing | Assembly progressing | CE/TÜV certification (EX conditions) | on time | 24 | Infrastructure | Cleaning | large-size US-bath
1.4.1.4.2.25 | WP25_Infrastructure-GEM-QA (Gain curve (55Fe)) |  |  | trying to achieve synnergies between competing projects | multi-channel electronics | risk of delay | 25 | Infrastructure | GEM-QA | Gain curve (55Fe)
1.4.1.4.2.26 | WP26_Infrastructure-GEM+PP-QA (OpticalScanner) |  | pop done | trying to achieve synnergies between competing projects | multi-source funding, no qualified personnel available | risk of delay | 26 | Infrastructure | GEM+PP-QA | OpticalScanner
1.4.1.4.2.27 | WP27_Infrastructure-GEM-QA (HomogeneityScanner ((x,y),X-Ray)) |  | infrastructure set up, TÜV certification achieved | software development, waiting for OK by legal authorities | lab-space constraints | on time | 27 | Infrastructure | GEM-QA | HomogeneityScanner ((x,y),X-Ray)
1.4.1.4.2.28 | WP28_Infrastructure-Framing (ProductionUnit) |  | pop done | CAD consolidation, production & assembly, slowly progressing | process control, no support by engineers | delayed | 28 | Infrastructure | Framing | ProductionUnit
1.4.1.4.2.29 | WP29_Infrastructure-GEM-Currents (HV-loads) |  | pop done on other projects, modules purchased partially | assembly slowly progressing | high channel counts | on time | 29 | Infrastructure | GEM-Currents | HV-loads
1.4.1.4.2.30 | WP30_Software-Production (QA Documentation) |  | test database installed | set up of interim database solution, first test installation under investigation | lack of qualified personnel | on time | 30 | Software | Production | QA Documentation | 0
1.4.1.4.2.31 | WP31_Software-Offline (Simulation) |  | first results & refinements for benchmark channels | detailed studies ongoing |  | on time | 31 | Software | Offline | Simulation | 0
1.4.1.4.2.32 | WP32_Software-Offline (Reconstruction) |  | first results & refinements for benchmark channels | detailed studies ongoing |  | on time | 32 | Software | Offline | Reconstruction | 0
1.4.1.4.2.33 | WP33_Software-Online (DAQ) |  |  | none |  | risk of delay | 33 | Software | Online | DAQ | 0
1.4.1.4.2.34 | WP34_Software-Online (Analysis) |  | first results & refinements for benchmark channels | detailed studies ongoing |  | on time | 34 | Software | Online | Analysis | 0
1.4.1.4.2.35 | WP35_Documentation (RiskAssesment,TechnicalFile,CE) |  |  | clarification of boundary conditions | no personnel available | stalled | 35 | Documentation |  | RiskAssesment,TechnicalFile,CE | 0
1.4.1.4.2.36 | WP36_Documentation-TDR |  | Collection of materials has started | none | Need successful steps ahead | stalled | 36 | Documentation | TDR |  | 0
1.4.1.4.2.37 | WP37_Construction |  |  | none | no qualified personnel available | stalled | 37 | Construction
1.4.1.4.2.38 | WP38_Production-small size (GEM-DISC#1) |  |  | none | no qualified personnel available | risk of delay | 38 | Production | small size | GEM-DISC#1 | 3
1.4.1.4.2.39 | WP39_Tests-in-lab (Gas-tightness and -purity, HV-stability, homogeneity of response) |  |  | none | no qualified personnel available | risk of delay | 39 | Tests | in-lab | Gas-tightness and -purity, HV-stability, homogeneity of response | 0
1.4.1.4.2.40 | WP40_Production-medium+large size (GEM-DISC#2+3) |  |  | none |  | risk of delay | 40 | Production | medium+large size | GEM-DISC#2+3 | 3
1.4.1.4.2.41 | WP41_Assembly |  |  | none |  | risk of delay | 41 | Assembly |  |  | 4
1.4.1.4.2.42 | WP42_Tests, operation-in-beam (FZJ&Elsewhere) |  |  | none |  | risk of delay | 42 | Tests, operation | in-beam | FZJ&Elsewhere | 0
1.4.1.4.2.43 | WP43_Tests, radiation hardness -in-beam (FZJ&Elsewhere) |  |  | none |  | risk of delay | 43 | Tests, radiation hardness | in-beam | FZJ&Elsewhere | 0
1.4.1.4.2.44 | WP44_Transportation&Installation |  | pop of feasibility of external skelleton | none |  | on time | 44 | Transportation&Installation |  |  | 4
1.4.1.4.2.45 | WP45_Commissioning |  |  | none | qualified personnel | risk of delay | 45 | Commissioning |  |  | 4
1.4.1.4.2.46 | WP46_Documentation-FinalReport |  | Collection of materials has started | Collecting information | Need successful steps ahead | risk of delay | 46 | Documentation | FinalReport |  | 0
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks

## Barrel DIRC
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status | Tentative WP Leaders
1.4.1.05 | Radiators |  | Prototypes produced, bar geometry validated, plate geometry validation pending (beam test Oct/Nov 2016 plus possible beam test in 2017) | QA/validation, additional motivated vendor (Nikon) engaged, free sample being validated in DIRC lab. | Bar/plate fabrication notoriously delayed in other DIRCs. | risk of delay | Decision pending; J. Schwiening (GSI) for now
1.4.1.05 | Sensors |  | Lifetime-enhanced sensor found | Test alternate vendor (production of samples from third vendor delayed) | Sensor production could be delayed due to high demand - investigating alternate source and possibility of spreading production over longer time. | on time | Albert Lehmann, Erlangen
1.4.1.05 | Optics |  | Lens w/o airgap produced, prism performed well in beam tests | Testing lens performance, designing new 3-layer cylindrical lens for plate geometry. | First results from test of radiation hardness of lens material promising, safety factor >10 for PANDA. | delayed | Decision pending; J. Schwiening (GSI) for now
1.4.1.05 | Electronics |  | One full readout sector tested with particle beams and preliminary design (PADIWA/TRB). | Improving electronics performance, moving to final design | Final electronics design (DiRICH) still needs to be validated with MCP-PMTs. Production of DiRICH for CBM/HADES delayed. | risk of delay | Decision pending; J. Schwiening (GSI) for now
1.4.1.05 | Mechanics |  | First design exists | Start of R&D delayed to 2017 due to lack of funding | R&D for bar box built from carbon fiber material needed - bar polution? Need R&D funding. | delayed | Decision pending; J. Schwiening (GSI) for now
1.4.1.05 | Infrastructure |  | First design exists | Preparing for more detailed plan |  | on time | Decision pending; J. Schwiening (GSI) for now
1.4.1.05 | Prototypes |  | Bar performance meets requirements (CERN 2015), plate with prism looking promising but does not yet meet requirement | CERN beam test analysis showed that timing resolution insufficient for plate validation | Performed beam test for plate in Oct/Nov 2016 (analysis ongoing), will need one more beam test in Aug/Sep 2017, independent of ECE decision. | risk of delay | Decision pending; J. Schwiening (GSI) for now
1.4.1.05 | Offline Software: Simulation |  | In good shape, time-ordered sim added, plate design added as option, baseline design updated | Keep up with design improvements |  | on time | Decision pending; J. Schwiening (GSI) for now
1.4.1.05 | Offline Software: Reconstruction |  | In good shape, time-based imaging for narrow bar and wide plate works with simulation PDFs | Working on time-based imaging | Long-term project to add analytical PDFs for time-based imaging | on time | Decision pending; J. Schwiening (GSI) for now
1.4.1.05 | Online Software |  | No activity yet except for liaison | Looking for manpower | Need personnel | risk of delay | Decision pending; J. Schwiening (GSI) for now
1.4.1.05 | TDR | M3: 7/2017 | TDR submitted to FAIR in Sept. 2016 | Preparing report/TDR addendum on 2016 beam test for FAIR ECE, to be submitted late March/early April after review committee approval; feedback from FAIR, expected after May/June ECE session. | Still need more information for final plate/bar deometry design decision. | will be delayed due to delay in ECE process - propose to move milestone to 7/2017, date of likely next ECE meeting | Decision pending; J. Schwiening (GSI) for now
1.4.1.05 | Project management |  | In good shape | Maintenance |  | on time | J. Schwiening (GSI)
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
PANDA Barrel DIRC radiator production cost overrun | po | mo | DIRC radiator bars require very tight specifications on the optical and mechanical properties, making them difficult and expensive to produce. The PMA cost estimate was based on an unrealistic quote. Preliminary estimates from potential vendors suggest that a cost increase by a factor 2-3 is likely for radiator bar production. | Production cost overrun, delayed or only partial installation of barrel DIRC detector radiator bars. | We are investigating an alternate radiator design: using one wider plate instead of 5 narrow bars potentially reduces the cost by 40-60%. The new geometry, which has also been chosen by the Belle II detector, has to be tested and the performance verified in a prototype. The mechanical design of the Barrel DIRC has been modified to allow delayed or partial installation of the radiator boxes. Plate design still needs to be validated with prototype in particle beams. | New potential vendor identified in 2015, delivered a free test sample, validation ongoing
PANDA Barrel sensor ageing | un | mo | The photon detector has to tolerate large photon fluxes in a high magnetic field and measure single photons with good efficiency and timing below 100ps. The best candidate is the micro-channel plate PMT. Until 2011 commercially available MCP-PMTs survive for less than 1 year in the PANDA environment due to photocathode deterioration. | Additional cost for purchase of replacement for damaged sensors and timem required for access and replacement. | Recent improvements in the production process of the MCP-PMTs increased the lifetime of the prototype tubes to close to the required 10 year lifespan. Additional steps are taken to further improve the lifetime and the production yield, and therefore cost, for the new process. A second vendor has been engaged, ageing measurements have started. | Given the MSV luminosities it is likely that this risk can soon be considered resolved.
PANDA Barrel DIRC focusing optics | un | ma | The compact expansion volume requires efficient and precise focusing of the Cherenkov photons. Simple lenses provide a good focus at the cost of losing a large fraction of photons at the lens-air interface, unless a material with a high refractive index is used. These materials are not common to optical industry, difficult to machine and polish, and may not be radiation hard enough. Initial results suggest that the prefered material us most likely sufficiently radiation hard for PANDA. | Additional cost for purchase of replacement for damaged sensors and timem required for access and replacement. | Prototype lenses have been procured and their focusing properties evaluated in the lab and with particle beams. A test of the radiation hardness of the material is nearing completion.
PANDA Barrel DIRC insufficient manpower | li | mo | The number of FTEs currently available at the institutions contributing to the PANDA Barrel DIRC effort is insufficient for the transition from the R&D phase to the construction phase. The lack of BMBF funding in 2015++ is a serious concern. | Delays in the construction of the detector. | All groups involved in Barrel DIRC (Erlangen, GSI, Mainz) have applied for additional manpower without success. New applications are being prepared for the 2018-21 funding cycle. Additional groups are invited to join Barrel DIRC effort. The mechanical design of the Barrel DIRC has been modified to allow delayed or partial installation of the radiator boxes. | The personnel/funding situation at Mainz is particularly severe and has caused this group to suspend their contribution to the Barrel DIRC.
PANDA Barrel DIRC infrastructure | po | mo | The assembly of the DIRC bar boxes is currently foreseen to take place in the DIRC cleanroom in the new HIM building in Mainz. Should the Mainz groups not receive the necessary funding for personnel and consumables, it is unlikely that this space will remain available to the DIRC. | Additional cost for the construction of a new cleanroom area at GSI. Delays due to possible lack of manpower. | Discussions between Mainz University and HIM are ongoing. | The personnel/funding situation at Mainz is particularly severe and has caused this group to effectively suspend their contribution to the Barrel DIRC.

## SciTil
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.06 | Detector |  | nearly final. 55 ps (comp. the initial goal of 100 ps) reached | - |  | on time
1.4.1.06 | Radiation Hardness |  | Assesment positive from literature study | - | Man power, SiPM not radiation hard | on time
1.4.1.06 | Electronics |  | TOF-PET evaluation kit tested | working on a FEE prototype |  | risk of delay
1.4.1.06 | Mechanics |  | New CAD Drawing with connectors, cables | - |  | on time
1.4.1.06 | Infrastructure |  | Information updated with the new realistic SM design | - | Waiting for the freezing of the design | on time
1.4.1.06 | Prototypes |  | First prototype built | New improved prototype in preparation |  | on time
1.4.1.06 | Slow Control |  | - | - |  | on time
1.4.1.06 | Offline Software: Simulation |  | Time based simulation, PID | physics simulation using SciTil |  | on time
1.4.1.06 | Online Software |  | online t0 algorithm with SciTil, relative TOF | event sorting algorithm |  | on time
1.4.1.06 | TDR | M3: 12/2016 | Internal review done, committee reccomends submission to FAIR | Preparing the version to be submitted to FAIR |  | on time
1.4.1.06 | Project management |  |  |  |  | on time
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
SiPM radiation hardness not sufficient | Possible (po): 10% -- <20% | Moderate (mo): several objectives affected | Sensor performance may deteriorate within the PANDA lifetime | time resolution becomes worse, detection efficiency becomes lower | Take enough safety margin to torelate the performance deterioration | current prototype shows ~50 ps time resolution in comparison to the design goal of 100 ps. The threshold can go from 20 mV up to 50 mV while not influencing the time resolution. This torelates higher noise
Funding | Possible | Critical | Negotiation with Austrian ministery needs to be restarted |  | Support from PANDA/FAIR necessary | Funding period 2018-2020

## FT
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.07 | Prototyping |  | Three modules for FT1 assembled and tested with high intensity proton beam | Construction of prototype of FT5 comprising one half frame equipped with 12 modules |  | on time
1.4.1.07 | Electronics |  | New version of FE ASIC produced and tested | Design of modified front-end card with removed connectors for analog outputs |  | on time
1.4.1.07 | Production facilities |  | Equipment for production of straw tube modules is prepared. |  |  | on time
1.4.1.07 | Tracking simulations |  | Pattern recognition code prepared | Simulation of benchmark channels |  | delayed
1.4.1.07 | TDR | M3:Q2/2017 | written in ~90% | Finalizing the TDR |  | delayed
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
straw tube aging | possible | loss of detection efficiency | The present limit for operating the PANDA straw tubes without observable aging of 1C/cm only marginally satisfies requirements for the FT | Performance loss after a few years of operation of the FT, potential need for replacement of modules with the highest radiation levels. | Extend the aging limit for safe operation of straws: studies of aging at doses exceeding 1C/cm, minimizing gas gain

## Disc DIRC
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status | Responsible
1.4.1.08.1.1.1 | WP1.1 (Optics, Radiator) |  | Inhouse QA measurements available, negotiations with different suppliers | integration | Impact of outgassing, rise in prices | on time | E. Etzelmüller
1.4.1.08.1.1.2 | WP1.2 (Optics, FLGs) |  | Prototypes meet specifications, inhouse QA measurements available | integration | Delivery time, rise in prices | on time | E. Etzelmüller
1.4.1.08.1.2 | WP2 (Mechanics) |  | Conceptual design | Working on a detailed design | none | on time | E. Etzelmüller
1.4.1.08.1.3 | WP3 (MCP-PMTs) |  | Prototypes meet specifications, inhouse QA measurements available, magnetic field tests done | evaluate a new photocathode option | manpower, rise in price | risk of delay | K. Föhl
1.4.1.08.1.4 | WP4 (Readout, ASICs) |  | Conceptual design finished | Working on a detailed design | Hardware for data output, manpower | risk of delay | new PhD
1.4.1.08.1.5 | WP5 (FEE, other than ASICs) |  | Conceptual design finished | Working on a detailed design, implementation on a PCB | Front End ASIC needs development, manpower | risk of delay | new PhD
1.4.1.08.1.6 | WP6 (Slow Control, DCS) |  | Standalone Programs for HV exist | Final version of source (HV, LV) to make it in EPICS | none | on time | A. Hayrapetyan
1.4.1.08.1.7 | WP7 (Calibration) |  | Prototype was tested | MC simulation is ongoing | Radiation hard quartz fibers | on time | A. Hayrapetyan
1.4.1.08.1.8 | WP8 (Simulation + Reconstruction) |  | Full Simulation of the EDD available | Extended studies, add passive detector material, compare backup design options | none | on time | M. Schmidt
1.4.1.08.1.9 | WP9 (Online PID + Trigger) |  | Basic concepts | In development | Processing speed | on time | M. Schmidt
1.4.1.08.1.10 | WP10 (Prototype) | M8: Q2/2020 | Improved prototype with ROMs but small radiator succesfully tested | Add additional FLGs and evaluate the prototype using cosmic muons | Insufficient funding | on time | M. Schmidt
1.4.1.08.1.11 | WP11 (TDR) | M3: Q4/2017 | Internal Design Report reviewed | Write TDR until 06/2017 | none | on time | E. Etzelmüller
1.4.1.08.1.12.1 | WP12.1 (EDD Quadrant) | M10: Q1/2023 | - | - | Successful TDR | on time | M. Düren
1.4.1.08.1.12.2 | WP12.2 (Full EDD) | [5 empty] | M. Düren
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
ASIC chips | unlikely (un) | marignal (ma) | The prospective ASIC chips for readout of MCP-PMTs do not meet the required specifications | Performance loss and delay, because more development iterations are needed | The design work starts with known and tested ASIC designs as building blocks. To mitigate the risk more manpower could be assigned | seems to work

## FTOF
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.09. | Electronics |  | TRB-3 with PADIVA-2 tested using SiPMs, TOT correction | TRB-3 with PADIWA-A as final variant to test with PMTs | Need personn | on time
1.4.1.09. | Mechanics |  | preliminary design |  | Need personnel | on time
1.4.1.09. | Infrastructure |  | under consideration | Procurement of fast light generatorfor for latency online monitoring. Design time calibration system |  | on time
1.4.1.09. | Prototypes |  | beam tests complited. 70 ps time resolution obtained | Final decision on PMT type, contacts with Hamamatsu, Bicron firms | Need personnel | on time
1.4.1.09. | Offline Software: Simulation |  | PANDAROOT Count rates, TOF detector interplay finished | Light propogataion (aparatus) MC |  | on time
1.4.1.09. | TDR | M3: 9/2017 | Main parts finished | finalizing text including TRB-3 tests and apparatus MC | more help in TDR drafting from dc | on time
1.4.1.09. | Project management |  | In good shape | TRB-tests, TDR finalization. |  | on time
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
Effect of dipole magnetic field | small <1% | no | magnet protected PMT housing has not yet directly tested | PMT signal drops down | direct control of housing sing realistic magnetic stray field
worsenning time resolution in data taking period to some 100ps | <10% | no | This may come come latency imstability, FEE temperature instability, agingof optical contacts etc. . | Hadron PID related to FTOF worsening | Thorough maintennence of latency calibration, mechanical stability of PMTs, temperature stability FEE (TRB+PADIWA)
Man power insuficient | <20% | possible | Serious problems in PNPI with experienced physicists will be by the PANDA commisioning time. Difficulties to hire young PhD persons.Unpreditctible situation with travel money.to participate in PANDA startup and datataking | problems with FTOF tests, calibration, maintennence | Getting additional Funding, Propaganda PANDA experiment physics.

## Barrel EMC
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.10.1 | WP1 Mechanics |  | Contract, mechanical design, parts for 1st slice delivered | Alveole production, preproduction slice | Verification of mechanical design (see WP8) | risk of delay
1.4.1.10.1 | WP2 Detectors |  | 3000 crystals, one complete slice; purchase of PWO raw material | Test crystals from CRYTUR/SICCAS | Crystal production funding | risk of delay
1.4.1.10.1 | WP3 Photosensors |  | APD contracts, 25% APD delivered, ~1500 ready to use | screening, APD irradiation, glueing | APD funding, APD screening | risk of delay
1.4.1.10.1 | WP4 Electronics |  | ASIC validated and produced | ADC prototype testing, HV distribution boards, serial adapter chip | Cables to ADCs, position of ADCs,preseries FE flex boards | delayed
1.4.1.10.1 | WP5 Cooling system |  | Setup cooling system for one slice at Orsay |  | Responsibilities cooling system | risk of delay
1.4.1.10.1 | WP6 Monitoring and Control |  | THMP,Sensors, LP prototype | Tests of fibre coupling | Integration of stimulated recovery, coupling light fibres to crystal, routing | on time
1.4.1.10.1 | WP7 Software |  | Basic feature extraction, PANDAroot code | Analysis Proto120 test beam | lack of person power | risk of delay
1.4.1.10.1 | WP8 System | M8: 12/2017 | Proto120 beam tests | assembly of first slice | beam test analysis | risk of delay
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
Verification of mechanical design | Very likely | moderate | Freeze for the slice design can be indicated only after the successful verification of the design of all components within the slice. | Delay for commissioning of first slice. Violation of contract deadlines with russian partner. | Intensify work on finalizing electronics and cooling design. Implies to increase manpower and funding
Crystal production | Very likely | business critical | production of 8500 crystals not assured by funding yet. Decision of mass production required. | Delay of production or bailout of production company (Crytur) when R&D funding is interrupted. Potential price increase of >50% when decision of mass production delayed beyond mid 2017. | identify funding source. Expression of willingness for mass production of crystals.
APD funding | Very likely | severe | 17000 APDs are to be funded. BMBF funding on hold/not yet granted, Austrian funding for 5400 APDs not yet available. | Severe delay and/or abruption of the production of multiple slices, APD production line at Hamamatsu needs startup time (~3 month) after begin of funding, delay of screening | identify funding source | No Austrian funding up to 2017
APD screening | Likely | moderate | APD sensors can not be fully characterized within the foreseen time plan. Delay of screening from APD lab and increasing lack of manpower assigned to irradiation in Giessen | probable delay of commissioning of series slices (not first slice). Minor impact on calibration procedures between APDs during operation | Develop additional online and offline energy calibration procedures before start of operation | 1 PhD might join QA at GSI ? 1 PostDoc might be added in the future?
Signal cables | Possible | moderate | signal cables are still in R&D phase. Feasibility of production of those cables with critical requirements is unsure | redesign of entire r/o chain beyond the FE-electronics. Relocation of ADCs into the slices probable | Design of modified ADCs fitting into slice volume | This item also impacts the first risk item “Verification of mechanical design”
Responsibilities cooling system | Very likely | moderate | There is no group or person currently working considerably on the development of the barrel cooling system | delay of the design freeze for the slice mechanics, assembly and integration | Assign manpower to this task
beam test analysis | Likely | moderate | Currently not enough personel working on software and protype analysis due to strong cut in funding | delay of the design freeze for the slice mechanics, assembly and integration | raise funding/persons for this task
electronics production | Likely | moderate | Production of preseries slice FE electronics (ASIC FE flex PCBs) delayed by 3 months due to administrative procurement problems | delay of the design freeze for the slice mechanics, assembly and integration | unknown

## BE EMC
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status | WP responsible
1.4.1.10.2.1 | Prototype | M8: 7/2017 | Design, Construction & assembly | Test & validation |  | on time | Luigi Capozza
1.4.1.10.2.2 | Mechanics |  |  | Design | Mechanical integration | on time | David Rodríguez
1.4.1.10.2.3 | PbWO crystals |  | All crystals available |  |  | on time | Valera Dormenev
1.4.1.10.2.4 | Photosensors |  | APD purchased | Screening |  | on time | Andrea Wilms
1.4.1.10.2.5 | Electronics & supplies |  | Preamplifier validated | Final FEE, optical system |  | on time | Luigi Capozza
1.4.1.10.2.6 | Cooling |  |  | Design |  | on time | David Rodríguez
1.4.1.10.2.7 | Software |  |  | APFEL feature extraction |  | on time | Oliver Noll
1.4.1.10.2.8 | Monitoring & control |  |  | ASIC control, EPICS integration |  | on time | Oliver Noll
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
Mechanical Integration | 100% | Business critical | Due to an increase of the MVD service cross section requirements the inner hole of the BE has to be enlarged. | Loss of an undefined amount of crystals. Reduciton of solid ange acceptance. Delay in the final design and construction. Funding issue for purchasing again already available tools. | Wait for the MVD design to be better defined. | There is a severe problem in the way agreements are made. Many meetings, exchange of information and public presentation in a Technical Board level were not enough in order to fix numbers.
Mechanical Integration | 40% | Severe | Due to an increase of the STT space requirements for cable routing in the BW region, the BE might be shifted upstreams by 50 mm (current, not dfinitive number). | Loss of hermiticity due to an increase of the gap between BE and barrel EMC. Reduction of the solid angle coverage. | Wait for the STT cable routing to be better defined. | MC symulations are needed for evaluating the impact of this change (and in general of the BE EMC) on the physics performance.

## FE EMC
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.10.3 | WP1 Mechanics |  | Backplate, inserts, alveoli, support frame | Inner isolation support, frame for beam tests |  | on time
1.4.1.10.3 | WP2 Detectors |  | All crystals ready | All crystals stored in Bochum |  | on time
1.4.1.10.3 | WP3 Photosensors |  | APD delivered, VPTTscreened, glueing procedure with primer fixed | VPTT matching | APD screening/matching | delayed
1.4.1.10.3 | WP4 Electronics |  | Prototypes, HV Filter, VPTT preamplifier, APD preamp gain fixed | Shaper/SADC prototype testing, distribution boards, SADC tendering |  | on time
1.4.1.10.3 | WP5 Cooling system |  | Setup cooling system at Orsay, 90% of VIPs ready | Operation of cooling system in Bochum |  | on time
1.4.1.10.3 | WP6 Monitoring and Control |  | THMP,Sensors, LP prototype | Production & calibration, test of LED cabling for stimulated recovery | Integration of stimulated recovery with APD | on time
1.4.1.10.3 | WP7 Software |  | EPICS, Basic feature extraction, PANDAroot code | Firmware testing | Online filter software, PANDAroot code updates | on time
1.4.1.10.3 | WP8 System | M9: 3/2018 | Funding for 2016/2017 secured | Start VPTT submodule production |  | on time
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
APD screening | likely | moderate | APD sensors can not be fully characterized within the foreseen time plan. Delay of screening from APD lab and increasing lack of manpower assigned to irradiation in Giessen | delay of assembly of alveoli and mounting at the forward endcap | Improve speed of analysis of screened APDs. Concentrate on APDs from same lots, which can be matched more easy. | 1 PhD might join QA at GSI ? 1 PostDoc might be added in the future?
APD screening insufficient results for matching | likely | moderate | HV settings for APDs might not be available before glueing APDs. | APDs are not perfectly matched. Loss of dynamic range and increased signal to noise range. | Develop in situ HV supply for single (unmatched) APDs | Work ongoing at Bonn University

## FSC
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.11 | WP1 Mechanics |  | 3D model design completed | more detailed design |  | risk of delay
1.4.1.11 | WP2 Detectors |  | Prototype met the goal requirements | engineering drawings preparation |  | risk of delay
1.4.1.11 | WP3 Photosensors |  | Hamamatsu R7899 Is tested with detector prototype at the test beam | Testing new PMT bases |  | risk of delay
1.4.1.11 | WP4 Electronics |  |  | general design | ADC for pre-series prototype | risk of delay
1.4.1.11 | WP5 DCS |  | prototype of the control unit is tested | system design for pre-series prototype |  | on time
1.4.1.11 | WP6 light monitoring system |  | prototype is tested | design of the mechanical parts |  | on time
1.4.1.11 | WP7 Software |  | FSC is implemented in PandaRoot | bugs hunting |  | on time
1.4.1.11 | WP8 TDR | M4:06/2017 |  | TDR approved, contract preparation to build the detector
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
pre-series prototype ADC | Likely | Moderate | ADC prototype should be in time for the pre-series FSC prototype tests to validate the readout design | Delay of the FSC modules mass production | Find commercially available ADC module with smilar parameters to test pre-series prototype

## Lumi
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.12.1 | Design | M3: 6/2017 |  |  |  | on time / risk of delay
1.4.1.12.1.1 | Mechanics and Vacuum |  | Mechanical prototype for vacuum box, linear shift mechnism and inner beampipe working stable, Design of new prototype vacuum box ready | New prototype box and modification of the new linear shift mechanism under construction, vacuum steering automatisation |  | on time
1.4.1.12.1.2 | Cooling |  | Cooling prototype working and proved that heat can conducted away | Complete half detector setup for tests |  | on time
1.4.1.12.1.3 | Electronics |  | Starrflex cable prototypes tested, flexprints arrived | Testing of the flex prints prototypes, PCB in development, Radiation hardness tests |  | on time
1.4.1.12.1.4 | HV-MAPS |  | MuPix7 tested in HD, Teleskop tested successfully | MuPix8 in production, expected 04/2017 | More prototyping steps necessary than expected | risk of delay
1.4.1.12.1.5 | DCS |  | all (except HV-MAPS-DCS) available with OPI, design of overheat protection ready | DCS of HV-MAPS, waiting for final chip |  | on time
1.4.1.12.1.6 | DAQ |  | DAQ for 4 MuPix6 chips with TRBv3 without SODA for readout of our telescope | Extension to MuPix8 | Interfaces to SODA and PANDA-DAQ | risk of delay
1.4.1.12.1.7 | Software |  | Luminosity extraction software (offline) ready incl. systematic uncertainties | Online trigger with GPU, alignment procedure |  | on time
1.4.1.12.2 | Prototyping | M8: 03/2018 | see above | see above |  | on time / risk of delay
1.4.1.12.3 | Prototype Detector |  |  |  |  | on time
1.4.1.12.3.1 | Construction | 12/2017 |  |  |  | on time
1.4.1.12.3.2 | Test an COSY | 06/2018 |  |  |  | on time
1.4.1.12.4 | Final Detector | M12: 12/2019 |  |  |  | on time
1.4.1.12.4.1 | Production |  |  |  |  | on time
1.4.1.12.4.2 | Assembly |  |  |  |  | on time
1.4.1.12.4.3 | Transportation/Installation |  |  |  |  | on time
1.4.1.12.4.4 | Commissioning |  |  |  |  | on time
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
LUMI Vacuum | unlikely | severe | If the transition foil breaks, material in the lumi vacuum will be in the beam pipe vacuum. Detector component could be damaged. | Damage of the Lumi detector component, no luminosity measurement, vacuum in the beam pipe gets worse | Testing and prototyping.

## Muon
Sub-PSP code | WorkPackage(*) | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.13 | WP1 (preparation) | M4: 6/2017 | main producers of MDT's components are known/ready | search for the building/area for the workshop installation | building/area and funding for the workshop installation | risk of delay
1.4.1.13 | WP2 (detectors) | M4: 6/2017 | MDTs are tested in prototypes | beam test of big prototype at CERN | second coordinate readout (noise) | risk of delay
1.4.1.13 | WP3 (structures) | M4: 6/2017 | general understanding exists |  | not defined (simple mechanics) | risk of delay
1.4.1.13 | WP4 (analog FEE) | M4: 6/2017 | most of analog cards are tested | R&D development of ASIC chip | test of 2nd coordinate FEE cards | risk of delay
1.4.1.13 | WP5 (digital FEE) | M4: 6/2017 |  | conceptual design is in progress | not defined | risk of delay
1.4.1.13 | WP6 (transportation) |  |  |  |  | risk of delay
1.4.1.13 | WP7 (software) |  |  | GEANT model is in progress |  | generally on time
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
absense of funding for the project | 100% (fact) | potentially severe | absence of the project money despite technical approval of the project by FAIR | serious delay of the mass production start | continuation of detector and electronics R@D, and supporting the contacts with industrial companies | solution is in the hands of FAIR and Rosatom management
absense of MDT assembly workshop | 100% (fact) | serious | assembly building planned for the PANDA MDTs is occupied by other activity | serious delay of the mass production start | negotiate with JINR directorate some other building/area | high level of JINR-FAIR cooperation assumes that solution should be found

## HYP
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.14.1 (primary target) | Electronics |  | Operation of step motors in vacuum, beam test at COSY | preparation of the online monitoring system | Need personnel | on time
1.4.1.14.1 | Mechanics |  | mechanical stability in vacuum | construction and implementation of primary target holder, monitoring devices | Need personnel | on time
1.4.1.14.1 | Infrastructure |  | first design |  |  | on time
1.4.1.14.1 | Prototypes |  | first design of chamber with different foils, monitoring system designed | under construction | Need personnel | on time
1.4.1.14.1 | Offline Software: Simulation |  | In good shape | Keep up with design improvements |  | on time
1.4.1.14.1 | Online Software |  | online monitoring procedure not yet decided | in preparation | Need personnel | on time
1.4.1.14.1 | TDR | M3: 8/2016 | Collection of materials has started | Writing text, collecting information |  | on time
1.4.1.14.1 | Project management |  | In good shape | Maintenance |  | on time
1.4.1.14.2 (secondary target) | Absorbers |  | stability test Boron Carbide and CFC layers under high vacuum conditions |  | Need personnel | on time
1.4.1.14.2 | Sensors |  | operation of a double sided microstrip detector | readout of double sided microstrip detector with long kapton cables | Need personnel | on time
1.4.1.14.2 | Electronics |  | Operation of a single composite structure with a single-layer readout | FEE Board in preparation, considering cooling options | Need personnel | on time
1.4.1.14.2 | Mechanics |  | First design | further design of holding structure | Need personnel | on time
1.4.1.14.2 | Infrastructure |  | Planning for cabling and supplies not started yet | Preparing for design |  | on time
1.4.1.14.2 | Prototypes |  | performance meets requirements | Geometry and tracking volume optimization |  | on time
1.4.1.14.2 | Offline Software: Simulation |  | In good shape, | Keep up with design improvements |  | on time
1.4.1.14.2 | Offline Software: Reconstruction |  | In good shape, | Tracking algorithm optimization, Prepare time-ordered reconstruction | Need personnel | on time
1.4.1.14.2 | Online Software |  | No activity yet |  | Need personnel | on time
1.4.1.14.2 | TDR | M3: 8/2016 | Collection of materials has started | Writing text, collecting information |  | on time
1.4.1.14.2 | Project management |  | In good shape | Maintenance |  | on time
1.4.1.14.3 (GE detector) | Electronics |  | First version of NanoMCA tested , on-board HV modules (ISEG) tested | Preparing implementation in Prototype | delivery of components | risk of delay
1.4.1.14.3 | Mechanics |  | First design in preparation | Design of holding structure, test of alternative option for the cooling device | Need personnel | on time
1.4.1.14.3 | Infrastructure |  | Planning for cabling and supplies not started yet |  | not yet considered | on time
1.4.1.14.3 | Prototypes |  | One-single crystal performance meets requirements, radiation test at COSY | Preparation of triple cluster detector Preparation of COSY beam test in 2015, In Beam-Measurements | Production and delivery of components. Need successful test beam to establish basis for TDR | risk of delay
1.4.1.14.3 | Offline Software: Simulation |  | In good shape | Keep up with design improvements | none | on time
1.4.1.14.3 | Offline Software: Reconstruction |  | In good shape | Prepare time-based reconstruction | none | on time
1.4.1.14.3 | Online Software |  | In good shape | online pulse shape analysis | Need personnel | on time
1.4.1.14.3 | TDR | M3: 8/2016 | Collection of materials has started | Writing text, collecting information |  | on time
1.4.1.14.3 | Project management |  | In good shape | Maintenance |  | on time
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
Radiation Hardness of HPGe | <20% | moderate | Present best candidates for the gamma spectroscopy of Doubly strange hypernuclei are HPGe crystals (Euroball). It has to withstand the level of radiation tolerance required for operation in PANDA | Physics performance loss (high precise gamma spectroscopy). | Early prototyping and irradiation tests can substantially reduce the risk. Annealing of the damage can be accomplished readily by heating the crystal for short time periods.
Germanium Triple Cluster Protototype | <10 % | unlikely | Delivery of a fully equipped triple cluster detector might suffer from some delay due to manufacturing problems. | Delay in submmiting Tech. Des. Report at the end of the 2016 | Sinergy with the DEGAS /DESPEC Collaboration at NUSTAR/FAIR. The scheduled beam test in June 2016 ensures delivery of the main components for the PANGEA Prototype.
Man power insuficient | <20% | severe | Lack of personel might induce some delay in fulfilling deadlines. | Delay in the scheduled Milestones | Getting additional Funding, extend collaboration with other groups and get external students/PostDocs

## DCS
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.18.3 | WP1-DCS TDR | M3: 12/2017 | Sketch of first draft | DCS interface with external systems Archiving | Data exchange and archiving | on time
1.4.1.18.3 | WP2-Central DCS software -sub-system GUI "standardization" | M7: 12/2017 | GUI's developed by LUMI and EMC sub-systems | Collecting feedback from sub-systems | FTE at sub-systems level | on time
1.4.1.18.3 | WP3-Central DCS software - Desktop application "standardization" | M7: 12/2017 | None | Collecting feedback from sub-systems | Data exchange and archiving | risk of delay
1.4.1.18.3 | WP4-Central DCS software - sub-systems merging into the Desktop application | M7: 06/2018 | None | None | DCS development at the sub-systems level | risk of delay
1.4.1.18.3 | WP5 - Central DCS software - Desktop application | M8: 12/2018 | None | None | Funding of man-power | risk of delay
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
Man-power | Possible | Moderate | There are several PANDA sub-systems were the controls subject was not addressed yet (May 2016), the main argument beeing the lack of man-power - willing or able to deal with the controls | Delay in the sub-system commissioning and/or integration in the Central PANDA DCS | DCS 'national' team to support the development of controls for the troubled sub-systems

## DAQ
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.19.1 | Data Concentrators |  |  |  |  | risk of delay
1.4.1.19.1.1 | Replacement for TRB3 |  | Zynq-based design ready, prototype produced | Test and debugging of of prototype |  | on time
1.4.1.19.1.2 | DC for MVD |  | Conceptual design |  | Withdrawal of manpower at FZ Jülich | risk of delay
1.4.1.19.2 | SODAnet |  | working prototype based on TRB3 | Performance and stability tests |  | on time
1.4.1.19.2.1 | SODAnet port to new DC |  |  |  |  | on time
1.4.1.19.2.2 | SODAnet port to MVD DC |  |  |  | Withdrawal of manpower at FZ Jülich | delayed
1.4.1.19.3 | Compute Node |  | Working prototype: xFP cards (Virtex 5 FX70T) and ATCA carrier board (Virtex4), working IPMI controller for carrier board and MMC controller for xFP card | Firmware development for data link between ATCA backplane and PCIx, stability and performance tests | Lack of manpower | on time
1.4.1.19.3.1 | Firmware for algorithms |  | Working Firmware for STT tracking, working firmware for burst building/event building, tested at MAMI/Mainz |  | Lack of manpower for further in-beam DAQ tests, no manpower for further algorithm develoment in detector groups | risk of delay
1.4.1.19.3.2 | Port of CN architecture to mor recent FPGA platform (Kintex Ultrascale (+)) | Conceptional design (7/2016) |  | Evaluation of different FPGA architectures, selection of Kintex 7 Ultrascale, Port of STT tracker firmware to Kintex 7 Ultrascale development board (AVNET) | Lack of manpower | risk of delay
1.4.1.19.3.3 | Kintex based CN Prototype | Working prototype (01.07.2017) |  |  | Lack of manower | risk of delay
1.4.1.19.4 | Networking, connectivity between CN layer and online server farm |  |  |  | Lack of manower | risk of delay
| Preparations of TDR for Day 0 DAQ/Event filter System | M3 01.12.2017 | Succssfull tests with CN and SODANET prototypes | Design of new CN platform, fdata concentrators, time-and event - based simulations, firmware development | Lack of manpower | risk of delay
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
Essential input for design decissions missing:time-based and event-based simulations | Likely | Delay of DAQ project, cost increase, waste of ressources | Time-based simulations and event-based simulations for a realistic startup scenary are indispensible input to make final design decisions with respect to bandwidth and performance of the DAQ/Event filter system. A realistic detector scenario has to be developed for first physics with PANDA and the integrated luminosity requirements have to be worked out. The maximum possible event rate depends on rejection factors, storage capacity, performance and bandwidth of DAQ/Filtering and hss to be mathched to the physics programme. | PANDA cannot run at the required luminosity to achieve ist physics objectives | Strenghen the simulation efforts, better overall coordination of computing, DAQ, online-trigger groups, provide more manpower
Lack of manpower for algorithm development in the detector groups |  | Event filtering cannot be done online | Firmware is needed to operate the event filtering, based on particle ID, tracking and calorimetry. Expert knowledge and manpower from the detector groups is required but not available. | The event filtering will be inefficient, resulting in limitations to the achievable integrated luminosity due to lack of mass storage and DAQ bandwith. | provide more manpower
no funding for DAQ construction available, no LOI to request funding form any existing PANDA group |  |  |  | no DAQ system | provide funding

## Computing
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.20.1 | Computing Model | M3 12/2018? | Preliminary estimation of requirements | Requirements calculations - standby | Funding. Panda manpower dedicated for the model. Uncertainty from DAQ | delayed
1.4.1.20.1.1 | Full Requirements |  | First numbers shown in dec14. Bottlenecks identified | Reduction of event size. Evaluation of bias from online - standby | Uncertainty of event size and online data reduction | delayed
1.4.1.20.1.2 | Requirements for starting phase |  |  | Plannings for first years - standby | In starting phase event reduction could be smaller -> larger data sample | delayed
1.4.1.20.1.3 | Distributed computing |  |  | Identify possible Tier sites and distribution strategy - standby | Computing funding is not set | delayed
1.4.1.20.1.4 | Prototyping distribution of jobs |  |  |  | 0 manpower. Possible middleware not identified | not started
1.4.1.20.2 | Offline software |  | A complete realistic reconstruction chain for the barrel |  | Manpower | delayed
1.4.1.20.2.1 | Forward tracking | Q4/2016 ? | Preliminary version of the code, not usable for production | Finalization of 1st version of the code - suspended. Groups in krakow starting from scratch | Manpower: only one PhD ending | delayed
1.4.1.20.2.2 | Secondary tracking |  | Improvements in tracking quality for secondary vertices. Optimized forward barrel part (GEM) | No activity - validation of new code needed | Currently no manpower, the existing one has left | started
1.4.1.20.2.3 | Forward PID |  | Correlation of (ideal) forward tracks to RICH. PID parametrization of FMDT | RICH+FTOF studies | Finalization of forward tracking. Manpower for FSC PID | started
1.4.1.20.2.4 | Full detailed geometry description |  | GEM from CAD drawings |  | Many detectors have not yet finalized the design | delayed
1.4.1.20.2.5 | Quality Assurance |  | Standard QA for tracking | No activity | Dedicated Manpower | delayed
1.4.1.20.3 | Online software |  |  | Simulation of the DAQ chain
1.4.1.20.3.1 | Timebased detector simulation |  | Implemented for most subdetectors | Implementation of the remaining det. | Manpower for missing subdetectors
1.4.1.20.3.2 | Timebased data reconstruction |  | Running for some subdetectors |  | Manpower
1.4.1.20.3.3 | Coarse tracking |  | STT Triplet Finder | Algorithm development for complete det. | Manpower
1.4.1.20.3.4 | Fine tracking |  |  |  | Manpower
1.4.1.20.3.5 | Event building |  | Coarse event building existing | Fine event building | Manpower
1.4.1.20.3.6 | EMC reconstruction |  | First version of timebased reco, not yet tested |  | Manpower
1.4.1.20.3.7 | Detectors correlation |  |  |  | Manpower
1.4.1.20.3.8 | Messaging system |  | Some test examples running for PANDA |  | Manpower
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
The central computing (Green Cube) is not funded by FAIR | Possible | Moderate | The central computing of FAIR should be hosted inside the Green Cube, funded by FAIR. In the case FAIR will not fund the Cube (there is no official sentence about in the papers), the PANDA computing costs will increase substantially (currently the include only the distributed resources) | Computing costs increase substantially. Computing resources ready for day-1 data taking, but possible delays for full luminosity.. This means lack of resources for data processing and analysis once running with full equipment. | The official FAIR commitment in the Green Cube funding should be set (FAIR Computing TDR). | With day-1 luminosity less physical interactions, but in the first months the online selection most probably will be lower, compensating this effect.
Insufficient manpower investment in the software developments | Likely | Severe | Lack of dedicated manpower makes the software developments slower, with important tasks uncovered, and code not deeply bug free, with also problematic aspects in the reconstruction for people doing the analysis which are slow to be fixed or improved. | Delays in having realistic simulations to evaluate the reconstruction capabilities, in particular for the design of the triggerless data acquisition system. | More software manpower from the collaboration. Service common tasks.
Italy quits Panda | Likely | Severe | The position of Italy inside Panda is now critical. If INFN quits PANDA, important computing task and expertice will vanish (software for STT FTS and MDT, tracking, PID, computing coordination) | Lack of manpower for detector software of STT/FTS/MDT, central tracking expertise lost | STT/FTS/MDT tasks covered by different groups, as well as coordination tasks.

## System Status Template
Sub-PSP code | Work Package | Next Milestone | Achievements | Current Activity | Critical Items | Schedule Status
1.4.1.X.Y.Z | WP1 | M7: 6/2015 |  |  |  | risk of delay
1.4.1.X.Y.Z | WP2 |  |  |  |  | on time
1.4.1.X.Y.Z | WP3 |  |  |  |  | delayed
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks

## Explanations Risk Report
Risk item | Probability | Damage | Description | Impact | Mitigation measures | Remarks
Short title of risk | Unlikely (un): < 10% | Marginal (ma): sub-goal affected or only partly reached | Longer description of risk | Impact on the system when the risk is realized | Measures to reduce or avoid the risk | Optional remarks
| Possible (po): 10% -- <20% | Moderate (mo): several objectives affected
| Likely (li): 20% -- <50% | Severe (se): essential objective of pillar not realized
| Very likely (vl): >= 50% | Business critical (bc): entire pillar threatened