## Slide 1: Super-FRS plans for commissioning and day-1 beams
H. Simon
FAIR Exp. & Acc. 20171215

## Slide 2: Outline
Timeline
No-beam activities
Phase-0 activities
Commisioning with beam
Phase-1
Notes: In-Flight  energies as high as 1500 MeV/u

## Slide 3: Timeline (Status Standard SC Dipole Magnets)
Scope
3 units 11°, 18 units 9.75°
Warm iron, SC coil
Aperture ±190mm x ±70mm
Weight: 50 to 60 ton
Magnetic systems define timeline
of the project 
tendering and testing
Tender Status :
Announcement published April 7, 2017
Qualifying submission closed May 12, 2017
  6 out of 7 companies invited to tender
Offers received by mid of July, 2017
Offers analyzed (with CEA colleagues);
Last negotiation round KW2 2018
Contract award expected soon after

## Slide 4: Timeline (SC Multiplets, Overview)
Schedule First of Series SC multiplets
Contract closed 07/2015
  (ASG, Genova)
Design phase for SM done, for LM running
  PDR 07/2016
  FDR 12/2016
  PRR 07/2017 (short multiplet)
  PRR LM Q4/2017
  FAT FOS short multiplet Q1/2018
8 short multiplets (PS)
  QS configuration
25 long multiplets (mainly MS)
  Quadrupol triplet
include corrector elements & steerer
7 m
≈60 ton
Main characteristics:
iron dominated, cold iron (up to 37 tons)
common helium bath
warm beam pipe (38 cm inner diameter)
per magnet 1 pair of current leads
max. current <300A for all magnets
2.5 m
≈25 ton
H. Müller,
E.J. Cho et al.

## Slide 5: Timeline (Magnet Testing CERN)
B.180 CERN
Control room
Power
cable
Collaboration between CERN and GSI
  CERN Building 180: Infrastructures, renovation done.
Cold (4K) testing of the SC dipoles and multiplets
  3 test benches installed, 59 magnet cryo-modules
Commissioning of the cryo-facility running
Procurement of last missing components in
progress (Jumper-line/elec. cabinets)
FoS SM testing foreseen to start in Q2 2018
K. Sugita,
G. Golluccio,

## Slide 6: Timeline Schedule SC Magnet Procurement incl. Testing
+ LEB
India !

## Slide 7
Timeline
Installation expected to be finished early 2024
 commisioning phase starts

## Slide 8: No-beam activities Target area
Installation of NC magnets within the target-area shielding
H. Leibrock,
T. Blatz, et al.
Super-FRS target area will be heavily shielded
remote handling & robotics
Hot cell (2023+)
Plug concept
Flask and cranes/roboters
 Lots of testing and commisioning!
Plug support HC
H. Weick,
C. Karagiannis et al.

## Slide 9: No beam activities (Handling, Plug Guidance)
Michel Lindemulder,
Henk Smit, KVI-CART
required: ± 20mm shift,
± 2 mrad tilt
tested up to 70 mm
or 7 mrad
chamfered collar
(removable)
chamfered step
top plate
= support
automatic hooking,
by rotating square pin
corner rods
Mock up studies  prepare for SAT

## Slide 10: No beam activities (Media Board development)
Media board prototype designed and manufactured at GSI
One board part of beam instrumentation equipment (prototype developed for slits)
Large connector variety (high power, high voltage, data (10 Bbit), signals, fiber optics, fluids, compressed air, ...)
associated tests at FRS target area
pre-qualified systems will be available
robot training !
C. Schlör,
C. Karagiannis,
T. Blatz

## Slide 11: Phase-0 R&D (ToF and DE)
Si-strip
prototype
MUSAMP v.2
Time-of-Flight (Russian in-kind, IOFFE StP)
  Specification released
  IKC close to be signed
  R&D on diamond and silicon ongoing
  (use of CERN/EP-ESE picoTDC under investigation)
MUSIC (energy-loss, Finnish in-kind)
  Specification released
  IKC signed
  PreAmps by CEA Bruyeres
    successfully tested at beam time in 2016
    contract ready for signature
Plastics (Swedish in-kind)
  Specification released
  IKC running
   Expect SAT tests with beam
C. Nociforo,
O. Kiselev,
B. Voss et al.

## Slide 12: Phase-0 Detector R&D for FOS
SEM Grid (profile monitor), Finnish In-kind
  Specifications released (Q1/2016)
  IKC running
  prototype SEM in-house (Ti & C wire)
  beam test at JYFL Q4/2017
GEM-TPC (tracking), Finnish in-kind
    combined with SEM on a common drive
    several prototype tested at JYFL and GSI
    including new readout electronics
  Specification released
  IKC in preparation
  Beam test 2017/18
C beam
´cluster finding‘
Position drive,
Finnish In-kind
GEM-TPC
prototype
Fermilab design
POLAND digitizer
C. Nociforo,
A. Prochazka,
C. Caesar et al.

## Slide 13
Phase-0
R&D for series production for many detector systems
Beam tests required (SAT)
„all ions/all energies“
103-109 pps
2018 - 202x ?
Transition to Phase-1
Beam optics tests @ low intensity (~103 pps)
Commisioning of tracking system

## Slide 14: Ex.: BigRIPS beam optics tests H. Takeda BigRIPS Team, RIKEN Nishina Center
In-flight RI beam separator at RIBF
Two-stage scheme
  First stage: production and separation
  Second stage: particle identification (A,Z,Q)
Large acceptance
Large magnetic rigidity
F0
F1
F2
F3
F4
F5
F6
F7
}
First stage:
Production and
Separation
Second stage:
PID & Tagging
key issues to achieve
high particle identification power

## Slide 15: Track reconstruction
Numerical method is needed to solve
when higher order terms are considered.
 N. Fukuda’s talk
Final goal is to achieve high resolution in A/Q only with COSY calculation.
Among these terms, (x|a) is very sensitive to magnetic fields. In other words,
(x|a) can be optimized by relatively small tuning. Errors due to uncertainty in ai
can be minimized by eliminating the (x|a)ai term.

## Slide 16
Experience:

2-3 m of beam time
(1 branch!)

## Slide 17: SuperFRS will have 3 branches ...
R3B
to storage rings
ILIMA, EXL,...
Super-FRS collab.
parts from HISPEC / R3B
MATS /
LaSpec
HISPEC/
DESPEC
Cryogenic
stopping
cell
Chart: Z
| 1 | 20 | 40 | 60 | 80 | 92
 | 0 | 80 | 270 | 560 | 1040 | 1460
Q=Z 95%




## Slide 18
Initial Commisioning (slow extraction)
  e.g. C/U small intensity (~10³ pps)
  Br Range: 2Tm-20Tm optic tests
  RIBF: 2-3m, parasitic alignment (vs. beam axis) – Tracking Detector Commissioning
  remaining SAT tests 2-3 m (paras. beam)
Ramp up: SIS18/SIS100 medium intensity tests (~1010 pps, slow extraction) (all beams desirable (U, Sn, C at least)
  Thickness measurements (degraders etc.)
  Full identification including DE, TOF system commissioning
  Initial physics programme (e.g. spec. isotope search) 2-3 m (full beam)
Ring Branch: Fast extraction, dedicated tests
Commissioning  phase-1
Takeda
RIBF

## Slide 19: phase-1 (e.g. Beam Catcher Plugs)
BC1
BC2
BC3
CAD model of BC3 and sextupole on common adjustment platform
cut through BC chamber including pumping duct
plug assembly (BC1)
  Instrumentation Checks
  Verify Modelling
  „Training“
  Low activation
BC3 movable / linear drive

## Slide 20: phase-1 (Target Chamber & Plug Systems @ low activation)
Michel Lindemulder, Henk Smit, KVI-CART
H. Weick,
C. Karagiannis et al.
R&D with KVI-CART
A. Stolz NSCL
Verify machine protection system
Reliable detector operation
„Training“

## Slide 21
  Beam time is required during all phases of the Super-FRS construction
  Parameters for phase-0, initial commissioning, phase-1 provided
  Extend of phase-0 should be defined
  Time for „no-beam“ commissioning is substancial for the Super-FRS
    hot cell
    remote handling
  Schedule for the branches not yet final
    Indian in-kind to LEB
  Experiments within phase-0 and phase-1 foreseen & possible
Summary