## Slide 1: Status of the CBM Experiment – Key Dates for CBM Magnet
Walter F.J. Müller, FAIR, Darmstadt
CBM Magnet CDR Round 2, GSI 24-25 April 2018

## Slide 2: FAIR Construction on Track
picture taken March 19th, 2018

## Slide 3: Major External Milestones for CBM
G014 (CBM building)
  shell completed Dec ‘20
  installation window Dec ‘21 to Mar ‘22
  transition to ‘user mode’ Dec ‘22
Cryogenics and Accelerator
  Cryogenics ready in G014 Mar ’23
  SIS-100 ready for beam Jun ‘24
  HEBT ready for beam Aug ‘24
  SIS-100 pilot beam Nov ’24
  SIS-100 ‘1 user, low intensity’ Feb’ 25
Notes:
- during ‘installation window’ building is still in ‘construction site’ mode - only very basic ventilation and power services available - mainly useful for bringing in robust mechanical structures
Depending on whom one asks first opportunistic test beam (few hours parasitic to SIS-100 commissioning) might start between Jul and Nov ‘24.
Go for CBM M11 Mar’24
Cryo plant still on commissioning
Dates checked & updated 2018-04-22
Very often shown slide

## Slide 4: Installation Options for Magnet
Use installation window
  install magnet in Dec’21 to Mar’22 window
    Note 1: window will most likely be longer !
    Note 2: only basic construction site services available
    Note 3: other installation work in parallel (e.g mounting structs)
  do bring-up starting when Cryo is ready, earliest Mar’23
After building acceptance
  install magnet starting Dec’22
    Note 1: now full services available, except Cryo
    Note 2: many parties in the cave !
  bring-up when Cryo is ready, earliest Mar’23

## Slide 5: Time required for commissioning
Many other activities depend on the milestone Magnet ready for operation [M11] the most notable ones are
  magnet upstream remap with MUCH absorber
  installation STS in magnet
  commissioning STS
It is essential to understand the time required for
  cold-commissioning
  quench testing
  etc.

## Slide 6: The End
Thanks for your attention

## Slide 7: FAIR Schedule: SIS100 and CBM
The CBM bottom line:
  Dec 2021 to Jul 2022 1st installation window
  Dec 2022 Building acceptance
  Dec 2022 to Jun 2024 Installation & commissioning w/o beam
  Jun 2024 to Mar 2025 Commissioning beam from SIS100
 Schedule Quite Stable
Slide shown on Spring 17 CBM Week in plenary on 23rd March 2017

## Slide 8
Backup Slides