## Slide 1: Controls Status Review, Current Efforts and Outlook
Machine Meeting, 2018-07-17
Hanno Hüther

## Slide 2: First Beam Time Block (June / July) in Review
Main goal achieved: Most critical control system components for SIS18 successfully commissioned
Downsides: Bugs and immature UIs
  „PE“ interlocks at main dipole
    Late events in Timing System‘s Data Master
    Bugs in function generator‘s FESA class
  Injection from UNILAC
    Address translation issues in Data Master‘s communication with UNILAC gateway
  Reading status from / executing commands on devices
    Feature to periodically trigger these actions for devices not in a Pattern / when the Pattern is not running is not yet ready
    Device Control does not yet match the operator‘s requirements

## Slide 3: Current Developments in July Beam Time Break
Focus on stability and usability: Reduce control system outages and lessen pain for operators
  „PE“ interlocks at main dipole and injection from UNILAC
    Main issues identified and patched. Currently being tested and prepared for deployment. Further testing in production environment planned for coming week. Minor issues still being investigated.
  Reading status from / executing commands on devices
    Improved „table view“ (upper section) in Device Control currently being implemented
Conflicting goal: Minimum feature set needed for ESR operation in the next beam time block
  Beam transfer from SIS18 to ESR
  Multiple SIS18 injections into one ESR „cycle“
  Timing-enabled actuators in ESR

## Slide 4: Outlook for the coming (August / September / October) Beam Time Block
There will be a major improvement in stability
  Last week‘s problems with injection from UNILAC have been fixed
  Function generator / dipole interlock incidents have been greatly reduced, remaining issues will be addressed during the beam time
Enhancing usability will be an ongoing effort
  Bug fixes and improvements to applications (Device Control in particular) will continue to be deployed
  Reading status / executing commands on devices periodically without timing takes considerable effort, release is scheduled for October break
  Deployment of intermediate solutions to supplement / partly replace Device Control could start this beam time block, but should be carefully considered and prioritized because they take away resources from other requirements and a sustainable alternative
ESR operation will neither be comfortable nor efficient, but the control system‘s constraints have been discussed with machine experts and agreed upon as feasible to carry out the experiment