## Slide 1: Spare-part policy during construction and for commissioning
Martin Marenich
5th IKBest workshop, 9th April 2019

## Slide 2: Maintenance strategy in private industry
Terms of maintenance [1]:
  maintenance strategies may be failure oriented, periodic or condition/data based
  Definition: inspection, service, repair (spare parts), improvement (interoperability requirements)
Situation maintenance [2]:
  For a long time, maintenance was not considered a top priority neither in industrial science nor in industry practice; it was much more seen as a fire fighting when a failure occurred.
  This results in unforeseeable machine downtimes and a high number of rush orders.
  In the last decades, equipment became more expensive, down times were getting more costly and maintenance costs rose dramatically with the increase of the equipment’s complexity.
Three buffers available to synchronize demand with lowest cost and highest service level [3]:
  capacity
  inventory
  response time
  (patch work from „cellar spares“)
[1] Instandhaltungslogistik, K. Matyas, Carl Hanser, 2017
[2] R. Glawar, et.al "An approach for the integration of anticipative maintenance strategies within a production planning and control model"; Procedia CIRP, 2018
[3] W. Hopp and M. Spearman, “Factory Physics”, 1996

## Slide 3: Maintenance strategy for big science
Lean production and total quality management – emphasis requirements for maintenance strategies [1]
  internal or external maintenance
  IT in the maintenance,
  use and application of key indicators
  fundamentals and statistical methods of reliability engineering,
  methods of planning and predetermination as well as reliability testing,
  organizational anchoring of the reliability program in the company
Big Science Facilities are not production companies and more comparable with lean construction [4]
  Construction project: design, construction, commissioning, beam time, maintenance, upgrade, ....
  project-based production process
  industry with autonomous agents
  a social system
Mandate for spare policy or spare management
  If the scope just consists of delivering a facility that achieve operation performance, spare parts may not be in the scope of the project. However, if the mandates foresees the delivery of the facility plus spare parts for operating it over a certain period, then the procurement strategy of spare parts might be of prime importance [5].
[4] https://www.leanconstruction.org/
[5] Pierre Bonnal, CERN

## Slide 4: Spare categories for commissioning [6]
Capital spares (Long runner): Spare parts with delivery time of more then 3 months and therefore need to be bought within contracting / purchasing.
  expect to fail due to a high rate of infant mortality or as single point of failure,
  unlikely to meet specifications during installation, e.g. magnetic horn.
  not available in the future, like electronics due to out-of-date problematic
  economically justifiable to purchase with main contract etc. like power converters, thin vacuum chambers
  or is a unique component (e.g. requiring a special production line), like magnet coil or clystrons
  very long delivery times, like spare turbine plates of the cryogenic plant
  This original procurement is typically funded through project funding.
Operational Spare (short runner) - Spares routinely replaced post-project as a part of regular maintenance during operations.
  These are typically COTS (components out of the shelf) components. This equipment is typically funded by operations budget. Typical examples or operational spares would include vacuum pumps, power supplies and standard optics.
Hot Spares
  Some components have high probability of failure and/or extended facility downtime for replacement that the system may be designed with “hot spare’ redundancy that allows switch over to the “hot spare” component with minimal or no downtime. E.g. cryoplant.
[6] LINAC Coherent Light Source II (LCLS-II) Project Spares Plan, John Schmerge

## Slide 5: Spare management for commissioning
Spare policy
  Only the procurement of the original spare for commissioning are considered.
  System owner are responsible for spare estimation based on component lifetime and failure modes
  Low cost spares and/or consumables will be managed directly by system owners
Spares list
  A complete list of required spares for commissioning the facility.
  Various spare categories need different strategy
  Analysis of critical delivery time
  Storage estimation (volume, weight, needed infrastructure)
  Special tooling
work package | component | code | comments | Pieces | category | responsible
cost 2018 | already ordered? | option in Contract | planed contract milestone | time to order
m^2 per pcs | m^3 per pcs | t per pcs | special storage treatment

## Slide 6: Critical delivery time for spare magnets/coils
No critical spare item within the magnet area
Some main magnet contract have closure schedule in 2019 and would need spare funding
critical items
Status and actions
Magnets | Spare Cost [k€ @2005] | Status spare | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Time critical
HEBT |  | All 29 psp ordered |  |  |  |  |  |  | NO
S-FRS |  | 5 PSP main contract not signed |  |  |  |  |  |  | NO
CR |  | All BINP inkind, ordered as option |  |  |  |  |  |  | NO
P-Linac |  | All GSI inkind, all but 2 contracts not signed |  |  |  |  |  |  | NO
p-Bar |  | All BINP inkind, no contracts signed |  |  |  |  |  |  | NO
SiS100 |  | All 10 psp ordered |  |  |  |  |  |  | NO
HESR |  | All spare magnets ordered |  |  |  |  |  |  | NO
Legend:
M4 Contract Signing
M7 Final Design Review
not signed .. contract negotiation will include spare
time critical .. main production finished or decision open or time critical delivery times
ordered .. incl. in contracts as an option or scope
off the shelf items with availability
time critical acc. Milestone 4 to 7 (start cash out)

## Slide 7: Critical delivery time for various area´s
No critical spare item
Some contract have closure schedule in 2019 and would need spare funding
critical items
Status and actions
area | Spare Cost [k€ @2005] | Status spare | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Time critical
S-FRS, SiS 100 |  | Quench Detection GSI inkind |  |  |  |  |  |  | NO
Commons |  | Cryo plant spares (GSI) under negotiation, local cryogenics included |  |  |  |  |  |  | NO
P-Linac |  | RF-System (GSI, French and FAIR) |  |  |  |  |  |  | NO
SiS100 |  | RF-System (GSI and FAIR) |  |  |  |  |  |  | NO
CR, HESR |  | Stochastic cooling (GSI, FZJ) |  |  |  |  |  |  | NO
p-Bar |  | Passive target & magnetic horn (FAIR, BINP) |  |  |  |  |  |  | NO
Legend:
M4 Contract Signing
M7 Final Design Review
not signed .. contract negotiation will include spare
time critical .. main production finished or decision open or time critical delivery times
ordered .. incl. in contracts as an option or scope
off the shelf items with availability
time critical acc. Milestone 4 to 7 (start cash out)

## Slide 8: Spare parts costs per machine incl. their storage and handling [T€ money point 2005]
FAIR sub-projects and storage | Big items | 7% Beam diagnostic | 3% Vacuum Standard Components | 4% Power Converter | Uncertainty (15%) | Sum per topic | Costbook value per sub-project
SiS100 |  |  |  |  |  |  | 
Super-FRS |  |  |  |  |  |  | 
P-Linac/ pbar target |  |  |  |  |  |  | 
CR |  |  |  |  |  |  | 
HESR |  |  |  |  |  |  | 
HEBT |  |  |  |  |  |  | 
Cryo plant |  |  |  |  |  |  | 
Commons (3.5%) with cryo distribution, SiS18, alignment, controls and quench detection |  |  |  |  |  |  | 
Spare storage & handling |  |  |  |  |  |  | 
Subtotals per columns |  |  |  |  |  |  | 

## Slide 9: Lesson learned
Availability of spares increases beam time and decrease cost over life-cycle!
In order to procure spare parts cost-efficiently:
  Purchase/contract them with the main delivery
  With budget constraints in place, a contractual option may win time
  Spares may be former first of series components or taken from test banches
  Spares may be considered during design phase, for example with symmetrical design where only half a coil is necessary or standardization of generic components (Embedded Control, UPS, Power drive components, cables etc)
  Spare parts may lead to dependencies on supplier, consider and price them during main contract negotiation
Spare policy
  COTS (components out of the shelf) like for Beam diagnostics, electronics and vacuum Standard components may be calculated with a estim. percentage margin
  An analysis of critical delivery times will show priorities
  Maintaining of machines by people who work on them, for a minimum downtime [7].
  Management of defects, will show improvements [7].
CERN approach
  contractors must be able to provide all critical spare parts over a given time period (~7 years after final acceptance). So bidders who don’t accept this specification item are disqualified [5].
Future scarcity map on big science components & services needed?
[7] Kobayashi 20 keys to reduce wastes