## Slide 1: CR Status Dmitry Shwartz Ivan Koop
2nd BINP-FAIR Collaboration Coordination Workshop, FAIR, 20-25 May 2019

## Slide 2: Collector Ring @ FAIR Project
CR
HESR

## Slide 3: CR Layout
 | Antiprotons | Ions
Perimeter, П | 221.451 m | 
Rigidity, B | 13 Tm | 
Number of particles, N | 108 | 109
Kinetic energy, K | 3 GeV | 740 MeV/u
Velocity, v | 0.971c | 0.830c
Relativistic factor ,  | 4.20 | 1.79
Betatron tunes, x, y | 4.39, 3.42 | 3.40, 3.44
Revolution frequency, 0 | 1.35 MHz | 1.16 MHz
RF harmonic, q | 1 | 
Injection from P_bar separator
or SFRS
Extraction to HESR
RF – cavities
Injection Kicker
magnets
Stochastic cooling
Pickups
Stochastic cooling
Kickers
ToF System
Space reserved for five
RF-cavities for future upgrade

## Slide 4: Magnets: Dipole
Status: CDR, FDR are released; FoS production is in progress
Parts of stamping tool for side spacers laminas
Parts of FoS dipole
Tooling for coils impregnation

## Slide 5: Magnets (2)
Quads: design is in progress, WQ CDR docs are ready
Sextupoles: design is in progress, CDR docs are ready
Steerers: design is ready, CDR is ready, materials procurement started
Octupoles: design is in progress
Decapoles: not in contract, desired by ILIMA, feasibility study is ongoing

## Slide 6: Power Converters
Status: Conceptual design in progress. Quads PC prototyping in progress.

## Slide 7: Injection/Extraction
Injection septa: design in progress, prototype of ceramic vac.chamber procurement ongoing.
Kickers: vacuum tank and magnets design nearly finished. PC conceptual design in progress. “HV cable problem” solved: procurement of halogen-free cable is feasible. Unclear questions: procurement of cables and ferrite via FAIR; assembling and testing of whole series @ FAIR?
dB/B=7*10-4

## Slide 8
Injection/Extraction Septum Magnets
CDR → June/July 2019
FDR → End of 2019
CDR → September 2019
FDR → End of 2019
Injection
Extraction

## Slide 9: Kickers PC concept
ET1R2000
Uout = 0-1,5kV
Imax = 2 A
Capacity 1,6 mF
Umax=1500V
Fast Thyristor
Imax=32kA
TT120N16SOF * 21pcs
HV Transformer
U input=1kV
U output=70kV
Two chargers, for injection and for extraction!
Kicker magnet
Thyratron CX2593X
Compensation load
PFN DS-2335
Two power supply line for + and – current polarity
A.Kasaev

## Slide 10: Diagnostics
Pickups: types-1,2 designed, type-3 design is ongoing. CDR is ready. Unclear solution for pre-amplifier: low signal (10 uV @ 10^7 antiprotons, noise ~4-5 uV), radiation resistance (1-2 kGy/year near vacuum chamber for LNA).
Preliminary: VGA=Amplifier-110 (Slovenia), LNA=?? Juelich or BINP?
FCT, DCCT: CDR is ready. To be procured via FAIR form Bergoz: DCCT + Analog Electronics (included 2 pcs), FCT + Pream. (to be bought, FEMTO DUPWA 1-70).
Beam scrapers: design is finished, CDR is ready.
Beam stoppers: design is finished, CDR is ready. (Can be used as Faraday Cup for ion beams, preamplifier required, who will pay?)
Scintillating screens: design is in progress. CDR released. (Two solutions: stepper driver, pneumatic drive - preferred).
RGM: conceptual design is in progress.
Pickups Test Bench: Conceptual design of mechanics not finished, DAQ Libera will be delivered (1 pcs, September 2019) by GSI for test, Software for tests (FESA, LSA etc.) not clear.

## Slide 11: Vacuum
Dipole chamber: CDR released. Prototyping is in progress.
Quadrupole-sextupole chambers: CDR is ready. Prototyping is in progress.
Round wide tubes: spec is ready. Procurement is ongoing.
Bellows: spec is in progress.
Pumps, valves, roughing stations: the list is prepared and sent for procurement via FAIR.
Round narrow tubes: spec is not ready.

## Slide 12: RF system
Two inductively loaded coaxial quarter wavelength resonators working on a common ceramic gap
Ring core of cobalt-based magnetic alloy
Max. voltage 40 kV/unit
Number of units 5
Frequency range 1.1 – 1.5 MHz
Inner pipe diameter 150 mm
First of Series CR debuncher during commissioning at GSI.
First of series RF system accepted in 2017
FAT of all 5 RF cavities done. SAT ongoing
FAT of 4 Power Supplies done. SAT ongoing
More details in talk by U.Laier

## Slide 13: Stochastic cooling system
Palmer Pick-up
RF concept + engineering ready Mechanical integration with BINP flanges/bellows. Spec + manufacturing drawings ready for tendering the vacuum tank
Cryogenic Plunging Pick-Up
Testing of the full cryo-plunging concept in the GSI prototype tank ongoing.
Engineering/mechanics/assembly activities ongoing.
Long-time mechanical durability tests of the plunging foils ongoing.
Vacuum-compatibility tests of materials.
Electrode module re-design, contacts with providers.
Power Amplifiers
SAT FoS done in Q2/2018.
Series production ongoing

## Slide 14: Stochastic cooling system
Microwave Damping- Coated Ceramic Absorbers
Draft engineering concept ready.
First batch of Al2O3 tubes for prototyping coated (by NiCr-sputtering at ISE Freiburg).
UHV test done (outgassing rate acceptable). RF test planned.
2019: Procure and store series of tubes.
assembly and full damping tube concept test after delivery a prototype chamber by BINP.
Procurement of the series of holders is tested successfully.
Microwave Damping-Ferrite Absorbers
Ferrite design ready.
UHV test done (outgassing rate acceptable).
Ferrite tiles purchased for all pick-ups
More details in talk by C.Zhang

## Slide 15: Infrastructure
Water pipes distribution
Pressurized air distribution
Feb 4-5 – first workshop BINP – FSB on the CR building.
Feb 7 - first meeting BINP – Mueller & Bleher.

## Slide 16: Infrastructure (2)
Cables connectors info uploaded to Cable Data Base
Tables with coordinates of water and air connections prepared

## Slide 17: Assembling, Testing, Installation
LCM workshop (Tue, May 21)
Estimations of time and manpower are done.

## Slide 18: PLM for CR
Generated CIDs: 256
Assigned AIDs: 48
The CDR documentation have been uploaded for all this AIDs.
Working on the following Technical systems at present:
Vacuum
Beam Diagnostics
Magnets
Target Technical systems for the nearest future:
Injection/Extraction
Power Converters

## Slide 19: CDR docs uploaded to EDMS (M6)
Vacuum, WPL Alexander Krasnov
Wide quadrupole & sextupole vacuum chambers
Magnets, WPL Alexandr Starostenko
Vertical Steering Magnets
Combined Steering Magnets
Sextupole Magnets
WQ Quadrupole Magnets
Beam Diagnostics, WPL Yury Rogovsky
Beam Position Monitor System
DC Current Transformer (DCCT)
Fast Current Transformer (FCT)
Beam Stopper
Beam Scraper

## Slide 20: Specifications (M3)
13/18 specs to be finalized:
1 item – TCR1 magnets (steerer)
6 items – CR vacuum (1 uploaded to EDMS for engineering check)
? 3 items – CR vacuum standard equipment
6 items – TCR1 vacuum
? 2 items – TCR1 vacuum standard equipment

## Slide 21
Thank you!