## Slide 1: The CBM Silicon Tracking System
Status & Issues

## Slide 2: Outline
Overview: Silicon Tracking System (STS)
Module & Ladder: Critical Assessment Components
  Sensors
  Micro Cables
  Readout (ASIC/FEB)
  Sensor Support Structures
  Performance Issues
Status of System Integration
  Mechanical Aspects
  Thermal Aspects
Series Production of Modules and Ladders
  Sensor QA
  Module Production Schedule

## Slide 3: CBM-STS Project Teams
Germany
Helmholtz Center (GSI), Darmstadt
Eberhard Karls University (EKU), Tübingen
Goethe University (GU), Frabnkfuert
Karlsruhe Institute of Technology (KIT), Karlsruhe
Poland
University of Science and Technology (AGH), Krakow
Jagiellonian University (JU), Krakow
Warsaw University of Technology (WUT), Warsaw
Russia
Joint Institute for Nuclear Research (JINR), Dubna
Ukraine
Institute for Nuclear Research (KINR), Kiev
Japan
High Energy Accelerator Research Organization (KEK), Tsukuba (associate member)
STS timeline:
Construction: 2019/20 – 2024
Installation: 2024/2025
First beams: end 2025

## Slide 4: Silicon Tracking System (STS)
central tracker of CBM
  8 stations equipped with Double-Sided Silicon-Strip Sensors
Requirements
good resolution, high granularity, fast …
low-mass modules/ladders
  FEE outside acceptance
radiation tolerant
  sensor target temperature
STS inside super-conducting dipole

## Slide 5: The STS Module
STS module for mSTS
4 different sensor sizes ()
cable length from 15-45 cm
thickness
strip pitch
stereo angle
18 different module types
hit spatial resolution  25 µm (x), 450 µm (y)
sensors ordered from Hamamatsu, delivery start in Nov. 2019

## Slide 6: Sensor: Radiation Tolerance
Prototype sensors from both vendors satisfy the performance requirements almost up to twice the expected lifetime (= ﬂuence of in terms of reverse current and charge collection efﬁciency.
Prerequisite is operation at sufﬁciently low temperatures (-10 ◦C) and sufﬁciently high bias voltage (up to 500 V), target parameters for the STS detector design.
p-side
n-side
E. Momot GSI:
Charge collection efficiency () vs depletion voltage as fct. of fluence

## Slide 7: Micro Cables

## Slide 8: MicroCable: Type LTU, Ukraine
pro:
fast ultrasonic TAB bonding favorable for identical materials: aluminum sensor contact pads and bonded aluminum micro-cable leads
low Z material
Challenges:
semi-industrial, largely manual production
problems with quality?
yield ( = production time) ?
32 individual micro cables/module (C. Simons, R. Visinka - GSI)

## Slide 9: Micro Cables Stack: Type LTU
Additional spacers (PI-mesh) are placed between two signal layers to reduce the capacitance contributions from the adjacent connecting layers.
Shielding layers reduce the noise level and prevent shorting between the stacks of cables.
er Foamtak II = 1,5 er PI-meshed 30% = 1,75  strip capacitance = 0.38 pF/cm
Manufacturer: LTU Kharkiv, Ukraine

## Slide 10: MicroCable: Type KIT
pro:
well known in PCB-Flexboard technology
industrial production (Dyconex, CH)
offers interconnected multilayer solutions one cable with two layers (bottom & top) and vias instead of two single Al-cables
challenge:
highly customized bonding technology (flip chip, soldering, …)
higher Z material (Cu/Au)
As an alternative to the Aluminum-microcables a R&D-project has been started at KIT that investigates Copper-based cables (T. Blank, P. Pfister (KIT)):
flip chip Au-stud bonding

## Slide 11: MicroCable: Type KIT
proof of principle of bonding technology
  but: functional module has not yet been produced
next step required: assembly and test of full module with both sensor and STSXyter2.1 in Cu-technology
example of bonding on sensor-side in Cu-technology

## Slide 12: Summary: LTU vs KIT MicroCables
Cable technology: single point of failure!
tools for both types of interconnect technologies have been developed at GSI/KIT
working and tested modules using Al-micro cables
awaiting working and tested module using Cu-micro cables (ongoing)
Decision on continuation of Cu-micro cable path by end of Q4/2019!?
  required input: working and tested modules using CU-micro cables
  KIT agrees to use TAB-bonding for module production at KIT using Al-cables

## Slide 13: Readout

## Slide 14: ASIC & FEB
ASIC:
Preliminary EDR in 9/19
No major issues found
Revive input ESD protection?
Final EDR in 11/19
launch ASIC production
FEB (Front-End Board):
FEB-8/2 available (DetLab)
prototype FEB-8/5 available as Polish in-kind contribution
  test: dielectric strength
R. Kapell, J. Lehnert – GSI,
K. Kasinski – AGH
STSxyter 2.1

## Slide 15: ASIC: Noise
Expected/measured noise contribution from
ASICS:
total expected (minimal) noise:
ASIC
cable
sensor
A. Rodriguez2, O. Rodriguez - GSI

## Slide 16: Sensor Support Structures

## Slide 17: Carbon Fiber Ladders
complete set of CF Ladders (130 pc.) produced at a local company in “winding” technology:
carbon tube, 1.5/0.7mm 
carbon fiber + epoxy resin
W. Niebur, J. Heuser, U. Frankenfeld (GSI), J. Weinert – GSI DetLab

## Slide 18: Carbon Fiber Ladders Validation
precision & sagging comparable to CERN/JINR type (from ALICE-ITS)!
U. Frankenfeld – GSI

## Slide 19: Ladder Assembly Tool
L-leg glueing tool
Sensor holder
Base plate
Mounting block sensorposition
U. Frankenfeld, O. Vasylyev – GSI DetLab, S. Mehta – Tübingen

## Slide 20: Ladder Optical Metrology
Focus based optical metrology for sensors (developed at Tübingen, E. Lavrik) adapted (U. Frankenfeld – GSI) to ladder metrology:
successful vadildation of assembly technique
module placement achieved within target ± 200 µm (z), < 100 µm rms (xy)
10 µm position resolution
fiducial marks on sensors
measurement grid: 1 mm
3D image of sensors on ladder

## Slide 21: Performance Issues

## Slide 22: Performance Tests: mSTS
0
1
0
1
instrumented:
2 detector modules on 2 ladders on C-frame
analysis:
on-going
issues:
many channels “gave up the ghost“ (related to broken wire bonds due to thermal stress via glob-top on ASICS → thermal cycling tests ongoing)
larger noise then nominal ( ~ 3 ke, pick-up noise, ground loops → solved by more careful grounding)
J. Heuser, U. Frankenfeld, A. Lymanets, J. Lennert, A. Toia, P. Loizeau – GSI, C. Simons, O. Vasylyev – GSI-Detlab

## Slide 23: Thermal Cycling of FEBs
Shaifali Mehta - Tübingen
disruptive behavior of glob-top glue reproduced!

## Slide 24: Noise Performance
A. Lymanets – GSI , A. Rodriguez2, O. Rodriguez, A. Toia – GSI/Frankfurt
noise of single module: close to physical lower limit
issues to be addressed:
  system noise
    common mode noise
    full setup behavior
    ….
channel number
ENC(e)
< 1000 e-
500 e-

## Slide 25: Status of System Integration

## Slide 26: Mechanical Aspects
rail system (to move STS in and out of magnet)
rail system ( to move C-frames)
main frame for C-frame mount
positioning / adjustment
cabling, tubes
vibrations / structural analysis
beam pipe (carbon/berylium)
overall stiffness
service / support mechanics
overall assembly procedure
material budget rear panel
addressed in mechanical demonstrator!
O. Vasylyev – GSI DetLab

## Slide 27: Thermal Aspects
sealing
feed throughs
panel connections
electronics liquid cooling plate and distribution
gas drying & cooling for sensor
O. Vasylyev – GSI , K. Agarwal – Tübingen
thermal insulation box
addressed in thermal demonstrator!

## Slide 28: Cooling

## Slide 29: Cooling Challenge
z
y
x
Silicon Sensors:
expected power dissipation ∼ 6 mW/cm² at end-of-lifetime (fluence – 1014 neq(1 MeV)/cm²)
target temp. ≤ -10°C
gas cooling - material budget!
K. Agarwal – Tübingen, H.R. Schmidt – Tübingen, GSI

## Slide 30: (CBM-S Cooling Challenge TS
z
y
x
Electronics, Power Cables, Walls:
expected power dissipation ∼ 40kW in < 3.5 m³
efficient heat exchanger and cooling system
Choice of cooling system is pending:
Monophase NOVEC*)
Bi-phase CO2
to be decided
*)3M™ Novec™ 649 Engineered Fluid for heat transfer applications (GWP=1)

## Slide 31: Cooling Chain
Silicon Sensors mounted on CF Ladders
Front-End Electronics Boxes (FEB Boxes) holding the FEBs
Cooling Plates (press-fitted tube channels) with monophase NOVEC 649 or bi-phase CO2 coolant
C-Frame (support structure) to hold the cooling plates and sensors mounted on ladders
K. Agarwal – Tübingen, M. Kis – GSI-DetLab, P. Koczon – GSI DetLab

## Slide 32: Thermal Demonstrator
K. Agarwal – Tübingen, O. Vasylev – GSI Detlab, R. Kapell – GSI DetLab,
A two-station thermal demonstrator is being build to verify all thermal aspects:
efficiency of liquid cooling to remove dissipated heat from FEE ()
efficiency of gas cooling to remove heat from sensor ( )
humidity inside box () (feed throughs!)
integration aspects
realistic heat sources

## Slide 33: Direct Sensor Gas Cooling
K. Agarwal – Tübingen, P. Kuhl - GSI Engineer, Technicians – GSI
measurement of temperature profile along sensors
issues:
  optimization of nozzle
  gas temperature vs. relative humidity
  thermal stress
  induced vibrations vs. flow velocity
  …

## Slide 34: Gas Cooling - Vibrations
S. Metha, K. Agarwal – Tübingen + GSI Technicians
sensor vibrations vs. flow velocity
structural Eigenfrequencies of ladders
…
Laser Doppler Vibrometer
C-frame mock-up with ladder dummy

## Slide 35: Choice of Cooling Plant
Bi-Phase
enthalpy at
kinematic vicosity:
heat transfer coefficient:
superior in all relevant physical parameters
Mono-Phase NOVEC
specific heat :
kinematic vicosity
heat transfer coefficient:
NOVEC operation much simpler, plant commercially available

## Slide 36: MONOPHASE NOVEC 649 – COMPUTATIONAL FLUID DYNAMICS (CFD)
Coolant Temp. = -40°C
Heat Load = 1080 W
Tube ID = 5.4 mm
Tube Length = 2.7 m
Mass Flow = 150 g/s
Pressure Drop = 1.25 bar
Example Case NOVEC with min. temp. and max. load
K. Agarwal – Tübingen
SolidWorks Flow Simulation Module
simulation goal: Max. FEB Temp. < -10°C
Feasibility Study NOVEC:
use of NOVEC requires very low coolant temperature
high flow high pressure drop

## Slide 37: Cooling – Summary and Open Questions
NOVEC:
possible solution, but operation close to physical limits, almost cryogenic
bi-Phase CO2:
possible solution, but large uncertainties in terms of operation & cost (distribution system)
Industrial offers both for NOVEC and CO2 based demonstrator systems available (cost for plant: comparable)
Decision on liquid cooling technology by Q4/2019! (EDR, CERN experts)

## Slide 38: Series Production

## Slide 39: STS Project Plan
J. Heuser – GSI, W. Müller – GSI/FAIR
Detailled planning for production phase: 2019 -2024
most time consuming step: module assembly!
  bonding of >28672 micro cables to sensor and ASICs

## Slide 40: Optical QA of Sensors
E. Lavrik – Tübingen (now GSI):
custom-build scanning station in Tübingen
all sensors will be inspected optically (scanned) upon arrival
identify and classify defects on sensors employing CNN (Convolutional Neural Network)
automatic detection and recognition rate > 96 & 93%, respectively
setup will be transported from Tübingen and installed at GSI DetLab

## Slide 41: Electrical QA of Sensors
I. Panasenko – Tübingen
custom-build probe station in Tübingen
high precision for repetitive steps
allows to inspect 12cm sensors
inspect fraction of sensors (1%-10%) of each delivered batch
setup will be transported from Tübingen and installed at GSI DetLab
strip resistance

## Slide 42: Preparation of Production: Logistics
component data base
  component types
  nomenclatures
  e-logbook
A. Wilms – GSI DetLab, E. Lavrik – Tübingen/GSI (back-end, based on FairDB)

## Slide 43: Module Production Step 1-3
step 1:
TAB bonding of read-out ASIC to micro cables
(
step 2:
test of ASIC-cable bonds
(before bonding to sensor)
step 3:
TAB bonding of “chip cables” to sensor (front side)

## Slide 44: Module Production Step 4-8
step 4:
installation of read-out chips into front-end board (front-side)
step 5-8:
repeat step 1-4 for back side cables
step 9:
testing of complete module!
tools & steps of module assembly have been worked out, but not yet optimized!

## Slide 45: Module Assembly Through-Put
site | #modules | #ladders
JINR | 400 | 46
GSI | 248 | 60
KIT | 248 | -
+ 15% spares
planned module production time: < 2 ½ years for 896 modules
current estimate of GSI/KIT “linear” through-put:
2x3 modules/month required: 2x10 modules/month
  2x30 modules/year
current estimate of JINR “human power optimized” through-put:
10 modules/month required: 16 modules/month
  100 modules/year
Conclusion:
we need careful analysis of all production step, to find out:
bottle-necks, limitations (human power, machine park, tools, …)
potential of parallelization
…
start with pre-series production soon!

## Slide 46: Summary and Conclusions
were do we stand?
finishing R&D phase, few issues remain:
noise ok module level, system aspects have to be addressed (mCBM)
mechanical aspects, vibrational analysis, stiffness, …
thermal aspects, choice of cooling system, sensor gas cooling, …
starting up production phase, few issues to be solved:
micro cables (technology)
module assembly optimization (time)
Thank You!

## Slide 47: Backup

## Slide 48: CBM Experiment at FAIR

## Slide 49: Dipole Magnet

## Slide 50: Delivery schedule of sensors to GSI/FAIR
confirmed by Hamamatsu Photonics Deutschland GmbH, 20 August 2019
delivery |  | sensors |  |  |  |  |  | fraction
batch | week/year | 6x2 | 6x4 | 6x6 | 6x12 | sum | integral | [%]
1 | 45/19 | 20 | 20 | 20 | 20 | 80 | 80 | 7.25
2 | 50/19 | 20 | 20 | 20 | 20 | 80 | 160 | 14.49
3 | 01/20 | 31 | 20 | 20 | 20 | 91 | 251 | 22.74
4 | 07/20 |  | 35 | 35 | 35 | 105 | 356 | 32.25
5 | 11/20 |  | 35 | 35 | 35 | 105 | 461 | 41.76
6 | 15/20 |  | 35 | 35 | 35 | 105 | 566 | 51.27
7 | 19/20 |  | 35 | 35 | 35 | 105 | 671 | 60.78
8 | 24/20 |  | 35 | 35 | 35 | 105 | 776 | 70.29
9 | 28/20 |  | 35 | 35 | 35 | 105 | 881 | 79.80
10 | 33/20 |  | 35 | 35 | 35 | 105 | 986 | 89.31
11 | 37/20 |  | 21 | 21 | 40 | 82 | 1068 | 96.74
12 | 41/20 |  |  |  | 36 | 36 | 1104 | 100.00
sum |  | 71 | 326 | 326 | 381 | 1104 | 1104 | 100.00
sensor variant | serial number | pieces ordered
6x2 | S13847-22 | 71
6x4 | S13847-42 | 326
6x6 | S13847-62 | 326
6x12 | S13847-124 | 381
 | sum | 1104

## Slide 51: Microstrip sensors
4 main variants
strip lengths matched to particle densities in STS
6.2 cm x 2.2 cm - 71 x
6.2 cm x 4.2 cm - 306 x
6.2 cm x 6.2 cm - 296 x
6.2 cm x 12.4 cm - 381 x

## Slide 52: STS-XYTER 2.1 Radiation Studies

## Slide 53: Summary: Charge Collection Efficiency

## Slide 54: MicroCables LTU
Since the microcables are very delicate objects with fine structures, the
manufacturing processes are complex and can cause failures.
For the Aluminum microcables the yield decreases with the cable length.
Yield improvements can be achieved by:
using photomasks with higher resolution
using better equipment
using advanced raw material
improvement of photolithography process
improvement of etching parameters

## Slide 55
build-up of micro-copper-cable of version 2:
surface finish: EPIG (Electroless Palladium, Immersion Gold),
thin (300 nm) noble surface for soldering and bonding in contrast to standard ENIG (5..7µm) (-> Pitch), Palladium serves as a highly efficient diffusion barrier
two copper layers L1/L2 with spacer (30% filling),
laminated to one cable, electrically interconnected
 strip capacitance < 0,8 pF/cm

## Slide 56: Material budget calculations
Alu cable stack per sensor (without shielding and central spacer)
  4 x 15 µm Alu x 1/3 fill factor + 4 x 10 µm PI + 2 x 75 µm meshed PI
  60 µm Si equivalent
Cu cable stack per sensor (without shielding and central spacer)
  4 x 8 µm Cu x ¼ fill factor + 4 x 12.5 µm PI + 2 x 75 µm meshed PI + 4 x 12.5 µm glue
  100 µm Si equivalent
Taken as input for GEANT3 MC simulation
  Geometry version v16g

## Slide 57: STS material budget simulations
Aluminum microcables
Copper microcables (1/4 FF)
Notes: Simulations: Geometry version v16g, 10^7 events, gkCableThickness= 0.006 cm and 0.01 cm (equivalent thickness in Silicon)
Matbudget_mc.C
Matbudget_ana.C
UrQMD (Ultra relativistic Quantum Molecular Dynamics) is a fully integrated Monte Carlo simulation package for Proton+Proton, Proton+nucleus and nucleus+nucleus interactions.
The UrQMD model is part of the GEANT4 simulation package.
The Parton-Hadron-String Dynamics (PHSD) is a microscopic off-shell transport approach that consistently describes the full evolution of a relativistic heavy-ion collision from the initial hard scatterings and string formation through the dynamical deconfinement phase transition to the quark-gluon plasma as well as hadronization and to the subsequent interactions in the hadronic phase. It has been developed by the Giessen/Frankfurt groups on the basis of the Hadron-String Dynamics transport approach (HSD) and in the hadronic sector, PHSD is equivalent to HSD.

## Slide 58: LV Powering Scheme: FEB
P. Koczon – GSI

## Slide 59: STS-XYTER 2.1 Radiation Studies

## Slide 60: Powering
P. Koczon – GSI

## Slide 61: C-frames

## Slide 62: Cooling Challenge
z
y
x
Thermal Enclosure:
CF sandwiched foam (∼ 20 mm) → Structural support
feed throughs
thermal and moisture tight ( at 20°C)

## Slide 63: Sensor QA
QA test done by manufacturer:
current-voltage (IV) and capacitance-voltage (CV) curve, up to 200V
estimation of the full-depletion voltage
strip test:
  all strips - p and n sides, including the corner strips
  AC aluminium open, AC aluminium short), at 30V
QA done done by clident:
10% of sensors/batch will be inspected for
pinholes in capacitor dielectric
strip metal and implant shorts and opens
single strip leakage current
1% of sensors/batch will undergo specific tests
coupling capacitance of the readout strip
polysilicon resistance
interstrip capacitance
strip capacitor breakdown voltage

## Slide 64: NOVEC Data Sheet

## Slide 65: Liquid CO2 Properties

## Slide 66: Cooling – Summary and Open Questions
NOVEC-based cooling system
pro:
available commercially (e.g. LAUDA, Huber)
operation at “low” pressure (
standard operation, simple distribution system to heat exchanger plates
con:
operation at high flow and very low temperature ( (to compensate for “low” heat capacity)
operation at “high” pressure (to compensate pressure loss due to high flow)
“thicker” heat exchanger plate (tube diameter helps )
  minimal thickness 9 mm (ok)
  integration aspects
conclusio:
possible solution, but operation close to physical limits

## Slide 67: Cooling – Summary and Open Questions
CO2-based cooling system
pro:
superior physical parameters in all relevant aspects
  enthalpy/specific heat
  viscosity
  thermal conductivity, heat transfer coefficient
con:
  oil-free systems not commercially available (radiation hardness!)
    evaporative systems (not oil-free) available for supermarket etc.
  present offer is custom made (oil-free), not tested etc.
  operation more difficult (safety margin PED:
  distribution system more complex (tune different flows to saturation line)
    complex, possibly expensive
conclusio:
possible solution, but large uncertainties in terms of operation & cost (distribution system)