## Slide 1: R³B critical items
H. Simon ● GSI Darmstadt
ECE 11 and ECSG 02
Meeting 20191104-05
GSI Darmstadt
LOS Start detector

## Slide 2
Starting point 2016

## Slide 3
L3T (DSSSD,delayed)  AMS up to 8 systems
18 det.ladders (6+12)
Strip pich 50µm
912 ASICS 116736 channels
NeuLAND
8/12 (30) double planes + frame 1600/2400 (6000) el. channels & HV
Advanced tracking system PSPs, MUSIC, plastic ToF (DE and position via ToT)
fibre detector trackers
(partly in vacuum, with electronics)
GLAD & LH2 target station
R3B set up progress
DAQ & Controls (NUSTAR DAQ / EPICS)
Simulation-Analysis (UCESB/R³BRoot)
Califa (forw. Barrel)

## Slide 4
Preparations: R3B SOFIA setup for fission campaign  A. Chatillon
High rate &
resolution
2 fragment
ID: light &
heavy
+ (p, 2p) excitation energy determination
ECE - ECSG Meeting 20191105

## Slide 5
Critical items
L3T Si Tracker (UK) – performance
GLAD (F/D) – technical

## Slide 6
(1) L3T: Project started UK funded ~2009
Status: EoI for FAIR, no TDR; built with UK project funds

## Slide 7
TDR drafted in the process …
(Draft 2017)
Favourable to have a 100µm inner layer
300µm achievable
compromises accepted in R3B collaboration meetings
Two outer layers (300µm) +
thin inner layer (100µm)
reduced to two layers

## Slide 8
Remaining issue: ASIC performance
T
E
Dynamic range 40keV – 50 MeV
Full data readout  noise determines limitations to threshold setting (req. 100keV)
No external trigger forseen (Califa cannot determine coincidence window)
Long strips with large capacitance (noise on outer layer)

## Slide 9
R3B
2019
Status of L3T
Mechanics:
- Completed and tested at Daresbury lab. (DL)
- Vacuum system tested.
- Vacuum chamber delivered at GSI for 2020
campaign)
- New Vacuum chamber (simpler design)
being build to resume tests at DL
- Mechanics for KVI test produced.
Hardware :
- Both inner and outer layers assembled and
cabled at DL
- 2 assembled outer det. show HV issues.
- All 6 inner layers work fine.
- Minimum energy threshold (~150keV),
affecting high energy proton efficiency.
- Noisy strips: ~1.5% disabled per det.
- Spare detectors:
  3 inner detector spares: all working
  1 outer detector spare: has HV issue.
- Extremely low efficiency with Cosmic put
severe doubt on the efficiency.
WG:
Detectors
outer layer covering
inner layer
inner layer
Cabling with additional Common-mode chokes on LV cables

## Slide 10
R3B
2019
Status of L3T
DAQ:
- Triggerless mode & triggered mode available.
(Triggered mode still to be tested).  used for data reduction in buffers!
- Up to 2 external signals (“trigger”) can be use as input
- System synchronisation tested successfully with
external Pseudo-random generator.
- Recently tested with AMS DAQ at GSI and pulse generator.
- DAQ compatibility with MBS still to be completed.
  - Requires completion of the L3T data merger with time ordered data.
  - Delayed as manpower needed for other projects (ex: AIDA at GSI)
Test with cosmic muons:
- 2 plastic scintillators used above and below L3T.
- Coincidence rate between plastic: 0.5Hz
- But coincidences rate with L3T with 150 keV threshold is very low: <1%
Test with proton beam at KVI
- To be performed in November (6-8th).
- Will determine decision regarding future work:
  ASIC replacement / 4th iteration ?
  both solutions leading to large delay and cost.
WG:
Detectors
Contact: Marc Labiche
Clock-Sync-Trigger cards (1 per crate)
AMC cards
(1 per ladder)
micro-TCA crates ( only 2 showed here, 3 used in total)

## Slide 11
L3T and AMS detector test, KVI-CART (End of this week)
Proton beam, up to 190 MeV
4 AMS detectors as external tracker, 2 L3T inner layer detectors as DUT
XY linear stage remote controlled
Critical
performance
decision !

## Slide 12: Backup: Si microstrip detector system for proton and light ion tracking
AMS detector system refurbished:
XY sensitivity, area 28 cm2, 100/110 µm strip pitch
Dynamic range – from p to Fe
1024 channels, multiplexed readout
Position resolution : 40 µm for protons, 15 µm for light ions
Readout – GSI SIDEREM system or AMS DAQ (as a backup)
Tracking of protons, C, P, Ar, Ne ions
Used for quasi-free scattering and 2p-radioactivity experiments
Backup solution replacing L3T for 2020
O. Kiselev et al.

## Slide 13: AMS detectors in Cave C, 2019
4 detectors just few mm behind the target wheel
Theta coverage 14 – 60
Practically full phi coverage

## Slide 14: Preparations: AMS Si microstrip system
Delivered to GSI
Bell chamber
Shipped from
Daresbury
S. Paschalis et al.
ECE - ECSG Meeting 20191105

## Slide 15: Arrangement for 2020 setup
6 detectors in left-right or up-down arragement
Solid or liquid H2 target in the middle
Cooling with water in case of liH2 target keeping temperature < 20-22
Temperature measurement at each detector

## Slide 16
(2) GLAD Magnet - sees field for the first time (Nov/Dec 2018)
Controls for Magnet Powersupply, Quench Protection,
Cryo system running together at real conditions:
He consumption tested,
Ramping tested
Field alignment verified
 Prerequisites for 2019 runs !
Meanwhile: LN2 pre-cooler prepared for sustained operation (07/2019). Campus infrastructure: media supplies - computing – counting room – preparation areas: upgrade measures (2019/20).

## Slide 17
20190225 5:12 Quench @2800A !!!
Quench while ramping up for 124Sn run
Analysis yields bad QD probe contact
Recovery within 48h !!!

## Slide 18
Status of GLAD magnet (F-D in-kind)
Problem tracked down to bad probe contact
… and repaired this summer
Final Cool-down ongoing Dry-run Nov 14th
prior to engineering beam time.
C. Mayri, H.S. T. Hackler et al.
Issues solved – verification in progress