## Slide 1: NUSTAR Project Status
J. Gerl
FAIR-NUSTAR Sub-Project Leader, NUSTAR Technical Coordinator / Project Manager
FAIR/GSI Darmstadt, Germany
Expert Committee Experiment
November 2019

## Slide 2: NUSTAR Overall Schedule
2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027
Phase 0
Phase 1
Super-FRS
NUSTAR caves
NUSTAR experiments
construction and installation
civil construction
Day one
Early Start
operation at FAIR
installation
commissioning
full operation
construction/operation „outside“ FAIR (GSI and ext.)
commissioning
Modular detectors enable step-wise upgrade of set-ups for early physics exploitation
infrastructure inst.

## Slide 3: NUSTAR Project Progress
Schedule analysis
S- curve comments & mitigation proposal milestone in the past
1.2.5.1.2.5 (2.6%) – Neutron ToF spectrometer (NeuLAND)
FAT in clarification
S- curve comments & mitigation proposal progress delay
1.2.5.1.1.2 (4,8%) – GLAD magnet
Awaiting final SAT measurements
1.2.1.2.1 (3,0%) GSI-PMA Stopping cell, extraction, cooling, beam-distribution system and electrostatic beamlines
Awaiting ECE approval of TDR
1.2.3.3 (0,5%) – RFQ and switchyard
Awaiting detailed technical specs for contract
None are time critical

## Slide 4
Risk Register
Inclusion of technical risks for Si-Tracker and DEGAS agreed
Risk ID | Status | Risk description | Probability | Performance impact | Risk Score | Strategy | Preventive mitigation | Contingency plan | Residual Risk | Approval status
173 | Mitigation proposed | NUSTAR Common Cause: The budget for infrastructure is not approved yet. It is supposed to come from common fund that requires a signed or at least agreed MoU. Event: No budget available to order infrastructure. Impact: Installation of experiment cannot start. | 25% | severe | 14 | mitigate | Request for additional funds from GSI (2 Million EUR) | Other money source have to be made available. | 0 | 2019-10-15
240 | Mitigation ongoing | LaSpec Cause: LEB Buncher/Spectrometer has been assigned to accelerator as part of the CBWG review. Full version is recommended by CBWG. Funding needs to be ensured. Event: Budget not yet available. Impact: Required specifications may not be reached; Realization might be delayed. Experiments cannot be performed at all (worst case scenario). | 25% | major | 13 | escalate | Further optimize the design to save costs (done) . Decision about the funding is pending. |  | 0 | to be decided @ Council until 2019-12-6
157 | Mitigation ongoing | R3B Quadrupole Triplett Cause: Multiplet R3B and cryogenic infrastructure has been assigned to accelerator as part of the CBWG review. Funding needs to be ensured. Event: Budget not yet available. Impact: R3B experiments cannot be performed. | 25% | major | 13 | escalate | Assign item to relevant area and find best market prices /technical solution (done). Decision about the funding is pending. |  | 0 | to be decided @ Council until 2019-12-6
156 | Mitigation ongoing | LaSpec Cause: Laser and DAQ Hut LEB cave has been assigned to FAIR site and building as part of CBWG review. Funding needs to be ensured. Event: Budget not yet available. Impact: Incomplete infrastructure for LASPEC and HISPEC, possible safety issue and denial of operative license. | 25% | major | 13 | escalate | Assign item to relevant area and find best market prices /technical solution (done). Decision about the funding is pending. |  | 0 | to be decided @ Council until 2019-12-6
155 | Mitigation ongoing | LEB infrastr. Cause: LEB beam dump and/or HEC beam dump has been assigned to accelerator as part of the CBWG review. Funding needs to be ensured. Event: Budget not yet available. Impact: Possible beam safety issues and denial of operative licence @NUSTAR experiment caves. | 25% | major | 13 | escalate | Assign item to relevant area and find best market prices /technical solution (done). Decision about the funding is pending. |  | 0 | to be decided @ Council until 2019-12-6
Waiting for decision on Common Funds
Assigned to ACC, decision on funding pending
Assigned to ACC, decision on funding pending
Assigned to FSB, decision on funding pending
Assigned to ACC, decision on funding pending

## Slide 5: TDR Status
TDR # | title | submission | date | approval | date
 |  | status |  | status | 
2_01 | LEB infrastructure | expected | Nov 19 |  | 
2_02 | Cryogenic Stopping cell | submitted | Aug 18 |  | 
2_03 | Beam tracking/identification | obsolete |  |  | 
2_04 | HISPEC/DESPEC infrastructure | submitted | Nov 18 |  | 
2_05 | NUSTAR DAQ | submitted | Nov 16 | approved | Jun 18
2_06 | MINOS | obsolete |  |  | 
2_07 | Active target (India) | expected | Nov 22 |  | 
2_08 | HYDE | expected | Nov 22 |  | 
2_09 | LYCCA | submitted | Jun 08 | approved | Sep 08
2_10 | Plunger | submitted | Apr 14 | approved | Jun 14
2_11 | AIDA | submitted | Aug 08 | approved | Mrz 13
2_12 | DEGAS | submitted | Aug 14 | approved | Jul 15
2_13 | FATIMA | submitted | Mrz 15 | approved | Jul 15
2_14 | BELEN | submitted | Jan 14 | approved | Aug 14
2_15 | MONSTER | submitted | Feb 13 | approved | Aug 14
2_16 | NEDA | submitted | Sep 14 | approved | Jan 16
2_17 | DTAS | submitted | Apr 12 | approved | Jan 13
2_18 | Isomeric moments | expected | Nov 19 |  | 
2_19 | MATS/LaSpec | submitted | Sep 09 | approved | Mai 10
2_20 | R3B multiplet | obsolete |  |  | 
2_21 | GLAD | submitted | Jun 06 | approved | Jul 08
2_22 | R3B tracking | submitted | Nov 14 | approved | Jul 15
2_23 | Large Area ToF Wall | obsolete |  |  | 
2_24 | CALIFA barrel | submitted | Nov 11 | approved | Jan 13
2_25 | CALIFA fwd endcap | submitted | Nov 14 | approved | Jul 15
2_26 | Si tracker | expected | Mrz 20 |  | 
2_27 | NeuLAND | submitted | Nov 11 | approved | Jan 13
2_28 | R3B vacuum | expected | Sep 19 |  | 
2_29 | R3B infrastructure | expected | Nov 19 |  | 
2_30 | R3B spectrometer | expected | Nov 21 |  | 
2_31 | R3B spectrom tracking | obsolete |  |  | 
2_32 | ACTAF | submitted | Sep 15 | approved | Jun 17
2_33 | ILIMA Schottky | submitted | Dez 17 | approved | Dez 18
2_34 | ILIMA TOF detectors | submitted | Dez 17 | approved | Okt 18
2_35 | ILIMA Heavy ion detector | submitted | Nov 17 | approved | Okt 18
2_36 | AGATA | obsolete |  |  | 
2_37 | Slowed down beam setup | expected | Nov 21 |  | 
2_38 | EXPERT | submitted | Sep 16 | approved | Jul 17
2_39 | Super-FRS Exp infrastructure | submitted | Mai 19 |  | 
2_40 | Liquid hydrogen target | expected | Jul 21 |  | 
2_41 | (Ice target and tensor force) | expected | Jul 21 |  | 
2_42 | (future WASA) | expected | Jul 24 |  | 
3 under evaluation by ECE
4 needed for Day-one and are still expected in the next months
8 more expected, but not time critical
21 approved

## Slide 6: Score Card
progressing steadily…

## Slide 7: Super-FRS and NUSTAR Caves
All NUSTAR experiments are planned to move into the FAIR buildings in 2022-2024.
Realization planning is ≈3/6 months (caves/CR) behind schedule.
LEB
HEB
Super-FRS
CR
H-ESR

## Slide 8: NUSTAR Installation Workshops 2019
How to install technical infrastructure and experimental equipment…
all infrastructure items identified
sequence of installation work defined
required installation personnel specified

## Slide 9: Initial installation plan
… will be refined and parallelized in the coming two years
result of yet another workshop with building planners…

## Slide 10: Digital Mock Up
A detailed 3D model of the whole facility helps to avoid collisions
Experiments are asked to provide set-up models to be included in the facility model

## Slide 11: Recent Infrastructure Activities
General NUSTAR Cave Infrastructure is handled by FSB and Super-FRS machine in close consultation and collaboration with NUSTAR.
Cable data base (almost) completed
Detector gas supplies (including LN2) defined
Cooling power needs updated
Electronic racks organized
Concrete shielding blocks organized
Access defined for all doors
UPS and clean power in discussion
….

## Slide 12: Critical to Success
Acquiring funding for NUSTAR infrastructure through MoU
Fulfilling all formal safety requirements to be able to operate the planned set-ups
Getting sufficient beam time at GSI for i) testing FAIR/NUSTAR equipment, ii) re-gaining operating experience and iii) training scientists and technicians

## Slide 13: LEB Buncher/Spectrometer
Assigned to Accelerator (Super-FRS)
India stepped back from realization
Funding pending
Plan to go for slightly modified Super-FRS multiplets
Dipoles cannot be copied, but are producable by industry
Delivery and testing planned at the end of the Super-FRS sequence…

## Slide 14: Phase-0 detectors successfully used
FATIMA in operation at GANIL
DTAS in operation at JYFL
MATS/LaSpec at TRIGA Mainz
NEULAND in operation at RIKEN
FATIMA
AGATA
MATS
LASPEC

## Slide 15: LaSpec – Phase 0 program
TRIGA-LASER Beamline
ATLAS & CARIBU:
Conditions comparable to LEB (Beams at 5 kV)
Perfect place to test and optimize the new prototypes
2021/22: Return to FAIR for Day-1 experiments
MATS/LASPEC at TRIGA Mainz
TDR done

## Slide 16
Continued operation of MATS prototype TRIGA-TRAP at research reactor TRIGA Mainz
Technical and methodical developments for mass spectrometry
Characterization and improvements of cryogenic stopping cell for MATS/LASPEC
MATS – Phase 0 program
TDR done

## Slide 17: HISPEC – ready for operation
-LYCCA heavy ion calorimeter with ToF capability in operation Day-1
-AGATA gamma spectrometer in operation Day-1
-NEDA Neutron detector array under construction Phase-1
-Hyde light particle array prototype Phase-1
HISPEC-0 was used at GSI in 2012-2014, next utilization on Day-1
TDRs done

## Slide 18: DESPEC at FRS/S4
DESPEC setup at S4 of the FRS First successful test in April
active implanter AIDA
fast beta detector b-plast
fast gamma detector array FATIMA
high-resolution gamma monitor DEGAS/GALILEO
ion timing detector FINGER
EDAQ sub-systems coupled with white rabbit
Purpose of the tests
Check basic functionality of sub-systems
Check white rabbit correlation
Investigate response of detectors to ions and radiation background
Latest news: Time resolution of FATIMA improved from 340 ps to 220 ps by
using TAMEX!

## Slide 19
use DTAS to measure β-strength distributions
use FATIMA to measure lifetimes
use DEGAS for high-resolution spectroscopy
use MONSTER to perform neutron spectroscopy
take AIDA as common active implanter
Ingredients for a successful DESPEC Phase-0 programme at GSI

## Slide 20: R3B Set-up
neutrons
heavy fragments
protons
light fragments
-rays
protons
NeuLAND
CALIFA
Si Tracker
Tracking
Detectors
GLAD
Notes: 20

## Slide 21: R3B - Readiness
neutrons
heavy fragments
protons
light fragments
g-rays
protons
Tracking
Detectors
Experiments Phase O
Day 1
GLAD : 100% in operation and employed for experiments in Q2 2019
CALIFA: Detector in DEMONSTRATOR configuration ready for experiments
NeuLAND: 40 % of final detector in operation since 2018
L3T Si-Tracker: Detector in 2 layer version not yet in operation (see report by H. Simon)
Full detector readiness depends on evolution of funding situation
After detector completion, dedicated calibration and commisioning experiments will be needed
Extended commissioning beam time has started, first runs with stable beams have been performed
Dedicated experiments for CALIFA and NeuLAND calibrations have been performed
On-site experienced man-power is required for running and maintenance of the complex equipments
Most TDRs done, Infrastructure and Si-Tracker in preparation
Notes: 21

## Slide 22
R3B - Coulomb dissociation of 16O on 208Pb
Challenging Setup
109 pps
K. Göbel, M. Heil, R. Reifarth et al.

## Slide 23: ILIMA Phase-0
Critical Issues
-Repair of electron cooler drifttubes postponed
-Slow-down required to start ESR-Cryring program
New Schottky pickup being tested
Experimental program at ESR and Cryring planned starting in 2020 with already approved experiments

## Slide 24: ILIMA – Day-1
All TDRs done
Move to CR/H-ESR not before 2026

## Slide 25: NUSTAR Early Implementation
Super-FRS including the high-energy cave
and a dedicated experimental area in front of it
Commissioning and early physics program
possible with SIS18 beams
Low-energy and ring branch will be taken
consecutively into operation

## Slide 26
R3B Cave C currently
DESPEC S4 currently
DESPEC FHF1
early imp. 2025
DESPEC LEB
from 2026
Moving to FAIR
R3B Cave C from 2025
ILIMA at ESR
from 2020
SFRS-CSC
from 2026
SFRS-CSC
early imp. 2025
SFRS-CSC S4
currently

## Slide 27
DESPEC Experiments |  | Year
Commission AIDA + FATIMA at FRS |  | 2019
Commissioning and experiment runs Sxxx, S452, S460 |  | 2020
Commission AIDA + DEGAS and run S450 and further experiments to be proposed |  | 2021
Continue commissioning new detectors and performing respective experiments |  | 2022
 |  | 2023
Continue experiments at moderate scale at FRS | Install compact set-up (AIDA+DEGAS) at Super-FRS FHF1 | 2024
 | Commissioning and first experiments at Super-FRS FHF1 | 2025
 | Install full initial DESPEC set-up at LEB and run first experiments | 2026
DESPEC Time Line

## Slide 28: Conclusions
All NUSTAR Sub-Projects perform experiments in FAIR Phase-0
Preparations for Phase-0 and Day-1 are well advanced, in time, with no apparent show-stoppers (assuming funding, in particular for infrastructure items, will be available in time)
The anticipated set-ups will enable an interesting program with important results
Transition from GSI FRS to FAIR Super-FRS will be done gradually with selected experiments continuing at GSI FRS beyond the start of the Super-FRS

## Slide 29: Super-FRS Experiment - WASA set-up
Planned set-up at the FRS
for Hypernuclear experiments in Phase-0

## Slide 30: WASA at S2
Set-up and preparation time: 2-3 months planned after beam time period 2020
Experiment performance: Could be early in the beam time period 2021
Removal time: 1-2 weeks directly after beam taking

## Slide 31: Stopping Cell for the LEB of the Super-FRS
Further tests and first experiments with prototype at the FRS Ion Catcher in FAIR Phase-0
Helium recovery unit:
approved by FAIR Council ;
in-kind contract with Sweden
/ Finland in preparation
TDR in preparation
Technical design and construction well advanced
Collaboration
GSI / JLU Gießen / KVI-CART
Univ. Jyväskylä / ELI-NP / Univ. Tel Aviv