## Slide 1: cw-LINAC (14.12.2020)
    Advanced Demonstrator (HI-Mainz activities)
    CH-cavities (CH1&2) at RI for final preparation
      CH1 delivered to Mainz, first RF-test @HI-Mainz in the horizontal test cryostat asap
      CH2 delivered to Frankfurt, Rf-testing @ GUF in a vertical cryostat asap
        Further testing not possible due to missing Oxygen sensor!
    HI-Mainz Lab-activities
    preparation of test cryostat o.k.
    set up of cryo, rf, controls-infratsructure o.k.
    preparation of test cave o.k.
CH1-Test
HIM/Lab.
First cavity test at horizontal cryostat
(Mainz, December 19)

## Slide 2
    Preparation of Advanced Demonstrator cave and its infrastructure
    setup of bunker accomplished => setup of infrastructure => setup of beamline
    dismantling of the scaffolding => cleaning SH1 (G. Gruber)
    set up of cryo transfer line, incl. all distr. boxes and controls – Restart of activities – weld inspection (X-Ray) accomplished
    Ordering
      4 RF-amplifiers (o.k.)
      2 sc solenoids (delivery: Q2/2020)
      cryostat I (delivery: Q2/2020)
      cryostat II (o.k.)
      (ultrapure) Niobium delivered (SAT, qualification at DESY this week)
      2 sc rebunchers (o.k.)
      2 sc CH cavities (CH1 FAT, SAT o.k.)
      cryo supply controls (o.k.)
      2 Feschenko Monitors (cw-Linac + p-Linac) (delivery: autumn 2020, SAT at cw-Linac-transfer line)