## Slide 1: Super-FRS requirements to reach intermediate results
Haik Simon
FAIR-BINP Workshop May 25-29, 2020

## Slide 2: Delivery Matrix Nov. 2019
FAT First of Series
FDR First of Series

## Slide 3: Overview components

## Slide 4: Overview components

## Slide 5: Potential resource issue?
All delays seem to be related to the design
Prioritization of resources?
Name | Milestone | Real date | Contract date
NC dipoles | FDR accepted (M7) (payment associate) | 14/09/2020 | 16/12/2019
NC dipoles chambers R&D | Mid-term meeting: preliminary design review (PDR) with preliminary 3D-Model (payment associated) | ? | 20/05/2020
NC Multipoles R&D | Mid-term report R&D (after 3 months) (acceptance of IK – mechanical design) | ? | 11/12/2019
SC Standard-Dipoles Chambers | CDR FoS accepted (M6) | ? | 28/11/2019
SC Standard-Dipoles Chambers | FDR FoS accepted (M7) | ? | 20/02/2020
SC Standard-Dipoles Chambers | CDR accepted (M6) | ? | 26/03/2020
SC Standard-Dipoles Chambers | FAT FoS accepted (M9) | ? | 30/04/2020
Diagnostic chambers | FDR M7 FoS diagnostic chamber (payment associate) | ? | 30/09/2019
Diagnostic chambers | CDR accepted (M6) (payment associate) | ? | 21/12/2019
Diagnostic chambers | FAT FoS diagnostic chamber (payment associate) | ? | 29/02/2020
Diagnostic chambers | FDR accepted (M7) (payment associate) | ? | 31/03/2020
SC Branched-Dipoles Chambers | M4 - contract - vacuum chamber sc branched dipoles (design issue) |  | 

## Slide 6: Status of vacuum components
late, but still ok
NC-dipole chamber R&D
SC-standard dipole chambers
Pre-assembly FoS dipole: Q1/Q2 2021
Logistic issue (~ 60 tons/magnet)
SC-branched dipole chambers
Contract not finalised due to potential design issue. Production(s) to be scheduled in accordance to magnet delivery schedule
Apparent slight delay:
FoS design (02/2020) not ready
FAT FoS (04/2020): ?
Diagnostic chambers
Delay:
FoS design ( 09/2019  ~ today )
FAT FoS ( 02/2020  ? material procurements started )
BPM
Necessary design adaptations may still delay the contract finalization
Few remaining contracts for standard components on their way…

## Slide 7: Status of NC dipoles
≈95 ton
Target Area
Detailed specs released
MIC ordered by FAIR
Contract signed on 15/03/2019
Conceptual Design Review (02/03/2020)
Final Design Review: expected on 09/2020 (delay: 9 months)
Issue: purchase of iron
Originally planned purchasing together with nc multipoles may not occur.  Cost of iron would be higher than expected
 purchasing strategy affects real cost of nc dipoles and multipoles!

## Slide 8
≈30 ton
≈30 ton
R&D contract signed on 16/09/2019
R&D first results basis for closure of IKC due on 11/2019
 IKC Contract signature expected Q4/2019
End of R&D (CDR): March 2020 (not yet achieved)
Actual MSP Plan:
Contract signature: if now (?)
FDR: 11/2020
End of SAT: Dec 2022
Installation (actual LCM): January 2023
no buffer anymore !
Status of NC multipoles

## Slide 9: Conclusions
Urgent: enabling decision on nc multipole production !
Issues: assure production and delivery of assembly components according to harmonized schedule
Readiness of Super-FRS is one of few projects goals with priority.