## Slide 1: CR status
Dmitry Shwartz
on behalf of the BINP team
4th BINP-FAIR Collaboration Coordination Workshop, WWW, 25-29 May 2020

## Slide 2: CR status
Dmitry Shwartz
on behalf of the BINP team
4th BINP-FAIR Collaboration Coordination Workshop, WWW, 25-29 May 2020
Not based on a dashboard,
just status as is

## Slide 3: Collector Ring overview
Beam from
p_bar & SFRS
Extraction to HESR
RF debunchers
Inj/Extr kickers
Stochastic cooling
pickups
Stochastic cooling
kickers
ToF detector
Inj septa
Extr septa
Dipole
NQ
EWQ
SWQ
WQ
Sextupole
Pickup
CR
HESR

## Slide 4: Magnets: Dipole
Spec
CDR
FDR
FoS
FAT
SAT
One of two (upper and lower) 20 ton yoke blocks
FoS coils
Parts of inner pole block
FoS ready for tests: July-2020
Delivery to FAIR: Dec-2020
Yoke side block in press cradle
Test lamina of the magnet pole part @ measuring machine
Stamping matrix for side blocks

## Slide 5: Magnets: multipoles and steerers
Spec
CDR
FDR
FoS
FAT
SAT
WQ – FDR released, both for CR/TCR1. FoS production has been started.
SWQ, EWQ, NQ, NQM, NQS – CDR done, docs corrections nearly finished. Manufacturing tooling design is ongoing.
Sextupoles – CDR presented, design is ongoing.
Octupoles coils – CDR presented, design is nearly finished.
Wide Steerers – CDR released, FDR done, corrections ongoing.
Combined steerers – CDR released, FDR done, corrections ongoing. Two FoS are manufactured, preliminary magnetic measurements has been performed.
TCR1 combined steerer (1 pcs) – spec is in work.
WQ support stress analysis
WQ and sextupole
Wide vertical steerers
Steerer FoS preliminary magnetic measurements

## Slide 6: Power Converters
Spec
CDR
FDR
FoS
FAT
SAT
Dipole PC – CDR is in progress, procurement of main power part via FAIR is foreseen (~700 k€).
QPC – Type-1,2 CDR released, Type-3 CDR done. Pre-prototype is under study. Prototype production has been started.
Sextupoles PC – CDR under preparation.
Steerers PC – CDR under preparation.
QPC pre-prototype
testing
QPC racks model
QPC prototype delivery to FAIR for dipole measurements: Dec-2020

## Slide 7: Injection/Extraction Kickers
Spec
CDR
FDR
FoS
FAT
SAT
CDR was presented in Nov-2019. The set of docs ready for upload to EDMS.
HV cables is still not agreed: coax is a baseline. EMI is under discussion.
Procurement of ferrites, feedthroughs and HV PC via FAIR has been started after Ammendment-1 signing.
Kicker module 3D-model
Vacuum tank stress analysis
Field distribution

## Slide 8: Injection/Extraction Septa
Spec
CDR
FDR
FoS
FAT
SAT
Inj septa pre-CDR was presented in Nov-2019. Docs are in progress.
Hot topic: field quality demands in the spec are too tough. Change request prepared.
Extr septum: divided into 2 magnets. Design is ongoing. CR for spec is needed.
300mm
flange
550mm
flange
Support platforms
CR Vac. chamber
4σ pbar beam
to HESR
Bellow knob
16 turns
primary coils
Septum electrode
Secondary
coil envelope
60mm ceramic Vac.Chamber
Yoke
Vac.chamber
Injection septa
Extraction septum pulsed field inhomogeneity

## Slide 9: Diagnostics
Spec
CDR
FDR
FoS
FAT
SAT
Wide pickup prototype
Scrapers supports
Pickup preamplifier prototype
Pickups – FDR done in Nov-2019. Docs are in progress. Wide prototype is under intensive study. Small prototype manufacturing is ongoing. One TCR1 pickup in not designed yet.
Scrapers – FDR done in Nov-2019. Docs are nearly ready. Wide type manufacturing is ongoing.
Scintillators – CDR released. FDR coming soon. Scintillating plates partially produced. Optical components are purchased. Manufacturing has been started.
Stoppers – CDR released. Design is finished. FDR upcoming.
RGM – CDR docs are nearly finished, coming soon.
FCT, DCCT – CDR,FDR released. Purchase via FAIR is assumed. Annoying item: TCR1 FCT is not contracted!
Scrapers vacuum chamber parts
RGM 3D-model
Scintillating screens: manufactured plates, purchased objectives & CCDs
Scraper 3D-model

## Slide 10: Vacuum
Assembly of dipole and quad chambers prototypes test: vacuum achieved!
Spec
CDR
FDR
FoS
FAT
SAT
Dipole chamber – CDR released. Prototype ready and tested.
Quadrupole camber – CDR released. 2 prototypes tested, one will be delivered to FAIR for tests with MW ceramic tubes.
Other CR components – specs released, design is finished. CDRs upcoming.
Pumps – are part of FAIR purchase.
TCR1 components – design is ongoing, specs are in progress.
All the welded flanges changed to CR-K type.
MW damping system to be installed into hexagonal chamber

## Slide 11: Summary
Subproject Collector Ring moves from design phase to the manufacturing phase.
The documentation/models/drawings matching that are needed for milestones passage takes significantly more time than we expected.
Various managing efforts are ongoing: contracts amendments; procurement via FAIR; temporary import; etc.
Vacuum chamber for SC MW damping system tests will be ready for delivery in July.
First CR component delivery (FoS dipole and QPC prototype) is expected @ FAIR site in December 2020.
Thank you for your attention!