## Slide 1: 4th BINP Workshop Video-Conference 25. – 29.05.2020 Site Management – Resource Planning
H Reich-Sprenger & H Hagelskamp

## Slide 2
Site Management – Resource Planning
Objectives:
Collaboration agreements for HEBT
Pre-Assembly / Installation HEBT A – Resource Planning
Pre-Assembly / Installation HEBT B – Resource Planning
Pre-Assembly / Installation HEBT C – Resource Planning
FAIR Resource Planning HEBT
Resource Planning CR (BINP)
Resource Planning SRFS (BINP)

## Slide 3
Pre-Assembly HEBT Magnets & Vacuum Chambers Batch2&3
Provider Obligations
Installation of vacuum chambers into the magnets at the Company‘s site together with 3rd party and with support of the Company
To support the mounting of the vacuum chambers into the magnets at FAIR site, this equates an effort of 2200 person-hours for the vacuum part of mounting 272 vacuum chambers.
Site Management – Resource Planning

## Slide 4
Tunnel installation HEBT Magnets & Vacuum Chambers
Provider Obligation
For Batch 2&3
  Preparation for installation on Company‘s site (including vacuum chamber installation into magnets).
  Provision of personnel for the transport and approximate placement into the tunnel.
  Necessary training of the Company personnel.
For Batch 4:
  Installation of the complete system at the FAIR company site.
Site Management – Resource Planning

## Slide 5
Site Management – Resource Planning
HEBT A Scope:
pre-assembly and installation of 145 VC (incl. Efremov Batch 1) and 107 NCM
pre-assembly to start 6 months before installation (Dec-2020)
estimated resource required:
  pre-assembly: ...... from BINP; ...... from FAIR.
  installation: …… from BINP; …… from FAIR.
batch 4 VC to be delivered in 2021.

## Slide 6: Site Management – Resource Planning
HEBT B Scope:
pre-assembly and installation of 87 VC and 83 NCM
pre-assembly to start 6 months before installation (Dec-2021).
estimated resources required:
  pre-assembly: …… from BINP; …… from FAIR
  installation: …… from BINP; …… from FAIR
Batch 4 VC delivery to start in 2021.

## Slide 7: Site Management – Resource Planning
HEBT C Scope:
pre-assembly and installation of 71 VC and 71 NCM
pre-assembly to start 6 months before installation.
estimated resource required:
  pre-assembly: …… from BINP; …… from FAIR.
  installation: …… from BINP; …… from FAIR.
Batch 4 VC Deliveries to start in 2021.

## Slide 8
FAIR Site Management
Installation Resource Planning
Site Management – Resource Planning

## Slide 9: Site Management – Resource Planning HEBT Installation - Mechanicals
Chart: 
| Mai. 21 | Jun. 21 | Jul. 21 | Aug. 21 | Sep. 21 | Okt. 21 | Nov. 21 | Dez. 21 | Jan. 22 | Feb. 22 | Mrz. 22 | Apr. 22 | Mai. 22 | Jun. 22 | Jul. 22 | Aug. 22 | Sep. 22 | Okt. 22 | Nov. 22 | Dez. 22 | Jan. 23 | Feb. 23 | Mrz. 23 | Apr. 23 | Mai. 23 | Jun. 23 | Jul. 23 | Aug. 23 | Sep. 23 | Okt. 23 | Nov. 23 | Dez. 23 | Jan. 24 | Feb. 24 | Mrz. 24 | Apr. 24 | Mai. 24 | Jun. 24 | Jul. 24 | Aug. 24 | Sep. 24
SMG_Alignment_Engineer
SMG_Alignment_Technician
SMG_Electrician_Engineer
SMG_Electrician_Technician
SMG_Electrician_Worker
SMG_Logistic_Engineer
SMG_Logistic_Technician
SMG_Logistic_Worker
SMG_Mechanic_Engineer | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 6 | 6 | 9 | 7 | 5 | 3 | 1.65 | 1.65 | 1.65 | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SMG_Mechanic_Technician | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SMG_Mechanic_Worker | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 7 | 9 | 15 | 14 | 9 | 10 | 2 | 4 | 12 | 4 | 0 | 3.6 | 4.4 | 0 | 0 | 0 | 1.2 | 5.2 | 0 | 1.2 | 1.2 | 0 | 0 | 0 | 0
SMG_Scientist
Based on FAIR Installation Concept HEBT – November 2019

## Slide 10: Site Management – Resource Planning HEBT Installation - Electricians
Chart: 
| Mai. 21 | Jun. 21 | Jul. 21 | Aug. 21 | Sep. 21 | Okt. 21 | Nov. 21 | Dez. 21 | Jan. 22 | Feb. 22 | Mrz. 22 | Apr. 22 | Mai. 22 | Jun. 22 | Jul. 22 | Aug. 22 | Sep. 22 | Okt. 22 | Nov. 22 | Dez. 22 | Jan. 23 | Feb. 23 | Mrz. 23 | Apr. 23 | Mai. 23 | Jun. 23 | Jul. 23 | Aug. 23 | Sep. 23 | Okt. 23 | Nov. 23 | Dez. 23 | Jan. 24 | Feb. 24 | Mrz. 24 | Apr. 24 | Mai. 24 | Jun. 24 | Jul. 24 | Aug. 24 | Sep. 24
SMG_Alignment_Engineer
SMG_Alignment_Technician
SMG_Electrician_Engineer | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 4 | 4 | 4 | 6 | 18 | 19 | 12 | 11 | 7 | 6 | 12 | 9 | 7 | 6 | 5 | 9 | 4 | 2 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0
SMG_Electrician_Technician | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 3 | 5 | 4 | 4 | 12 | 8 | 5 | 6 | 6 | 7 | 9 | 7 | 6 | 9 | 9 | 10 | 6 | 4 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0
SMG_Electrician_Worker | 0 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4 | 3 | 4 | 4 | 13 | 11 | 9 | 8 | 6 | 3 | 0 | 0 | 0 | 6 | 4 | 3 | 4 | 3 | 3 | 3 | 0 | 2 | 2 | 0 | 0 | 0
SMG_Logistic_Engineer
SMG_Logistic_Technician
SMG_Logistic_Worker
SMG_Mechanic_Engineer
SMG_Mechanic_Technician
SMG_Mechanic_Worker
SMG_Scientist
Based on FAIR Installation Concept HEBT – November 2019

## Slide 11: Site Management – Resource Planning HEBT Installation - Mechanicals
Chart: 
| Jan. 23 | Feb. 23 | Mrz. 23 | Apr. 23 | Mai. 23 | Jun. 23 | Jul. 23 | Aug. 23 | Sep. 23 | Okt. 23 | Nov. 23
CR SMG_Alignment_Engineer
CR SMG_Alignment_Technician
CR SMG_Electrician_Engineer
CR SMG_Electrician_Technician
CR SMG_Electrician_Worker
CR SMG_Logistic_Engineer
CR SMG_Logistic_Technician
CR SMG_Logistic_Worker
CR SMG_Mechanic_Engineer | 3 | 5 | 3 | 2 | 4 | 2 | 2 | 4 | 4 | 3
CR SMG_Mechanic_Technician | 3 | 5 | 3 | 2 | 4 | 2 | 2 | 4 | 4 | 3
CR SMG_Mechanic_Worker | 12 | 20 | 12 | 8 | 16 | 8 | 8 | 16 | 16 | 12
CR SMG_Scientist
Based on BINP Installation Concept CR – February 2020

## Slide 12: Site Management – Resource Planning HEBT Installation - Electricians
Chart: 
| Jan. 23 | Feb. 23 | Mrz. 23 | Apr. 23 | Mai. 23 | Jun. 23 | Jul. 23 | Aug. 23 | Sep. 23 | Okt. 23 | Nov. 23
CR SMG_Alignment_Engineer
CR SMG_Alignment_Technician
CR SMG_Electrician_Engineer
CR SMG_Electrician_Technician
CR SMG_Electrician_Worker | 6 | 10 | 6 | 4 | 8 | 4 | 4 | 8 | 8 | 6
CR SMG_Logistic_Engineer
CR SMG_Logistic_Technician
CR SMG_Logistic_Worker
CR SMG_Mechanic_Engineer
CR SMG_Mechanic_Technician
CR SMG_Mechanic_Worker
CR SMG_Scientist
Based on BINP Installation Concept CR – February 2020

## Slide 13: Installation Ressources SFRS Mechanicals
SFRS
Pre-Assembly of Magnet Chambers at FAIR Site.
BINP Resource Planning ??

## Slide 14: Installation Ressources SFRS Mechanicals
Chart: 
| Mai. 21 | Jun. 21 | Jul. 21 | Aug. 21 | Sep. 21 | Okt.21. | Nov.21. | Dez. 21. | Jan. 22 | Feb. 22 | Mrz. 22 | Apr. 22 | Mai. 22 | Jun. 22 | Jul. 22 | Aug. 22 | Sep. 22 | Okt. 22 | Nov. 22 | Dez. 22 | Jan. 23 | Feb. 23 | Mrz. 23 | Apr. 23 | Mai. 23 | Jun. 23 | Jul. 23 | Aug. 23 | Sep. 23 | Okt. 23 | Nov. 23 | Dez. 23 | Jan. 24 | Feb. 24 | Mrz. 24 | Apr. 24 | Mai. 24 | Jun. 24 | Jul. 24 | Aug. 24 | Sep. 24 | Okt. 24 | Nov. 24 | Dez. 24
SMG_Alignment_Engineer
SMG_Alignment_Technician
SMG_Electrician_Engineer
SMG_Electrician_Technician
SMG_Electrician_Worker
SMG_Logistic_Engineer
SMG_Logistic_Technician
SMG_Logistic_Worker
SMG_Mechanic_Engineer | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 5 | 5 | 10 | 10 | 9 | 8 | 8 | 5 | 4 | 5 | 5
SMG_Mechanic_Technician | 1 | 1 | 2 | 4 | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 4 | 4 | 10 | 10 | 20 | 20 | 16 | 15 | 12 | 4 | 3 | 3 | 2
SMG_Mechanic_Worker | 4 | 4 | 14 | 17 | 8 | 6 | 4 | 0 | 4 | 3 | 4 | 4 | 3 | 5 | 4 | 9 | 12 | 12 | 19 | 18 | 13 | 21 | 19 | 15 | 11 | 10 | 9 | 2 | 2
SMG_Scientist

## Slide 15: Installation Ressources SFRS Electricians
Chart: 
| Mai. 21 | Jun. 21 | Jul. 21 | Aug. 21 | Sep. 21 | Okt.21. | Nov.21. | Dez. 21. | Jan. 22 | Feb. 22 | Mrz. 22 | Apr. 22 | Mai. 22 | Jun. 22 | Jul. 22 | Aug. 22 | Sep. 22 | Okt. 22 | Nov. 22 | Dez. 22 | Jan. 23 | Feb. 23 | Mrz. 23 | Apr. 23 | Mai. 23 | Jun. 23 | Jul. 23 | Aug. 23 | Sep. 23 | Okt. 23 | Nov. 23 | Dez. 23 | Jan. 24 | Feb. 24 | Mrz. 24 | Apr. 24 | Mai. 24 | Jun. 24 | Jul. 24 | Aug. 24 | Sep. 24 | Okt. 24 | Nov. 24 | Dez. 24
SMG_Alignment_Engineer
SMG_Alignment_Technician
SMG_Electrician_Engineer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 4 | 4 | 1 | 24 | 3 | 2
SMG_Electrician_Technician | 1 | 1 | 1 | 1 | 1 | 4 | 2 | 4 | 4 | 8 | 2 | 1 | 2 | 1 | 1
SMG_Electrician_Worker | 3 | 11 | 11 | 8 | 5 | 6 | 6 | 4 | 2 | 0 | 1 | 1 | 1 | 2 | 2
SMG_Logistic_Engineer
SMG_Logistic_Technician
SMG_Logistic_Worker
SMG_Mechanic_Engineer
SMG_Mechanic_Technician
SMG_Mechanic_Worker
SMG_Scientist

## Slide 16
Thank you very much !

## Slide 17: Installation Ressources HEBT / SFRS Mechanicals
Chart: 
| Okt. 20 | Nov. 20 | Dez. 20 | Jan. 21 | Feb. 21 | Mrz. 21 | Apr. 21 | Mai. 21 | Jun. 21 | Jul. 21 | Aug. 21 | Sep. 21 | Okt.21. | Nov.21. | Dez. 21. | Jan. 22 | Feb. 22 | Mrz. 22 | Apr. 22 | Mai. 22 | Jun. 22 | Jul. 22 | Aug. 22 | Sep. 22 | Okt. 22 | Nov. 22 | Dez. 22 | Jan. 23 | Feb. 23 | Mrz. 23 | Apr. 23 | Mai. 23 | Jun. 23 | Jul. 23 | Aug. 23 | Sep. 23 | Okt. 23 | Nov. 23 | Dez. 23 | Jan. 24 | Feb. 24 | Mrz. 24 | Apr. 24 | Mai. 24 | Jun. 24 | Jul. 24 | Aug. 24 | Sep. 24 | Okt. 24 | Nov. 24 | Dez. 24
SMG_Alignment_Engineer
SMG_Alignment_Technician
SMG_Electrician_Engineer
SMG_Electrician_Technician
SMG_Electrician_Worker
SMG_Logistic_Engineer
SMG_Logistic_Technician
SMG_Logistic_Worker
SMG_Mechanic_Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0.1 | 0.1 | 0.3 | 0.3 | 0.3 | 0.3 | 1.1 | 2 | 1 | 1 | 0 | 0 | 0 | 2.2 | 6 | 6 | 9 | 7 | 5 | 3 | 1.65 | 1.65 | 1.65 | 1.65 | 1 | 1 | 5 | 5 | 10 | 10 | 9 | 8 | 8 | 5 | 4 | 5 | 5 | 0 | 0
SMG_Mechanic_Technician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 2 | 4 | 3 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 2 | 4 | 4 | 10 | 10 | 20 | 20 | 16 | 15 | 12 | 4 | 3 | 3 | 2 | 0 | 0
SMG_Mechanic_Worker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 6 | 7 | 3 | 0 | 0 | 0 | 14 | 17 | 8 | 8 | 6 | 7 | 13 | 18 | 18 | 13 | 13 | 7 | 8 | 21 | 4 | 0 | 3.6 | 4.4 | 12 | 12 | 19 | 19.2 | 18.2 | 21 | 20.2 | 16.2 | 11 | 10 | 9 | 2 | 2 | 0 | 0
SMG_Scientist

## Slide 18: Installation Ressources HEBT / SFRS Electricians
Chart: 
| Okt. 20 | Nov. 20 | Dez. 20 | Jan. 21 | Feb. 21 | Mrz. 21 | Apr. 21 | Mai. 21 | Jun. 21 | Jul. 21 | Aug. 21 | Sep. 21 | Okt.21. | Nov.21. | Dez. 21. | Jan. 22 | Feb. 22 | Mrz. 22 | Apr. 22 | Mai. 22 | Jun. 22 | Jul. 22 | Aug. 22 | Sep. 22 | Okt. 22 | Nov. 22 | Dez. 22 | Jan. 23 | Feb. 23 | Mrz. 23 | Apr. 23 | Mai. 23 | Jun. 23 | Jul. 23 | Aug. 23 | Sep. 23 | Okt. 23 | Nov. 23 | Dez. 23 | Jan. 24 | Feb. 24 | Mrz. 24 | Apr. 24 | Mai. 24 | Jun. 24 | Jul. 24 | Aug. 24 | Sep. 24 | Okt. 24 | Nov. 24 | Dez. 24
SMG_Alignment_Engineer
SMG_Alignment_Technician
SMG_Electrician_Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 1 | 1 | 3 | 8 | 5 | 4 | 4 | 6 | 18 | 19 | 12 | 11 | 7 | 6 | 12 | 9 | 7 | 6 | 6 | 10 | 5 | 5 | 5 | 5 | 3 | 5 | 5 | 1 | 24 | 3 | 2 | 0 | 0
SMG_Electrician_Technician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 7 | 3 | 5 | 4 | 4 | 12 | 8 | 5 | 6 | 6 | 7 | 9 | 7 | 6 | 9 | 10 | 11 | 7 | 8 | 7 | 7 | 6 | 8 | 2 | 1 | 2 | 1 | 1 | 0 | 0
SMG_Electrician_Worker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 3 | 11 | 12 | 13 | 9 | 3 | 4 | 4 | 13 | 11 | 9 | 8 | 6 | 3 | 0 | 0 | 0 | 6 | 10 | 9 | 8 | 5 | 3 | 4 | 1 | 3 | 2 | 0 | 2 | 2 | 0 | 0 | 0
SMG_Logistic_Engineer
SMG_Logistic_Technician
SMG_Logistic_Worker
SMG_Mechanic_Engineer
SMG_Mechanic_Technician
SMG_Mechanic_Worker
SMG_Scientist