## Slide 1
CR
Main Magnetic Elements
STATUS
Alexandr Starostenko
May 2020

## Slide 2: Common Status report
PSP | 2.5.2
WP | CR Magnets
WP-Leader | Alexandr Starostenko
Report period | May 2020
WP subprojects (4th level):
Legend:
S - Specification; CDR Conceptual Design Review; FDR Final Design Review; PR- Production FoS; FAT FoS Factory acceptance test) FoS; SAT FoS - Site Acceptance Test of FoS; SP – Series Production; FAT SP – Factory acceptance test of Series Production; DL –Delivery; SAT SP – Site Acceptance Test of Series Production; IN – Installation; CO – commissioning without beam
PSP` | Subproject | Responsibility | S | CDR | FDR | PR FoS | FAT FoS | SAT FoS | SP | FAT SP | DL | SAT SP | IN | CO | Activities in reporting period / Risks
2.5.2.1 | Dipole Magnets | A. Starostenko | x | x | x |  |  |  |  |  |  |  |  |  | Top and Bottom parts was manufactured. First two coils was manufactured. Yoke Side spacers is in production
2.5.2.2 | Quadrupole Magnets | A. Utkin D. Gurov | x | x |  |  |  |  |  |  |  |  |  |  | FDR WQ done FDR – SWQ, EWQ, NQ, NQM, NFQ documents is in preparation Stamps is in preparation for production
2.5.2.3 | Sextupole Magnets | A. Tsyganov | x | x |  |  |  |  |  |  |  |  |  |  | FDR is in preparation, Stamp is in production
2.5.2.4 | Octupole Correction Magnets | D. Gurov | x |  |  |  |  |  |  |  |  |  |  |  | CDR is in preparation
2.5.2.6 | Orbit Correction Magnets | A. Tsyganov | x | x | х | х |  |  |  |  |  |  |  |  | FoS is ready
Qualitative rating:
done
as planned
critical, but reachable
very critical, unreachable
not applicable
X

## Slide 3
CR dipole

## Slide 4
Poles lamination. Geometrical test

## Slide 5
Yoke side block. First block is create on the Stacking fixture

## Slide 6: Coils. First set of coils is ready

## Slide 7: Outer yoke. Top and bottom plates are ready

## Slide 8
CR
steerers

## Slide 9
CR steerers.
2 Vertical correctors practically ready!
Chart: Field in the median plate of corrector
Chart: X, mm
| -77.28 | -67.53071100982261 | -58.092573740607321 | -48.595583087430946 | -39.113649521876688 | -29.598548926281843 | -20.064882887771489 | -10.606426294307127 | -1.0398483511743564 | 8.3816889655986557 | 17.889099734417911 | 27.408645597438294 | 36.865568413430083 | 46.364930113309583 | 55.891824815309917 | 65.375734524307745 | 74.820091825862846
+100mm_4.5A | -0.46254 | -0.23841 | -0.28162 | -0.21946 | -0.084556 | -0.15547 | -0.048944 | 0.069667 | 0.0028689 | 0.0077431 | 0.046052 | -0.028722 | 0.044498 | -0.069782 | 0.04304 | -0.23773 | -0.19346
0mm_4.5A | -0.23416 | -0.08388 | -0.12296 | -0.11114 | -0.10623 | -0.12995 | -0.032631 | 0.045266 | 0 | 0.008723 | 0.050617 | 0.064066 | 0.078236 | 0.03547 | 0.082977 | 0.00032058 | 0.088035
-100mm_4.5A | -0.026759 | 0.17907 | 0.14861 | 0.19376 | 0.28924 | 0.28247 | 0.34944 | 0.43297 | 0.38124 | 0.38854 | 0.41921 | 0.35306 | 0.40188 | 0.31368 | 0.35985 | 0.17755 | 0.17027
+100mm_9A | -0.45394 | -0.30252 | -0.2975 | -0.23756 | -0.14422 | -0.16087 | -0.086186 | -0.011358 | -0.038522 | -0.033483 | -0.0087336 | -0.048629 | -0.013919 | -0.081718 | -0.039249 | -0.18553 | -0.19066
0mm_9A | -0.15371 | -0.063277 | -0.097794 | -0.087691 | -0.073953 | -0.097523 | -0.030969 | 0.01505 | 0 | 0.015593 | 0.045301 | 0.063664 | 0.094103 | 0.10477 | 0.11716 | 0.12466 | 0.15034
-100mm_9A | -0.011544 | 0.12221 | 0.131 | 0.17867 | 0.25239 | 0.24961 | 0.31233 | 0.36945 | 0.35063 | 0.36036 | 0.37562 | 0.33845 | 0.35922 | 0.30483 | 0.31908 | 0.21566 | 0.19195

## Slide 10
Thanks!