## Slide 1: FAIR HEBT vacuum Batch 2,3 & 4
A. Krasnov
4th BINP-FAIR Collaboration Coordination Workshop
BINP

## Slide 2: General information
Name | Signed | End | Cost M€ | Status
AFAA2 HEBT Batch 2-3 Vacuum chambers | 05.2019 | 07.2021 | 1.71 | There is delay but not critical. CDR – 50%. 2D drawings – 30%. 40% of materials are under ordering. First FAT is expected in July 2020.
AFAA4 HEBT Batch 4 Vacuum chambers | 11.2019 | 12.2022 | 4.18 | 3D model of most complex chamber (x-cross) is accepted. 2D drawings of the x-cross chamber, standard pumping ports, drift chambers and supports are under consideration at BINP workshop

## Slide 3: HEBT Batch 2-3
*Several procedures like cleaning, vacuum tests are under minor corrections to be done during this week
** Open question regarding drawings versions
*** Mechanical analysis of the branching chambers WP10 is complex. Is it possible to do sub-separation of WP10 on sets of simple chambers and complex branching chambers?
 | Q-ty | Types | Description | CDR | FDR* | FAT | SAT Ab | May 2020, current work
WP1 | 6 | 3 | dip10 branch trapec 3.8m | 10/2019 | 01/2020 | 08/2020 | 12/2020 | 
WP2 | 5 | 1 | dip13 (ch. 55 Batch 1) | 05/2019 | 07/2019 | 12/2019 | 04/2020 | material ordering, 3 chambers are produced
WP3** | 7 | 5 | dip15-17 2 - 2.5m | 05/2019 | 07/2019 | 12/2019 | 04/2020 | material ordering
WP6 | 4 | 1 | dip19 120x80 3,7m | 07/2019 | 09/2019 | 04/2020 | 08/2020 | material ordering
WP7 | 91 | 13 | q1, q2, d120 some with bellow | 09/2019 | 01/2020 | 08/2020 | 11/2020 | design, material ordering
WP8 | 4 | 1 | q10, d160, 2,8m | 06/2019 | 07/2019 | 12/2019 | 04/2020 | material ordering
WP9 | 69 | 19 | q11, d100, oval 140x70, some with bellow | 10/2019 | 02/2020 | 12/2020 | 03/2021 | design
WP10*** | 17 | 8 | q12, some branch, oval, up to 2.1m, some with bellows | 09/2019 | 12/2019 | 12/2020 | 03/2021 | design, material ordering
WP11 | 63 | 35 | s100, s18, d150, some with bellow | 10/2019 | 12/2019 | 06/2020 | 07/2020 | design
WP13 | 4 | 3 | s13, d400 | 11/2019 | 02/2020 | 10/2020 | 02/2021 | 
WP14 | 2 | 2 | d4, 1 branch, 1 bend, 100x67 | 03/2020 | 06/2020 | 12/2020 | 04/2021 | 
 | 272 | 91 |  | All dates are contractual dates |  | In process |  | 
 |  |  |  | done | close to be done | in process | delay 6 - 8 months | 
Questions for discussions:

## Slide 4: Batch 2-3
Branching chamber inside Quad12
Preliminary: support is strong enough.
If not, we will apply double support or additional support applied at pump
200 kg

## Slide 5: Batch 4
3D model of most complex chamber “X-cross”
is accepted
Documents for CDR are under preparation
2D drawings of the x-cross chamber, standard pumping ports, drift chambers and supports are under consideration at BINP workshop, prototype of pumping port is ordered at BINP workshop
Questions to the workshop:
Released specification and DMU 3D models are still absent
Final requirements for relative magnetic permeability? It seems nobody really did estimation the influence on beam dynamic

## Slide 6: Batch 4
Are the placement and construction of supports checked from assembly convenience point of view?
If not, FAIR/GSI has a time to check most critical points and provide suggestions how to improve

## Slide 7: Session X
1. Production and delivery will be maximally synchronized with magnets (after receiving row material)
2. It is better to order row materials with big batches and the purchasing has to be done ASAP (before most of FDR completion). It looks critical from point of view of present BINP finance capability.
3. Is it possible to do sub-separation of WP10 on sets of simple chambers and complex branching chambers? Or there is no reason?
4. Are the placement and construction of supports checked from assembly convenience point of view?
If not, FAIR/GSI has a time to check most critical points and provide suggestions how to improve. BINP just pays attention for that. All suggestions and sketches have to come from FAIR/GSI.

## Slide 8: Batch 4
Are the placement and construction of supports checked from assembly convenience point of view?
If not, FAIR/GSI has a time to check most critical points and provide suggestions how to improve

## Slide 9: Thank you for your attention