## Slide 1
4th BINP-FAIR Collaboration Coordination Workshop
Status production PANDA solenoid
E.Pyata, BINP, Novosibirsk

## Slide 2
Development of the PANDA solenoid magnet
Name of item | Status of work
Yoke and frame | Design is ready, production
Cryostat of solenoid | Design is ready, technological development, Call for tender
Cold mass | Design is ready, technological development, Call for tender
Conductor purchasing | Development work, Call for tender
Control Dewar box | Preliminary design September 2020
PANDA solenoid power cabling | Design is ready, production
Power supply and energy extraction system | Detail design is ready, production
Magnet safety system | in process

## Slide 3
PANDA solenoid magnet, BINP responsibility
Power supply and energy extraction system
Cable channel
Control Dewar box
Solenoid and yoke
Frame of Yoke

## Slide 4: 3D model of the Magnet and Control Dewar.
Control Dewar box
Cryostat and Coil

## Slide 5
The main milestones of the yoke production
Name of milestone |  | Date 2017/10 | Comments
Production of the all barrel octants |  | 04/2020 | Ready
Production of the frame and beams |  | 04/2020 | Ready
Production of the doors | Upstream | 05/2020 | Ready
 | Downstream | 06/2020 | June 2020
Control assembling at SET |  | 07– 09/2020 | 
Finalization of the parts |  | 08 - 10/2020 | 
Assembling of the Yoke at BINP |  | ? | 

## Slide 6
The main milestones of the Cryostat production
Name of milestone |  | Date 2017/10
FDR of the Cryostat |  | 08/02/2019
FDR of the Cold Mass |  | 17/04/2019
Status production |  | 
Cryostat and stands for assembling solenoid and magnet | Design is ready, technological development, Call for tender | 
Cold Mass | Design is ready, technological development, Call for tender | 
First Prototype of the Coil | 11/2019 | 
Second Prototype of the Coil | 03/2020 | 
Third Prototype of the Coil | 08/2020 | 
Tooling for winding Coil (and Prototype) | 11/2019 | 
Tooling for impregnation of Coil (and Prototype)/modified | 11.2019/03.2020 | 
Tooling for winding and impregnation of PANDA Coil | Design is ready, technological development, Call for tender | 
Prepress prototype coil into cold mass | 08/2020 | 

## Slide 7
Status of the PANDA conductor development/ procurement

## Slide 8
Main risks
Longitudinal section of the cryostat with cold mass.
Cold mass cross-section.
Cross-section of the conductor.
Conductor mechanical and electrical parameters.
Thickness (after cold work) at 300 K | mm | 7.93 | ± 0.03
Width (after cold work) at 300 K | mm | 10.95 | ± 0.03
Critical current (at 4.2 K, 5 T) | A | > 14690 | 
Critical current (at 4.5 K, 3 T) | A | > 16750 | 
Overall Al/Cu/sc ratio |  | 10.5/1.0/1.0 | 
Aluminum RRR (at 4.2 K, 0 T) |  | > 1000 | 
Al 0.2% yield strength at 300 K | MPa | > 30 | 
Purchasing super conductive conductor - lack of a manufacturers
Rutherford cable, 8 strands, extruded in Al matrix

## Slide 9
Development works with a prototype Rutherford cable (Cu or NbTi) to co-extrusion/ conklad in a pure Al 995 and Aluminum A95
Status of the PANDA conductor development/ procurement
No. | Process | Plan | Comments
1 | Conklad with a prototype NbTi PANDA cable and A995/998 wire 9,5 mm. | 02/2020 | ? Depend from production A995
2 | Tests of the prototype NbTi PANDA cable and A995/998 matrix after Conklad | 02-03/2020 | After step 1
3 | Co-extrusion/ Conklad in SARKO with Cu Rutherford cable 1000m and A95 wire 9,5 mm. | 07-08/2020 | Discussing details of contract with SARKO
4 | Co-extrusion/ Conklad in SARKO with Cu Rutherford cable 1000m and A995/998 wire 9,5 mm. | ? | After step 1
5 | Cold work to result the overall geometrical conductor dimensions | 09-10/ 2020 | After steps 3 and 4; purchasing dies

## Slide 10
Development works with a prototype Rutherford cable (Cu or NbTi) to co-extrusion/ conklad in a pure Al 995 and Aluminum A95
Oven for preheating a Rutherford cable.
Temperature - 200 ÷ 450°C;
Shielding gas – N2
Status of the PANDA conductor development/ procurement

## Slide 11
Status of the PANDA yoke production

## Slide 12: 3D model of the Yoke and Frame.
Control assembling 12/2019
Frame
Yoke

## Slide 13: Production of the parts of the Yoke
Acceptance tests of the W5 and W7 modules in plant site
Modules W5 and W7 after final machining

## Slide 14
Production of the parts of the Yoke

## Slide 15: Production of the parts of the Yoke

## Slide 16
Status of the PANDA coils production

## Slide 17: The Prototype of the Coil (3pcs.)
OD = 1m,
h=180 mm
Conductor:Al
10,85 мм x 7.93 мм,
6 layers
16 turns
.
Design is ready, 2 prototype produced

## Slide 18: The Prototype of the Coil (3pcs.)
Preparation prestress procedure of coil
to an aluminum shell
For prototype heater:
Length - 17m;
Power - 3,5 kW;
Cross section - 24 x 3 mm;
Quantity - 1 pc.
For PANDA coil
Length - 36m;
Power - 3,0 kW;
Cross section - 24 x 3 mm;
Quantity - 8-9 pc.
.
Design is ready, preparation heat system

## Slide 19
Production of the coil prototype

## Slide 20
Development works with a prototype Rutherford conductor.
Material is Aluminum A95
Second prototype
Electrical tests;
Procedure heating Al shell with control uniformity distribution of temperature, temperature rate, shell expansion measurement;
Assembling coil and Al shell with prestress;
Mechanical test coil assembling;
Destroy tests;
Checking quality of an epoxy penetration, mechanical tests;
Analysis of the manufacturing quality of the second prototype;
Preparation production of the third prototype
Status of the PANDA coil development/ production

## Slide 21: Drawing of the Devices for winding coil (scheme).
Design is ready, production until 2020

## Slide 22
Status of the PANDA cryostat and cold mass production

## Slide 23
Status of the PANDA cryostat, cold mass and stands production
Item | Plan | Status
Design |  | Ready
Specification for production |  | Ready
Call for tender |  | In process
Procurement raw materials | 08-09/ 2020 | In process
Ti bars for suspend system | 10/ 2019 | Ready
Procurement interconnector Al/Stainless steel | 12/ 2020 | Negotiation with producers
Procurement Al pipes of cold mass | 2021 | In plan
Al pipes for thermoshields |  | In BINP

## Slide 24
LHe and GHe sealing

## Slide 26
Vacuum tests of the MO (Matsumot - Ohtsuka) type flange
Connection MO flange 1 | Date | Quantity cycle 78K – 300K without leakage | Test Leak rate, mbar x l/s | Pressure tests, bar | Time tests 78K, min | Leakage, mbar x l/s
Gasket 1 | 20/04 2020 - | 1 - 17 | ≤5 x 10E-10 | 25 | 30-40 | no
 | 25/05/2020 | 18 | 1,6 x 10E-11 | 10 | 1 | 8 x 10E-9
Gasket 2 | 27/05 – present time | 3 | ≤5 x 10E-10 | 25 | 30-40 | no
Gasket 3 |  |  |  |  |  | 
Connection MO flange 2..3 |  |  |  |  |  | 
Connection cryogenic process pipes in place assembly / disassembly transfer line between He liquefier and Control Dewar to move PANDA detector from beam position to assembling area.

## Slide 27
Flexible bus bar between cable way and current leads

## Slide 28
Preparation tests in BINP

## Slide 29
PANDA magnet, bld. 13. Area for cryogenic and coils tests and measurements of a magnetic field

## Slide 30
Thank you for your attention