## Slide 1
PANDA meeting
Status production PANDA solenoid
E.Pyata, BINP, Novosibirsk

## Slide 2
The main milestones of production of the PANDA solenoid magnet
The scope of delivery includes:
Magnetic and engineering design of the magnet including tools and support;
Production and delivery of the magnet (consisting of yoke, cold mass and cryostat, alignment components, proximity cryogenics, support frame and platform beams) and all tools;
Power converter and quench protection and instrumentation.
Item | Date
Start contract | 03/2017
Control assembling of the Yoke of solenoid at the BINP site | 09/2020
Magnetic tests of the PANDA solenoid including safety system and electrical components at BINP (additional contract) | 12/2021 - 05/2022
Assembling and tests at the FAIR site | 
Assembling of the magnet at Darmstadt | 06/2022
Acceptant tests at FAIR | 08/2022
Installation of the PANDA solenoid magnet at worked position and final acceptance tests | 01-05/2023

## Slide 3
PANDA solenoid magnet, BINP responsibility
Power supply and energy extraction system
Cable channel
Control Dewar box
Solenoid and yoke
Frame of Yoke

## Slide 4: 3D model of the Magnet and Control Dewar.
Control Dewar box
Cryostat and Coil

## Slide 5
Development of the PANDA solenoid magnet
Name of item | Status of work
Yoke and frame | Final machining 5 July 2020 Start control assembling July 2020
Cryostat of solenoid & Cold mass | Design is ready, technological development, purchasing raw materials Call for tender July 2020
Conductor purchasing | Development work, Call for tender July 2020
Control Dewar box | Preliminary design September 2020
PANDA solenoid power cabling | Design is ready, production
Power supply and energy extraction system | Detail design is ready, purchasing power convertors & components Production
Magnet safety system | in process

## Slide 6
Status of the PANDA cryostat and cold mass production

## Slide 7
The main milestones of the Cryostat production
Name of milestone |  | Date 2017/10
FDR of the Cryostat |  | 08/02/2019
FDR of the Cold Mass |  | 17/04/2019
Status production |  | 
Cryostat stands for assembling solenoid and magnet Cold Mass | Call for tender July 2020 | 
 | Purchasing raw material 09/2020 | 
 | Manufacturing Technical documentation 11/2021 | 
 | Contract: delivery to BINP 09/2021 | 

## Slide 8
Status of the PANDA yoke production

## Slide 9: 3D model of the Yoke and Frame.
Control assembling 12/2019
Frame
Yoke

## Slide 10
The main milestones of the yoke production
Name of milestone |  | Date 2017/10 | Comments
Production of the all barrel octants |  | 04/2020 | Ready
Production of the frame and beams |  | 04/2020 | Ready
Production of the doors | Upstream | 05/2020 | Ready
 | Downstream | 06/2020 | June 2020
Control assembling at SET |  | 07– 09/2020 | 
Finalization of the parts |  | 08 - 10/2020 | 
Assembling of the Yoke at BINP |  | ? | 

## Slide 11: Production of the parts of the Yoke
Acceptance tests of the W5 and W7 modules in plant site
Modules W5 and W7 after final machining

## Slide 12
Production of the parts of the Yoke

## Slide 13: Production of the parts of the Yoke

## Slide 14: Production of the parts of the Yoke
No. | Parameter | Measured beams W5 | Reference
1 | Dimension, 4070-1 mm | 4069,5/4069,5 | 
2 | Dimension, 805 mm | 801-803 | 
3 | Dimension, 1900 -5 mm | 1898/1899 | 
4 | Dimension, 1234 -1 mm | 1236/ 1234 | Not acceptable
6 | Dimension, 806 mm |  | 
7 | Angle 22°30ʹ-9ʹ | 22°31ʹ | Not acceptable
8 | Angle 22°30ʹ-9ʹ | 22°34ʹ | Not acceptable
9 |  | OK | By laser trecker
10 |  | OK | By laser trecker
12 |  |  | 
13 |  | OK | By laser trecker
14 | Dimension, 1585 ±0.5 mm | 1582 | Not acceptable Tests 20200429
 |  | 1584.45 | By laser trecker Tests 20200610
15 | Dimension, 1730 mm | OK | 
16 | Dimension, 1730 mm | OK | 
17 | Dimension, 1645 mm | OK | 
18 | Dimension, 1645 mm | OK | 
20 | Dimension, 1130 mm | OK | 
21 | Dimension, 1130 mm | OK | 
22 | Dimension, 565 mm | OK | 
23 | Dimension, 565 mm | OK | 
24 | Dimension, 1000 mm | 1003/1004 | 
25 | Dimension, 1200 mm | 1188,4/1187,4 | Not acceptable Tests 20200429
 |  | 1200.6 | Tests 20200603
26 | Dimension, 1020 mm | 1015 | Not acceptable Tests 20200429
 |  | 1021 | Tests 20200603
27 | Dimension, 1020 mm | 1004 | Not acceptable Tests 20200429
 |  | 1020.5 | Tests 20200603
28 | Dimension, Ø 350+1 mm | 350,76 | 
29 | Dimension, Ø 500 mm | 501 | 
30 | Dimension, 90 mm | 89 | 
31 | Dimension, 190 mm | 194 | Not acceptable
 |  | 190.4 | Tests 20200603
32 | Dimension, 30 mm, go | OK | 
33 | Welding, visual control | OK | 
34 | Dimension, 145 mm | OK | 
35 | Dimension, 145 mm | OK | 
36 | Dimension, 145 mm | OK | 
37 | Dimension, 145 mm | OK | 
38 | Dimension, 1360 mm | OK | 
39 | Dimension, 680 mm | 681 | 
 | Dimension, 680 mm | 681 | 
 | Dimension, Ø 440 mm | 440 | 
No objection | Objection | Left with defects
 | 22°31ʹ (7) | Yes
 | 22°34ʹ(8) | Yes
 | 1236/ 1234 (4) | Yes
 | 1582 (14) | 
 | 1188,4/1187,4 (25) | 
 | 1004/1060 (26) | 
 | 1004/1030 (27) | 
 | 194 (31) | 
No objection | Objection | Left with defects | Comments
1584.45 (14) |  |  | Measurement 2020/06/09
1200(25) |  |  | Measurement 2020/06/06
1021(26) |  |  | Measurement 2020/06/06
1020.5 (27) |  |  | Measurement 2020/06/06
190.4 (31) |  |  | Measurement 2020/06/06
No objection | Objection | Left with defects
x |  | 
Table 8. Main dimensions. Drawings FPD SSM 02010300AS_E.
*General tolerance for linear dimensions if not set the value of a tolerance for dimension: H14, h14, ±IT14/2 (DIN ISO 2768-m)
Test results: Repair: Results of repair:
3D measurements
Test results: Repair: Results of repair:
Conclusion: Upper module is produced according to the specification and drawings FPD SSM 02010300AS_E and is allowed to assembly the yoke.

## Slide 15
Status of the PANDA conductor development/ procurement

## Slide 16
Main risks. Conductor.
Status of the PANDA conductor development/ procurement
VNIINM Bochvar
VNIIKP
Saransk cable optic (SarKO)
Rutherford cable co-extrusion/ conklad in a pure Al
Production1000m Cu Rutherford cable for tests in SARKO - 03-04/ 2020 (in BINP)
Tests in SARKO, 1000m Cu Rutherford cable - 09-12/ 2020
Preparation contracts for PANDA NbTi strands production, VNIINM - 03/ 2020
Production strands VNIINM for central coil - 02/2021
Production strands VNIINM for up/downstream coils - 09/2021
PANDA Rutherford cables production, VNIIKP - 03-10/ 2021
Production PANDA conductor with SARKO - 03 - 11/ 2021
Purchasing superconductive conductor - lack of a manufacturers

## Slide 17
Main risks
Longitudinal section of the cryostat with cold mass.
Cold mass cross-section.
Cross-section of the conductor.
Conductor mechanical and electrical parameters.
Thickness (after cold work) at 300 K | mm | 7.93 | ± 0.03
Width (after cold work) at 300 K | mm | 10.95 | ± 0.03
Critical current (at 4.2 K, 5 T) | A | > 14690 | 
Critical current (at 4.5 K, 3 T) | A | > 16750 | 
Overall Al/Cu/sc ratio |  | 10.5/1.0/1.0 | 
Aluminum RRR (at 4.2 K, 0 T) |  | > 1000 | 
Al 0.2% yield strength at 300 K | MPa | > 30 | 
Purchasing super conductive conductor - lack of a manufacturers
Rutherford cable, 8 strands, extruded in Al matrix

## Slide 18
Development works with a prototype Rutherford cable (Cu or NbTi) to co-extrusion/ conklad in a pure Al 995 and Aluminum A95
Status of the PANDA conductor development/ procurement
No. | Process | Plan | Comments
1 | Conklad with a prototype NbTi PANDA cable and A995/998 wire 9,5 mm. | 02/2020 | ? Depend from production A995
2 | Tests of the prototype NbTi PANDA cable and A995/998 matrix after Conklad | 02-03/2020 | After step 1
3 | Co-extrusion/ Conklad in SARKO with Cu Rutherford cable 1000m and A95 wire 9,5 mm. | 07-08/2020 | Discussing details of contract with SARKO
4 | Co-extrusion/ Conklad in SARKO with Cu Rutherford cable 1000m and A995/998 wire 9,5 mm. | ? | After step 1
5 | Cold work to result the overall geometrical conductor dimensions | 09-10/ 2020 | After steps 3 and 4; purchasing dies

## Slide 19
Development works with a prototype Rutherford cable (Cu or NbTi) to co-extrusion/ conklad in a pure Al 995 and Aluminum A95
Oven for preheating a Rutherford cable.
Temperature - 200 ÷ 450°C;
Shielding gas – N2
Status of the PANDA conductor development/ procurement

## Slide 20
Status of the PANDA coils production

## Slide 21
The main milestones of the coils production
Status production | 
Cryostat and stands for assembling solenoid and magnet | Design is ready, technological development, Call for tender
Cold Mass | Design is ready, technological development, Call for tender
First Prototype of the Coil | 11/2019
Second Prototype of the Coil | 03/2020
Third Prototype of the Coil | 08/2020
Tooling for winding Coil (and Prototype) | 11/2019
Tooling for impregnation of Coil (and Prototype)/modified | 11.2019/03.2020
Prepress prototype coil into cold mass | 08/2020
Tooling for winding and impregnation of PANDA Coil | Design is ready, technological development, Call for tender

## Slide 22: The Prototype of the Coil (3pcs.)
OD = 1m,
h=180 mm
Conductor:Al
10,85 мм x 7.93 мм,
6 layers
16 turns
.
Design is ready, 2 prototype produced

## Slide 23: The Prototype of the Coil (3pcs.)
Preparation prestress procedure of coil
to an aluminum shell
For prototype heater:
Length - 17m;
Power - 3,5 kW;
Cross section - 24 x 3 mm;
Quantity - 1 pc.
For PANDA coil
Length - 36m;
Power - 3,0 kW;
Cross section - 24 x 3 mm;
Quantity - 8-9 pc.
.
Design is ready, preparation heat system

## Slide 24
Production of the coil prototype

## Slide 25
Development works with a prototype Rutherford conductor.
Material is Aluminum A95
Second prototype
Electrical tests;
Procedure heating Al shell with control uniformity distribution of temperature, temperature rate, shell expansion measurement;
Assembling coil and Al shell with prestress;
Mechanical test coil assembling;
Destroy tests;
Checking quality of an epoxy penetration, mechanical tests;
Analysis of the manufacturing quality of the second prototype;
Preparation production of the third prototype
Status of the PANDA coil development/ production

## Slide 26: Drawing of the Devices for winding coil (scheme).
Design is ready, production until 2020

## Slide 27
Status of the PANDA cryostat and cold mass production

## Slide 28
Status of the PANDA cryostat, cold mass and stands production
Item | Plan | Status
Design |  | Ready
Specification for production |  | Ready
Call for tender |  | In process
Procurement raw materials | 08-09/ 2020 | In process
Ti bars for suspend system | 10/ 2019 | In BINP
Procurement interconnector Al/Stainless steel | 12/ 2020 | Negotiation with producers
Procurement Al pipes of cold mass | 2021 | In plan
Al pipes for thermoshields |  | In BINP

## Slide 29
LHe and GHe sealing

## Slide 31
Vacuum tests of the MO (Matsumot - Ohtsuka) type flange
Connection MO flange 1 | Date | Quantity cycle 78K – 300K without leakage | Test Leak rate, mbar x l/s | Pressure tests, bar | Time tests 78K, min | Leakage, mbar x l/s
Gasket 1 | 20/04 2020 - | 1 - 17 | ≤5 x 10E-10 | 25 | 30-40 | no
 | 25/05/2020 | 18 | 1,6 x 10E-11 | 10 | 1 | 8 x 10E-9
Gasket 2 | 27/05 – 15/06/2020 | 20 | ≤5 x 10E-11 | 25 | 30-40 | no
Gasket 3 | 15/06/2020 – present time | 15 | ≤5 x 10E-11 | 25 | 30-40 | no
Connection MO flange 2..3 |  |  |  |  |  | 
Connection cryogenic process pipes in place assembly / disassembly transfer line between He liquefier and Control Dewar to move PANDA detector from beam position to assembling area.

## Slide 32
Flexible bus bar between cable way and current leads

## Slide 33
Power supply and energy extraction system

## Slide 34
Power Supply (Current Source – TDK-Lambda, Genesys+, 10V, 1500A)
New power supply

## Slide 35
Dump resistor sections assembling

## Slide 36
Preparation tests in BINP

## Slide 37
PANDA magnet, bld. 13. Area for cryogenic and coils tests and measurements of a magnetic field

## Slide 38
Thank you for your attention