## Slide 1: cw-LINAC 14.07.2020
      CH2 @ IAP Frankfurt (start of test promised after eastern!) IAP still locked down, postponed!
      CH0-test @HI-Mainz postponed for September 2020 due to Lockdown delays, 1.08.20: Start of “eingeschränkter Regelbetrieb”
      2x sc-Rebuncher in production
      CH0&CH1: HPR for CH1 ordered, waiting for offer of HPR for CH0
      CH3-5 specification finalized; waiting for budgetary offer
      Commissioning of LHe-transfer line and its controls in progress - recalibaration of temperature sensors!
      Connection of lHe-supply system to the future cw-Linac + “Brandschott” finished
      Coupler tests already started
      Preparation for beam line set up@SH1 – postponed due to delay of lHe-transfer line SAT!
      Preparation of RF-supply lines Rf-supply room => test bunker for CH0, CH1, CH2, sc-Reb., UCW-Reb.
      Internal review on cooling concept for APF-IH-DTL
      RFQ-prototype (iap) Rf-test in preparation – delivered; preparation for high power Rf-test at test bunker