## Slide 1: cw-LINAC 18.08.2020
      CH2 @ IAP Frankfurt (start of test promised after eastern!) IAP still locked down, postponed!
      CH0-test @HI-Mainz postponed for September 2020 => test in preparation. Test scheduled to 01.09. - 20.09
      CH0&CH1: HPR for CH1 ordered, offer for CH0 now available
      CH3-5 specification finalized; budgetary offer is available; waiting for budget (GFEV is done)
      recalibration of temperature sensors for LHe-transfer is done! Commissioning is ongoing
      Cleaning of SH1 (HLI-hall) is done!
      Beam line set up@SH4 are ongoing. First part before cryostat is assembled!
      RFQ-prototype: Preparation for high power Rf-test at test bunker; rf-conditioning is ongoing