## Slide 1: Operations – 18.08.2020
Shutdown
  essentially ongoing as planned
  Risks:
    delay of FSB Tunnel 101  subsidence of ground  delayed survey and alignment of SIS18  start of beam time 2021 is at risk more information after meeting (invitation of T. Miertsch)
    Water ingress over HKR ceiling  1 evtl. 2 printers destroyed  origin unclear  water in false floor could damage HKR technics G. Stephan is informed, waiting for response
    Beryllium-contamination in “Leichtbauhalle”  No access to spare parts by VAC, TRI, ...  could cause delays in shutdown work (esp. IPM), if not solved in reasonable time  outlook: company will start working in Sept.
    irritating and corrosive liquid found during sealing work, caused a closure of the Kicker-Room for work  delays in sealing and shutdown work
2021 general schedule
  very preliminary schedule approved by management
  details are planned to be discussed after GPAC
  Next steps:
    Meeting with operators (incl. candidates from VAC + IKP) scheduled on Wednesday to clarify availability during first half of 2021
    Meeting with Machine Coordinators and Heads of technical departments on details (commissioning time and order, technical availabilities, intermediate shutdown, beam studies, availability of on-call, ...)