## Slide 1: cw-LINAC, 01.09.2020
      CH2 @ IAP Frankfurt (start of test promised after eastern!)
      IAP still locked down, postponed!
      CH0-test @HI-Mainz postponed for September 2020 => CH0 ready for cool down. Test scheduled for 07.09. - 20.09
      Advanced demonstrator and CM2/delivery status:
        superconducting solenoids:Q4/2020
        cryostat 1 (Q1/2021) , cryostat2 (2021)
        superconducting buncher1 (2021), buncher2 (2022)
        rf-amplifiers (advanced demonstrator) Q1/2021, rf- amplifiers (CM2) to be ordered
        20 rf-windows for high power couplers to be purchased
      CH3-5 + CH6-8 specification finalized; budgetary offer is available; waiting for budget (GFEV is done waiting for confirmation)
      recalibration of temperature sensors for LHe-transfer is done! Commissioning is ongoing – further tests after Sep. 20th.
      Beam line set up@SH4 are ongoing. First part before cryostat is assembled! – Equipment commissioning is the next step…
      4rod-RFQ-prototype (cw): Preparation for high power Rf-test at test bunker; rf-conditioning is still ongoing (10 kW, 30% duty factor)