## Slide 1: Accelerator Operations – 01.09.2020
Shutdown
  essentially ongoing as planned
  Risks:
    substantial delay of FSB Tunnel 101  ground settlement  delayed survey and alignment  start of beam time 2021 in Feb. is at risk
      more information after meeting (invitation of T. Miertsch this Thursday)
      shutdown schedule is tight in terms of alignment, Nov. 30 Survey must start to be able to finish alignment of critical areas until Jan. 29th
      building settlement will be observed by Heinen&Fischer – measurements can be started, when radiation safety wall is installed / settlement of 1-3 cm expected / discussion ongoing
      it is not yet clear whether the earth has to be put back on tunnel 101 before beam time or not. if not – no big risk for beam time expected, otherwise additional settlement will continue over beam time
      meeting with FSB on Sept 23th for detailed discussion
    Water ingress over HKR ceiling
      Mr. Reckziegel responded and takes care on the issue, a leakage in HKR-roof was identified
      a preliminary “drainage” has been installed in HKR
      Last rainfall caused no water ingress anymore
      Complete renovation of the roof sealing is planned for autumn this year.
    irritating and corrosive liquid found during sealing work, caused a closure of the Kicker-Room for work  delays in sealing and shutdown work
      A. Schumann provided a schedule for cleaning of the transformers and the switching cabinet in front of the kicker room until 31.08. to not to interfere with H=2-Cavity tests
      no new information
    TVS no progress since July  working UNILAC access system at risk
      ACO and BEA are waiting for a risk analysis and the strategy document by T. Radon
      Meeting with T. Radon after Machine Meeting
UI development for beam instrumentation applications
  facing the reality, the decision was taken between BEA and ACO, that BEA is now officially responsible for all instrumentation related user applications (RB support can still not be ensured)
  development process has to be synchronized via. ACC-ACO-Steering meeting
2021/22 general schedule
  1 operator declared absence in Jan. – Apr. due to health reasons.  reactivation of retired operator must be discussed
  until now: no request for dedicated beam-time for FAIR development
  Cryring stand-alone operation block will be discussed tomorrow
  last Dry-Run before beam time will start on Jan 11th