## Slide 1: cw-LINAC, 08.09.2020
      CH2 @ IAP Frankfurt (start of test promised after eastern!) – IAP-Rf-bunker still not available!
      CH0-test @HI-Mainz postponed for September 2020 => CH0 cool down already started. Test scheduled for 07.09. - 20.09
      Advanced demonstrator and CM2/delivery status:
        superconducting solenoids:Q4/2020
        cryostat 1 (Q1/2021) , cryostat2 (2021)
        superconducting buncher1 (2021), buncher2 (2022)
        rf-amplifiers (advanced demonstrator) Q1/2021, rf- amplifiers (CM2) to be ordered
        20 rf-windows for high power couplers to be purchased, when budget 2020 and 2021 (prelim.) is available
      CH3-5 + CH6-8 specification finalized; budgetary offer is available; waiting for budget (GFEV is done; waiting for confirmation)
      recalibration of temperature sensors for LHe-transfer is done! Commissioning is ongoing – further tests after Sep. 20th.
      Beam line set up@SH4 are ongoing. First part before cryostat is assembled! – Equipment commissioning is the next step…
      4rod-RFQ-prototype (cw) Rf-test should be completed by the middle of this week
      cw-APF-IH-DTL beam dynamics design and Rf- and mechanical layout makes significant progress
cw-APF-IH1-tank