## Info
Steps for the monthly Status Report.
Step 1 | Update the “Actual status Controls” sheet. | To be filled in free text form.
Step 2 | Update the fields in the “Actual status Controls Equipment” sheet. | Update the schedule and dashboard status 1; 2; 3 (see Legend). | Legend
Step 3 | Send the filled Excel file back to FAIR contact person. | Dr. Ralph Bär; r.baer@gsi.de | -1 | not necessary
|  | * Report has to be updated at least once per month. | 0 | not stated
|  |  | 1 | planned
|  |  | 2 | in process
|  |  | 3 | ready

## Aktual Status Controls
Monthly report |  |  | Controls
Report period |  |  | June 2020 |  | Date: | 2020-06-05
Dr. Ralph Bär; r.baer@gsi.de
Company: FAIR GmbH Planckstraße, 1 64291 Darmstadt Contact person: Dr. Ralph Bär; r.baer@gsi.de |  |  |  | Provider: GSI Helmholtzzentrum für Schwerionenforschung GmbH Planckstraße, 1 64291 Darmstadt Contact person: Dr. Ralph Bär; r.baer@gsi.de
1. Completed tasks for last month
1 |  | First Version
2
3
4
5
6
7
8
9
10
11
12
13
14
2. Planned task for next month
1 |  | Text…
2
3
4
5
6
7
8
9
10
11
12
13

## Actual Status Controls Equipm.
[5 empty] | 43987 |  |  |  | 153 | 133 | 117 | 91 | 63 | 47 | 23 | 29 | 88 | 87 | 80 | 76 | 56 | 19 | 12 | 15 | 17 | 42
Controls | [5 empty] | Legend |  |  |  | must be updated by FAIR/GSI team
[6 empty] | -1 | not necessary |  |  | must be updated by BNG team
Contract | GSI IKC 3 |  |  |  |  | 0 | not stated
PSP: | 2.14.10.1 |  |  |  |  | 1 | planned
[6 empty] | 2 | in process |  | Design |  | Hardware & Electronics | [5 empty] | Software | [7 empty] | Tests
In Abstimmung mit PLM werden Controls CID's in FNT-Command verwaltet | [5 empty] | 3 | ready |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 17
[9 empty] | M3 Extern | M3 (CDR) | M6? | M8? |  |  | M9? | M10 | M6? |  | M8? | M10 | M102 |  |  | M11 |  |  |  | Soll | Ist | Status in %
Machine | System | Resp. Org | Units | CID/AID (?) | Contracted FAT date [target date] | Contracted Delivery date [target date] | Hardware Readiness [actual date] | Software Readiness [actual date] | Require- ments complete | General System Design | HW Design | Prototype incl. FW | FW/GW completed | Production | Completion status | Ready for Installation | SW Design | Base (Erklaerung) Version | Prototype Version | First Version | Ready for Int/Comm. | Advanced Version | Acceptance | Ready for Beam OP | INT- System | In use (ACC)
Common / Superordinate Systems | FAIR Data Master (Phase-0 version) | ACO | 1 | -1 | -1 | -1 | 2018-10-30 | 2019-10-30 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 0 | 51 | 45 | 88.2353
Common / Superordinate Systems | FAIR Data Master (FAIR version) | ACO | 1 | -1 | -1 | -1 | 2022-06-30 | 2024-06-30 | 2 | 2 | [16 empty] | 0 | 51 | 4 | 7.8431
Common / Superordinate Systems | Interlock System (FESA) | ACO | 1 | -1 | -1 | -1 | 2023-03-30 | 2021-10-30 | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  | 3 | 3 | 0 | 51 | 33 | 64.7059
Common / Superordinate Systems | Timing Monitor Systems | ACO | ~6 | -1 | -1 | -1 | 2019-10-30 | -1 | 3 | 3 | 3 | 3 | 3 |  |  |  | 3 | -1 | 3 | 3 | 3 |  |  |  | 3 | 3 | 1 | 48 | 33 | 68.75
Common / Superordinate Systems | Bio-Rem Integration in FESA (several types?) | ACO | ~50 | -1 | -1 | -1 | -1 | -1 | 1 | [17 empty] | 0 | 51 | 1 | 1.9608
Machine SIS100 | Main Power Converter (sc, ACU, ramped) | ACO | 1 | -1 | -1 | -1 | 2021-03-30 | 2021-09-30 | 3 | 3 | 3 | 3 | 2 | 2 |  |  | 3 | 3 | 3 | 3 | 3 | [5 empty] | 0 | 51 | 31 | 60.7843
Machine SIS100 | Power Converters (sc, ACU, ramped) | ACO | 235 | -1 | -1 | -1 | 2021-03-30 | 2021-09-30 | 3 | 3 | 3 | 3 | 2 | 2 |  |  | 3 | 3 | 3 | 3 | 3 | [5 empty] | 0 | 51 | 31 | 60.7843
Machine SIS100 | Power converters (nc, ACU, ramped) | ACO | 3 | -1 | -1 | -1 | 2021-03-30 | 2021-09-30 | 3 | 3 | 3 | 3 | 2 | 2 |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  | 3 | 3 | 0 | 51 | 37 | 72.549
Machine SIS100 | Magnetic Septum (injection, nc, ramped) | ACO | 2 | -1 | -1 | -1 | -1 | -1 | 1 | [17 empty] | 0 | 51 | 1 | 1.9608
Machine SIS100 | Magnetic Septum (extraction, nc, ramped) | ACO | 3 | -1 | -1 | -1 | -1 | -1 | 1 | [17 empty] | 0 | 51 | 1 | 1.9608
Machine SIS100 | Lambertson Septum | ACO | 1 | -1 | -1 | -1 | -1 | -1 | 1 | [17 empty] | 0 | 51 | 1 | 1.9608
Machine SIS100 | Lambertson Steerer | ACO | 2 | -1 | -1 | -1 | -1 | -1 | 1 | [17 empty] | 0 | 51 | 1 | 1.9608
Machine SIS100 | Electrostatic Septum (extraction) | ACO | 2 | -1 | -1 | -1 | -1 | -1 | 2 | [17 empty] | 0 | 51 | 2 | 3.9216
Machine SIS100 | Kicker (injection) | ACO | 1+5 | -1 | -1 | -1 | -1 | -1 | 2 | 2 | 2 | [15 empty] | 0 | 51 | 6 | 11.7647
Machine SIS100 | Kicker (extraction/emergency, ramped) | ACO | 1+8 | -1 | -1 | -1 | -1 | -1 | 2 | 2 | 2 | [15 empty] | 0 | 51 | 6 | 11.7647
Machine SIS100 | Kicker (Q-kick) | ACO | 2 | -1 | -1 | -1 | -1 | -1 | 1 | [17 empty] | 0 | 51 | 1 | 1.9608
Machine SIS100 | KO-Exciter | ? | 1 | -1 | -1 | -1 | -1 | -1 | 1 | [17 empty] | 0 | 51 | 1 | 1.9608
Machine SIS100 | Ring RF: group DDS and switch matrix | RRF | ? | -1 | -1 | -1 | 2019-10-30 | -1 | 3 | 3 | 3 | [15 empty] | 0 | 51 | 9 | 17.6471
Machine SIS100 | Ring RF: acceleration cavities | RRF | 14 (20) | -1 | -1 | -1 | 2019-10-30 | -1 | 3 | 3 | 3 | [15 empty] | 0 | 51 | 9 | 17.6471
Machine SIS100 | Ring RF: bunch compression cavities | RRF | 16 | -1 | -1 | -1 | 2019-10-30 | -1 | 3 | 3 | 3 | [15 empty] | 0 | 51 | 9 | 17.6471
Machine SIS100 | Ring RF: barrier bucket cavities | RRF | 2 | -1 | -1 | -1 | 2019-10-30 | -1 | 3 | 3 | 3 | [15 empty] | 0 | 51 | 9 | 17.6471
Machine SIS100 | Ring RF: long. feedback cavities | RRF | 2 | -1 | -1 | -1 | 2019-10-30 | -1 | 3 | 3 | 3 | [15 empty] | 0 | 51 | 9 | 17.6471
Machine SIS100 | QD-TM (quench detection trigger matrix) | ACO | ~20 | -1 | -1 | -1 | 2021-11-01 | 2021-11-01 | 3 | 3 | 3 | 3 | 2 | 2 |  |  | 2 | 3 | [8 empty] | 0 | 51 | 21 | 41.1765
Machine SIS100 | BPM Concentrator (SIS-100) | ACO | 1 | -1 | -1 | -1 | 2020-10-01 | 2020-10-01 | 3 | 3 | 3 | 3 | -1 | -1 |  |  | 3 | 3 | 3 | 2 |  |  |  |  | 2 | 2 | 2 | 45 | 27 | 60
Machine SIS100 | Fast-BLM DAQ & protection (~200 channels) | ACO | ~12 | -1 | -1 | -1 | -1 | -1 | 2 | 2 | 2 | 2 | 2 |  |  |  | 1 | [9 empty] | 0 | 51 | 11 | 21.5686
Machine SIS100 | FBAS (fast beam abort system) logic matrices | ACO | 6+x | -1 | -1 | -1 | -1 | -1 | 2 | 1 | [16 empty] | 0 | 51 | 3 | 5.8824
Machine SIS100 | FBAS (fast beam abort system) WR interfaces | ACO | ~12 | -1 | -1 | -1 | -1 | -1 | 1 | [17 empty] | 0 | 51 | 1 | 1.9608
Machine SIS100 | Stepping motor control (collimation w/o Timing) | ACO | 3 | -1 | -1 | -1 | -1 | -1 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  | -1 | 3 | 1 | 48 | 39 | 81.25
Machine SIS100 | Digitizer (cycle mode/fast-DAQ) | ACO |  | -1 | -1 | -1 | -1 | -1 | 3 | 3 | 3 | 3 | 3 |  |  |  | 3 | 3 | 3 | 3 | 3 |  |  |  | 3 | 2 | 0 | 51 | 35 | 68.6275
Machine Super-FRS | Power supply control (ACU, sc, DC/multiplex) | ACO | 154 | -1 | -1 | -1 | 2022-03-30 | 2022-09-30 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 3 | 3 | 3 | 3 | [5 empty] | 0 | 51 | 32 | 62.7451
Machine Super-FRS | Power supply control (ACU, DC/multiplex) | ACO | 6 | -1 | -1 | -1 | 2022-03-30 | 2022-09-30 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 3 | 3 | 3 | 3 | [5 empty] | 0 | 51 | 32 | 62.7451
Machine Super-FRS | Stepping Motor Control (collimation, w/o Timing) | ACO | 5 | -1 | -1 | -1 | 2021-12-01 | 2019-03-30 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | [5 empty] | 0 | 51 | 36 | 70.5882
Machine Super-FRS | Stepping Motor Control (collimation, with Timing) | ACO | ? | -1 | -1 | -1 | 2021-12-01 | 2020-12-01 | 2 | 2 | 2 | [5 empty] | 3 | 2 | 2 | [7 empty] | 0 | 51 | 13 | 25.4902
Machine Super-FRS | FBAS (fast beam abort/extraction inhibit) | ACO | 1 | -1 | -1 | -1 | -1 | -1 | 2 | 1 | [16 empty] | 0 | 51 | 3 | 5.8824
Machine HEBT (primary beamlines) | Power Supply Control (warm beamline magnet) | ACO | 557 | -1 | -1 | -1 | 2021-03-30 | 2021-09-30 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 3 | 3 | 3 | [6 empty] | 0 | 51 | 29 | 56.8627
Machine HEBT (primary beamlines) | FBAS (fast beam abort/beam inhibit) | ACO | 1 | -1 | -1 | -1 | -1 | -1 | 2 | 1 | [16 empty] | 0 | 51 | 3 | 5.8824
Machine HEBT (primary beamlines) | Fast-BLM system (beam loss monitor, ~200 channels) | ACO | 15 ? | -1 | -1 | -1 | -1 | -1 | 2 | [17 empty] | 0 | 51 | 2 | 3.9216
Machine HEBT (primary beamlines) | BPM concentrator | ACO | 1 | -1 | -1 | -1 | 2019-10-01 | 2021-03-30 | 3 | 3 | 3 | 3 | -1 | -1 |  |  | 2 | 2 | [8 empty] | 2 | 45 | 16 | 35.5556
Machine HEBT (primary beamlines) | Stepping Motor Control (collimation, w/o Timing) | ACO | ? | -1 | -1 | -1 | -1 | -1 | 3 | 3 | [16 empty] | 0 | 51 | 6 | 11.7647
Machine HEBT (primary beamlines) | Stepping Motor Control (collimation, with Timing) | ACO | ? | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
Machine HEBT & p-bar (secondary beamlines) | Magnetic horn | ACO | 1 | -1 | -1 | -1 | -1 | -1 | 2 | 2 | 2 | [15 empty] | 0 | 51 | 6 | 11.7647
Machine p-Linac | Data Master (p-Linac) | ACO | 1 | -1 | -1 | -1 | 2023-09-30 | 2025-03-30 | 1 | [7 empty] | 1 | [9 empty] | 0 | 51 | 2 | 3.9216
Machine p-Linac | Power Supply (4 Hz pulsed magnets) | ACO | ? | -1 | -1 | -1 | 2023-09-30 | 2023-09-30 | 3 | 3 | 3 | 3 | 2 | 2 |  |  | 1 | [9 empty] | 0 | 51 | 17 | 33.3333
Machine p-Linac | Chopper (p-Linac, with protection interface) | ACO | 1 | -1 | -1 | -1 | -1 | -1 | 3 | 2 | 2 | [5 empty] | 1 | 3 | [7 empty] | 3 | 0 | 51 | 14 | 27.451
Machine p-Linac | Ion source: gas inlet system | ACO | 1 | -1 | -1 | -1 | 2017-09-30 | 2017-09-30 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | -1 | 3 | 1 | 48 | 48 | 100
Machine p-Linac | Ion source: magnetron | ACO | 1 | -1 | -1 | -1 | 2017-09-30 | 2017-09-30 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | -1 |  | 1 | 48 | 45 | 93.75
Machine p-Linac | Ion source: Impedance Adapter | ACO | 1 | -1 | -1 | -1 | 2017-09-30 | 2017-09-30 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | -1
Machine p-Linac | LLRF Control (Libera) | ACO | 10 | -1 | -1 | -1 | 2020-09-30 | 2021-09-30 | 2 | 2 | [16 empty] | 0 | 51 | 4 | 7.8431
Machine p-Linac | Digitizer (4 Hz) | ACO | ? | -1 | -1 | -1 | 2022-03-30 | 2023-03-30 | 3 | 3 | 3 | 3 | 3 |  |  |  | 2 | 3 | [8 empty] | 0 | 51 | 20 | 39.2157
Machine p-Linac | Stepping Motor Control (collimation, w/o Timing) | ACO |  | -1 | -1 | -1 | -1 | -1 | 3 | 3 | 3 | 3 | 3 | 3 | 1 |  | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 3 |  | 3 | 0 | 51 | 44 | 86.2745
Machine CR | Ring power converters (ACU interface) | ACO | ? | -1 | -1 | -1 | 2023-03-30 | 2023-09-30 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 2 | 3 | 3 | 3 | [5 empty] | 3 | 0 | 51 | 31 | 60.7843
Machine CR | Ring power converters (SCU-bus direct) | ACO | ? | -1 | -1 | -1 | 2023-03-30 | 2023-09-30 | 3 | 3 | 3 | 2 | 2 | 2 |  |  | 2 | 3 | 3 | 3 | [5 empty] | 3 | 0 | 51 | 29 | 56.8627
Machine CR | Kicker | ACO | ? | -1 | -1 | -1 | -1 | -1 | 1 | [17 empty] | 0 | 51 | 1 | 1.9608
Machine CR | Stochastic cooling | x |  | -1 | -1 | -1 | -1 | -1 | 1 | [17 empty] | 0 | 51 | 1 | 1.9608
Machine CR | Digitizer (Sync/SR mode) | ACO | ? | -1 | -1 | -1 | -1 | -1 | 3 | 3 | [6 empty] | 2 | 3 | 3 | 3 | [6 empty] | 0 | 51 | 17 | 33.3333
Machine CR | BPM Concentrator (CR) | ACO | 1 | -1 | -1 | -1 | -1 | -1 | 3 | 3 | 3 | 3 | -1 | -1 |  |  | 3 | 3 | 3 | 3 | [6 empty] | 2 | 45 | 24 | 53.3333
Machine HESR | Power Supplies (ACU, nc, ramped) | ACO | many | -1 | -1 | -1 | -1 | -1 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 3 | 3 | 2 | [6 empty] | 0 | 51 | 28 | 54.902
Machine HESR | Digitizer (all modes) | ACO |  | -1 | -1 | -1 | -1 | -1 | 3 | 3 | [16 empty] | 0 | 51 | 6 | 11.7647
Machine HESR | BPM Concentrator (HESR) | ACO | 1 | -1 | -1 | -1 | -1 | -1 | 3 | 3 | 3 | 3 | -1 | -1 | [12 empty] | 2 | 45 | 12 | 26.6667
SIS-18 (Controls Upgrade for FAIR) | BPM Concentrator | ACO | 1 | -1 | -1 | -1 | 2020-10-31 | 2020-10-31 | 3 | 3 | 3 | 3 | -1 | -1 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 2 |  |  |  |  | 2 | 45 | 30 | 66.6667
SIS-18 (Controls Upgrade for FAIR) | Magnet Power Converter | ACO |  | -1 | -1 | -1 | 2018-03-30 | 2018-09-30 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 3 | 3 | 0 | 51 | 44 | 86.2745
SIS-18 (Controls Upgrade for FAIR) | RF | ACO |  | -1 | -1 | -1 | 2018-03-30 | 2018-09-30 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | 2 | 3 | 0 | 51 | 43 | 84.3137
SIS-18 (Controls Upgrade for FAIR) | Spill Abort System | ACO |  | -1 | -1 | -1 | 2019-09-30 | 2019-09-30 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |  |  | -1 | 2 | 1 | 48 | 40 | 83.3333
SIS-18 (Controls Upgrade for FAIR) | Bumper | ACO |  | -1 | -1 | -1 | -1 | -1 | 1 | [17 empty] | 0 | 51 | 1 | 1.9608
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0

## Actual Status Timing Hardware
[5 empty] | 43987 |  |  |  | -12 | -12 | 36 | 35 | 35 | 25 | 660 | 33 | 33 | 33
Controls | [5 empty] | Legend |  |  |  | must be updated by FAIR/GSI team
[6 empty] | -1 | not necessary |  |  | must be updated by BNG team
Contract | GSI IKC 3 |  |  |  |  | 0 | not stated
PSP: | 2.14.10.3 |  |  |  |  | 1 | planned
[6 empty] | 2 | in process |  | Design |  | Hardware & Electronics | [5 empty] | Tests
In Abstimmung mit PLM werden Controls CID's in FNT-Command verwaltet | [5 empty] | 3 | ready |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 9
[11 empty] | M6? | M8? |  |  | M9? | M10 |  |  |  | Soll | Ist | Status in %
Machine | System | Resp. Org | Units | CID/AID (?) | Contracted FAT date [target date] | Contracted Delivery date [target date] | Forecast FAT date [actual date] | Hardware Readiness [actual date] | Require- ments complete | General System Design | HW Design | Prototype incl. FW | FW/GW completed | Production | Completion status | Ready for Installation | INT- System | In use (ACC)
Common / Superordinate Systems | Timing Receiver AMC | ACO | 280 | AID:0002209 | -1 | -1 | 2019-06-30 | 2019-12-15 | -1 | -1 | 3 | 3 | 3 | 3 | 280 | 3 | 3 | 3 | 2 | 21 | 21 | 100
Common / Superordinate Systems | Timing Receiver PMC | ACO | 220 | AID:0002210 | -1 | -1 | 2019-06-30 | 2019-12-15 | -1 | -1 | 3 | 3 | 3 | 3 | 220 | 3 | 3 | 3 | 2 | 21 | 21 | 100
Common / Superordinate Systems | Timing Receiver PCIe | ACO | 500 |  | -1 | -1 | 2020-11-30 | 2021-01-30 | -1 | -1 | 3 | 2 | 2 | [5 empty] | 2 | 21 | 7 | 33.3333
Machine SIS100 | White Rabbit Switch | ACO | 95 | AID:0002489 | -1 | -1 | 2020-08-30 | 2020-10-30 | -1 | -1 | 3 | 3 | 3 | 2 | 60 | 3 | 3 | 3 | 2 | 21 | 20 | 95.2381
Machine Super-FRS | White Rabbit Switch | ACO | 55 | AID:0002489 | -1 | -1 | 2020-08-30 | 2020-10-30 | -1 | -1 | 3 | 3 | 3 | 2 | 37 | 3 | 3 | 3 | 2 | 21 | 20 | 95.2381
Machine HEBT (primary beamlines) | White Rabbit Switch | ACO | 49 | AID:0002489 | -1 | -1 | 2020-08-30 | 2020-10-30 | -1 | -1 | 3 | 3 | 3 | 2 | 33 | 3 | 3 | 3 | 2 | 21 | 20 | 95.2381
Machine p-Linac | White Rabbit Switch | ACO | 13 | AID:0002489 | -1 | -1 | 2020-08-30 | 2020-10-30 | -1 | -1 | 3 | 3 | 3 | 2 | 5 | 3 | 3 | 3 | 2 | 21 | 20 | 95.2381
Machine CR | White Rabbit Switch | ACO | 29 | AID:0002489 | -1 | -1 | 2020-08-30 | 2020-10-30 | -1 | -1 | 3 | 3 | 3 | 2 | 10 | 3 | 3 | 3 | 2 | 21 | 20 | 95.2381
Machine HESR | White Rabbit Switch | ACO | 25 | AID:0002489 | -1 | -1 | 2020-08-30 | 2020-10-30 | -1 | -1 | 3 | 3 | 3 | 2 | 10 | 3 | 3 | 3 | 2 | 21 | 20 | 95.2381
Machine HEBT & p-bar (secondary beamlines) | White Rabbit Switch | ACO | 2 | AID:0002489 | -1 | -1 | 2020-08-30 | 2020-10-30 | -1 | -1 | 3 | 3 | 3 | 2 | 0 | 3 | 3 | 3 | 2 | 21 | 20 | 95.2381
Experiments | White Rabbit Switch | ACO | 17 | AID:0002489 | -1 | -1 | 2020-08-30 | 2020-10-30 | -1 | -1 | 3 | 3 | 3 | 2 | 5 | 3 | 3 | 3 | 2 | 21 | 20 | 95.2381
SIS-18 (Controls Upgrade for FAIR) | White Rabbit Switch | ACO |  | AID:0002489 | -1 | -1 | -1 | -1 | -1 | -1 | 3 | 3 | 3 | 3 |  | 3 | 3 | 3 | 2 | 21 | 21 | 100
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [10 empty] | 0 | 27 | 0 | 0

## Actual Status Controls Software
[5 empty] | 43987 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Controls | [5 empty] | Legend |  |  |  | must be updated by FAIR/GSI team
[6 empty] | -1 | not necessary |  |  | must be updated by BNG team
Contract | GSI IKC 3 |  |  |  |  | 0 | not stated
PSP: | 2.14.10 |  |  |  |  | 1 | planned
[6 empty] | 2 | in process |  | Design |  | Hardware & Electronics | [5 empty] | Software | [7 empty] | Tests
In Abstimmung mit PLM werden Controls CID's in FNT-Command verwaltet | [5 empty] | 3 | ready |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 17
[9 empty] | M3 Extern | M3 (CDR) | M6? | M8? |  |  | M9? | M10 | M6? |  | M8? | M10 | M102 |  |  | M11 |  |  |  | Soll | Ist | Status in %
Machine | System | Resp. Org | Units | CID/AID (?) | Contracted FAT date [target date] | Contracted Delivery date [target date] | Forecast FAT date [actual date] | Forecast by supplier delivery date [actual date] | Require- ments complete | General System Design | HW Design | Prototype incl. FW | FW/GW completed | Production | Completion status | Ready for Installation | SW Design | Base (Erklaerung) Version | Prototype Version | First Version | Ready for Int/Comm. | Advanced Version | Acceptance | Ready for Beam OP | INT- System | In use (ACC)
| Controls Services |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
| MASP |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
| BTM |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
| Archiving System |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
| Diagnostic Logging |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
| Controls Application |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
| DeviceControl |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
| … |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
|  |  |  | -1 | -1 | -1 | -1 | -1 | [18 empty] | 0 | 51 | 0 | 0
DRAFT - WORK IN PROGRESS

## Legende (hidden)
-1
0
1
2
3