## Sheet1
| Activities |  |  | Executing Departments (directly involved in SW development) | [12 empty] | SPL Requester Anforderer | Phases Phasen |  |  | Prio (1-4, Erläuterung siehe rechts) | Status | 1: “geht nicht ohne” – zwingend für den Anlagenbetrieb 2: “geht ohne” – aber nur auf Kosten von Personal-Ressourcen & (In-)Betriebs-Effizienz 3: Qualitäts- und Maschinenschutz (Hochstrombetrieb, p, ...) 4: “geht ohne” – aber mit reduzierter Betriebseffizienz ACC: alle Beschl., wenn nicht alle, dann Einzelaufzählung
| Beschreibung: | Description | Kürzel | ACO | BIT | BEA | SFR | SRP | RRF | OPE | SYS | DEC | APH | CRY | EXP | count |  | HWC (& controls) | BC (& dry runs) | OP (user)
Facility Control | Kryoanlage: | Cryogenic Controls | [13 empty] | 1
| Kryoanlagensteuerung (Integration) | Cry plant (Cryo2) control (integration only) | [13 empty] | 1 | COM |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) CRY
| Kryverteilung Steuerung | Cryo distribution control | [13 empty] | 1 | COM |  |  |  | 1 |  |  | Prioritäten-Verteilung
| SIS100 (dynamische) Wärmelastvorhersagen | SIS100 dynamic load predictions | [13 empty] | 1 | SIS |  |  |  | 3 |  |  | Prio-1 | Prio-2 | Prio-3 | Prio-4 | bar: Executing Departments (directly involved in SW development) SYS
|  | Vauum Controls | [14 empty] | COM
|  | Vacuum control and safety | [14 empty] | COM |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) ACO
|  | Cryo insulation vacuum control | [14 empty] | COM |  |  |  | 1
| TGA Überwachung | Building services engineering (TGA) Monitoring | [13 empty] | 1 | [7 empty] | 41 | 6 | 6 | 6
| Medienversorgung | Monitoring of accelerator media | [13 empty] | 1 |  |  |  |  | 4 |  |  | 69.49% | 10.17% | 10.17% | 10.17%
| el. Leistungsüberwachung (puls + common ?) | Electrical load monitoring (pulse/common mains) | [13 empty] | 1 | SIS |  |  |  | 3
| Kühlwassertemperaturen | Cooling water temperatures | [13 empty] | 1 |  |  |  |  | 4
| Kühltürme | Cooling plants | [13 empty] | 1 |  |  |  |  | 4
| Lüftungen/Kühlung | Ventilation/colling | [13 empty] | 1
| Anlagen-Ablaufsteuerung | Sequential Facility Control incl. Apps | Timing | [12 empty] | 1 |  |  |  |  | 1
| Timing System | Timing Master | [13 empty] | 1 | ACC |  |  |  | 1
| Timing System Steuerung | Timing Director | [13 empty] | 1 | ACC |  |  |  | 1
| Experiment Anfordereinheit | Request Processor | [13 empty] | 1 | EXP |  |  |  | 1
| Ausführungssteuerung | Scheduling | BSS Control | [12 empty] | 1 | ACC |  |  |  | 1
| Ausführungsplanung | Pattern Creation | Scheduling App | [12 empty] | 1 | ACC |  |  |  | 1
| Machine- und Beam-Mode Verwaltung | Machine and Beam-Mode Control | [13 empty] | 1 | ACC |  |  |  | 1
| Timing Monitor | Timing Monitor & Diagnostics | [14 empty] | ACC |  |  |  | 2
| Personenschutz | Personnel Safety | [13 empty] | 1
| Strahlenschutz-Systeme | Radiation Protection System | [13 empty] | 1 | SRP |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) SRP
| Beschleuniger Zugangskontrolle PAS | Acc. Personnel Access System (PAS) | PAS | [12 empty] | 1 | SRP |  |  |  | 1
| Maschinenschutz | Machine Protection | [13 empty] | 1
| Geräteüberwachung & Verriegelung | Device Status Monitoring and Interlocking | MASP | [12 empty] | 1 | all |  |  |  | 1
| Schneller Strahlabwurf – SIS18/SIS100 | Fast-Beam-Abort-System – SIS18/SIS100 | FBAS | [12 empty] | 1 | SIS |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) SYS
| Schneller Strahlabwurf - Primärstrahllinien | Fast-Beam-Abort-System - primary beam lines | FBAS | [17 empty] | 3
| Schneller Strahlabwurf – SuperFRS | Fast-Beam-Abort-System – SuperFRS | FBAS | [12 empty] | 1 | SFR |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) SFR
| Schneller Strahlabwurf – Experimente | Fast-Beam-Abort-System – Experimente | FBAS | [12 empty] | 1 | EXP |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) EXP
| Fast BLM System (Protection) | Fast BLM System | [18 empty] | 3
| Permit-Service | Permit-Service (Powering, Movable Devices) | MASP | [17 empty] | 3
| Anlagen-Statusanzeige (General) | Acc. Facility Overview
| Beschleunigeranlagenstatus | Status Machine(s) | [18 empty] | 1
| Status der Strahlproduktionskette | Beam Production Chain Status | [18 empty] | 1
| Online Timing & scheduling Monitor | Online Timing & Scheduling Monitor | [14 empty] | ACC |  |  |  | 1
| Status industrielle Subsysteme | Status Industrial systems (vac, cryo) | [18 empty] | 2
| Anlagenstatusanzeige (Web-basiert) | Fixed-Display (web-based) | [13 empty] | 1
| Beschleunigeranlagenstatus | Accelerator Facility Status | [13 empty] | 1 | ACC |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) OPE
| Maschinen Status | Ind. Machine Status | [13 empty] | 1 | ACC,SIS |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) SYS
| Status der Strahlproduktionskette | Beam-Production-Chain Status | BPC Status | [12 empty] | 1 | SIS |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) SYS
| Experiment Status | Experiment Status | [13 empty] | 1 | EXP.ACC |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) EXP
| Verfügbarkeitsanalyse Tools | Machine Availability Analysis Tools | [13 empty] | 1 | OPE |  |  |  | 4
| … | ... | [13 empty] | 1
Machine Controls (system- and beam-based) | Datenversorgung | Settings Supply | [13 empty] | 1
| Sollwert-Vorgaben und Steuerung | Device and beam parameter settings | ParamModi | [12 empty] | 1 | ACC |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) SFR; Executing Departments (directly involved in SW development) SYS
| Maschinen-Modellierung | Machine modelling | LSA make-rules | [12 empty] | 1 | ACC |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) SFR; Executing Departments (directly involved in SW development) SYS
| Strahlüberwachungssysteme | Beam Monitoring | [13 empty] | 1
| Transmissionsüberwachung | Beam-Transmission-Monitoring | BTM | [12 empty] | 1 | ACC |  |  |  | 2
| Strahlparamterüberwachung | Beam-Quality-Monitoring | BQM | [12 empty] | 1 | SIS,DEC |  |  |  | 3
| Multi-Parameter-Beam GUI | Multi-Parameter-Beam GUI | [13 empty] | 1 | APE |  |  |  | 3
| Strahlbasierte Regel- & Steuerungssysteme | Beam-Based Control Systems | [13 empty] | 1
| Inj./Extr. Trajektorien (BPM-basiert) | inj./extr. trajectories (BPM-based) | [13 empty] | 1 | SIS |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) SYS
| Strahlführungseinstellung | trajectory control HEST | “Benno” | [12 empty] | 1 | COM |  |  |  | 2 | bar: Executing Departments (directly involved in SW development) OPE
| Closed Orbit and Radiallage Korrektur | closed-orbit and radial-loop | [13 empty] | 1 | SIS |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) SYS
| Q/Q’-Kontrolle | Q/Q’ control | [13 empty] | 1 | SIS |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) SYS
| Injektion Matching (trans. & long.) | Multi-Turn-Injection | MTI | [12 empty] | 1 | SIS,DEC |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) SYS
| Bunch2Bucket Strahltransfer | Bunch2Bucket beam-transfer | B2B | [12 empty] | 1 | SIS |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) SYS
| Optimierung Langsame-Extraktion (allgemein) | Slow-Extraction | [13 empty] | 1 | SIS |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) SYS
| Optimierung Langsame-Extraktion (Spillform/-struktur) | Slow extraction optimisation (spill form/structure) | [18 empty] | 2 | bar: Executing Departments (directly involved in SW development) SYS
| Optik Messung und Korrektur | optics measurement & correction | [13 empty] | 1 | SIS |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) SYS; Executing Departments (directly involved in SW development) APH to Executing Departments (directly involved in SW development) CRY
| Collimator/Cleaning set-up – SIS100 | Collimator/Cleaning set-up – SIS100 | [13 empty] | 1 | SIS |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) SYS
| Collimator/Cleaning set-up – SFR | Collimator/Cleaning set-up – SFR | [13 empty] | 1 | SFR | bar: Executing Departments (directly involved in SW development) SFR
| Maschinenschutzvalidierung – SIS100 | MPS validation – SIS100 | [13 empty] | 1 | SIS |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) SYS
| Maschinenschutzvalidierung – Super FRS | MPS validation – Super FRS | [13 empty] | 1 | SFR | bar: Executing Departments (directly involved in SW development) SFR
| Kühlprozess Optimierungen | beam-cooling optimisation | [13 empty] | 1 | SIS |  |  |  | 3
| Final-Focus Einstellung (x/y,x’/y’, β, …) | final-focus control (x/y,x’/y’, β, …) | [13 empty] | 1 | COM |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) SYS
| HF Manipulationen | RF bunch gymnastics | [13 empty] | 1 | SIS |  |  |  | 2 | bar: Executing Departments (directly involved in SW development) SYS
| Post-Mortem-Analyse | Post-Mortem-Analysis | [13 empty] | 1 | SIS,SFR |  |  |  | 3
| PM Datenerfassung | PM data acquisition readout and persistence | PM
| Supraleitende Magnete (Quench-Analyse) | superconducting magnets (quench analysis) | [13 empty] | 1 | SIS,SFR |  |  |  | 1
| Strahlverlust-bezogen (FBAS, pBar operation, …) | beam-related losses (FBAS, pBar operation, …) | [13 empty] | 1 | SIS,PLI |  |  |  | 3
| Steuerung Lokale Kryogenik | Control local cryogenics | [13 empty] | 1
| Visualisierung & Semi-automatische Steuerung (Sensoren, Druck, Temp, Aktuatoren, Heizer, …) | Visualisation, semi-automatic control (sensors, pressure, temp., actuators, heater, ...) | [14 empty] | SIS,SFR, COM |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) CRY
| Betriebsabh. automatische Steuerung | Automation processes/sequences | [13 empty] | 1 | SIS, COM |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) CRY
| andere semi-automatisierte Prozeduren | Other semi-automated procedures | [13 empty] | 1
| Parameter Scans | Parameter scan | [13 empty] | 1 | SIS,OPE |  |  |  | 4 | bar: Executing Departments (directly involved in SW development) SYS to Executing Departments (directly involved in SW development) APH
| … | … | [13 empty] | 1
Equipment Control | Beschleuniger-Gerätesteuerung | Accelerator equipment control & tools/GUIs | FESA | [17 empty] | 1
| Magnetstromversorgungen | Power converter control (all) | [14 empty] | COM |  |  |  | 1
| Ring-RF Steuerung | Ring RF equipment control | [14 empty] | COM |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) RRF
| Kicker/Septa Steuerung | Pulsed power systems control | [14 empty] | COM |  |  |  | 1
| Schrittmotorsteuerung | Stepping motor control | [14 empty] | COM |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) BEA
| Stahldiagnosesysteme | Beam instrumentation systems | [14 empty] | COM |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) BEA
| Maschinenspezifische Geräteklassen (diverse) | Maschine-specific FESA classes (various) | [14 empty] | COM |  |  |  | 1
| Digitizer Control | Digitizer Systems & Generic DAQ App | [14 empty] | COM |  |  |  | 1
| ... | ...
| Expertentools/GUIs für Gerätezugriffe (idR. per Device Klasse/Maschine) | Expert tools & GUIs (per device/machine) | [13 empty] | 1
| DC-Trafo, | DCT | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| AC-Trafo, | ACT | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| FCT-Ring & Transferlinien, | FCT Ring and Transfer Lines | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| BPM (je Typ./Maschine), | BPM (by type/machine) | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| RSA, SIS-Radio, | RSA, SIS-Radio | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| Lassie, | Lassie | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| IPM, | IPM | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| BIF | BIF | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| Profilgitter, | Profile grids | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| Kameras, | Cameras | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| HV-Control, | HV control | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| MAPS2, | MAPS2 | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| BIF, | BIF | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| BTF Scan | BTF Scan | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| IonSource GUI | IonSource GUI | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) OPE
| UNILAC Energie-Messung (ToF) | UNILAC Energy mesasurement (ToF) | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) BEA
| Schottky – Maschine | Schottky – Machine | [13 empty] | 1 | SIS |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) SYS
| Schottky – Experimente | Schottky – Experiments | [13 empty] | 1 | bar: Executing Departments (directly involved in SW development) EXP
| ... | ... | [13 empty] | 1
| Fast-Beam-Abort-System (Controller) | Fast-Beam-Abort-System (Controller) | [13 empty] | 1 |  |  |  |  | 3 | bar: Executing Departments (directly involved in SW development) RRF
| Bunch-2-Bucket System (low-level timing) | Bunch-2-Bucket System (low-level timing) | [13 empty] | 1 |  |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) RRF
| Device Control GUI | Device Control GUI | [13 empty] | 1 |  |  |  |  | 1
| Toleranzbandüberwachung | Actual-vs-Reference-Monitoring/Interlocking | [13 empty] | 1 | SIS |  |  |  | 2 | bar: Executing Departments (directly involved in SW development) SYS
| Integration generischer Sensordaten und Aktuatoren (z.B. Kryogenie, Vakuum) | Integration of generic sensor data and actuators (e.g. cryogenics, vacuum) | [13 empty] | 1 |  |  |  |  | 2
| Daten-Konzentratoren | Data Concentrators (PBM, ...) | [18 empty] | 2
Generic Services | LSA-Settings Verwaltung | LSA-Settings-Management | LSA
| Geräteversorgung (drive) | Device setting supply (drive) | [18 empty] | 1
| Muti-Parameter-Beam Infrastruktur | Muti-Parameter-Beam infrastructure | [18 empty] | 3
| Verwaltung kritischer Maschineneinstellungen | Management of Critical Settings | MCS | [17 empty] | 3
|  | Front-End Software Architecture | FESA | [12 empty] | 1 |  |  |  |  | 1
| Generische Kontrollraumanwendungen (nicht masch.-spez.) | Generic Control Room Apps (not machine specific) | [18 empty] | 1
| Beam Request System to users (App, API) | Beam Request System to users (App, API) | [18 empty] | 1
| Machine-Experiment Datenaustausch | Machine-Experiment Data Exchange Interface | [18 empty] | 4 | bar: Executing Departments (directly involved in SW development) SYS; Executing Departments (directly involved in SW development) EXP
| Archivierungs Dienst | Archiving-Service | [13 empty] | 1
| Archiving System | Archiving System | [13 empty] | 1 | ACC |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) OPE
| Generische Daten-Visualisierung | Generic data visualisation and retrieval | [13 empty] | 1
| Rechte Management | Role-Based-Access Management | RBAC | [12 empty] | 1 |  |  |  |  | 1
| generischer Automatisierungs-Dienst (Sequencer) | Sequencer Service | Sequencer | [12 empty] | 1 |  |  |  |  | 1
| Diagnostic Logging | Diagnostic Logging | [13 empty] | 1 |  |  |  |  | 1
| Post-Mortem-System | Post-Mortem-System | PM | [12 empty] | 1 |  |  |  |  | 1
| generische Digitalisierung (Digitizer, non-BI) | Generic Digitizers (non-BI) | [13 empty] | 1 | SIS |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) SYS
| Messdaten-Visualisierungstechnologien | Measurement data visualisation | chart-[fx,Qt] | [12 empty] | 1 | SIS |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) SYS
| Middle-Tier-Services (Maschinensteuerung) | Middle-Tier-Services (equip. & beam-based)) | [13 empty] | 1 | SIS |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) SYS
| HMI Schnittstelle – Poti-Board | ... | [13 empty] | 1
IT Infrastructure (for services / für Dienste) | Rechnercluster | Accelerator IT cluster system | [13 empty] | 1 |  |  |  |  | 1
| Generische Dienste | General services | [13 empty] | 1 | SIS |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) ACO to Executing Departments (directly involved in SW development) BIT
| Entwicklungsumgebung | Development environment & tools | [13 empty] | 1 |  |  |  |  | 1
| Continuous Int. und Deployment (CI/CD) | Continous int. & dev. Environment (CI/CD) | [13 empty] | 1 | SIS |  |  |  | 1
| Verwaltung von Container-Anwendungen | Container management services | [13 empty] | 1 |  |  |  |  | 2 | bar: Executing Departments (directly involved in SW development) ACO to Executing Departments (directly involved in SW development) BIT
| Versionsverwaltungssoftware | Version control systems | [13 empty] | 1 |  |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) ACO to Executing Departments (directly involved in SW development) BIT
| Logbuch (O-LOG) | Electronic log book (operation) | [13 empty] | 1 | ACC |  |  |  | 1 | bar: Executing Departments (directly involved in SW development) OPE
| User-Account Management (RBAC & Auth. Service) | User-account management (auth services) | [13 empty] | 1 | ACC |  |  |  | 3
| Datenbanken | Accelerator Databases | [13 empty] | 1 |  |  |  |  | 1
| Netzwerk-Infrastruktur (Technische Netze) | Network Infrastructure (technical networks) | [13 empty] | 1 |  |  |  |  | 1
| Technische Netzwerke | Ethernet, Profinet, White Rabbit | [18 empty] | 1
| Aktive Komponenten (Switches, Firewall, Proxies, ...) | Active components (switches, firewall, ...) | [18 empty] | 1
| Technische Ausstattung Main Control Room | Technical equipment Control Room (FCC) | [14 empty] | ACC |  |  |  | 1
| … | … | [13 empty] | 1

## Prio-Def
Priorities
1: essential function: no operation without
2: important function: operation at the expense of personnel resources & (in)efficiency
3: required function for quality- and high intensity operation
4: operation with degraded operational efficience possible