## Slide 1: Accelerator Operations – 29.09.2020
Shutdown
essentially ongoing as planned
Risks:
  delay of earth work on FSB Tunnel 101  start of SIS18-beam time 2021 in Feb. is at risk
    shutdown schedule is tight in terms of alignment, Nov. 30 Survey must start to be able to finish alignment of critical areas until Jan. 29th
    building settlement will be observed by Heinen&Fischer – measurements can be started, when radiation safety wall is installed / settlement of 1-3 cm expected / discussion ongoing
    if the earth cannot be put back on tunnel before beam time, SIS18 beam time must be delayed since the earth is part of the radiation shield
    additional settlement will continue over beam time  – no big risk for beam time expected
    meeting with FSB on Sept 23th for status update
  Water ingress via HKR ceiling
    Mr. Reckziegel responded and takes care on the issue, a leakage in HKR-roof was identified
    a preliminary “drainage” has been installed in HKR
    Last rainfall caused no water ingress anymore
    Complete renovation of the roof sealing is planned for autumn this year.
    no new information

## Slide 2
irritating and corrosive liquid found during sealing work, caused a closure of the Kicker-Room for work
  A. Schumann provided a schedule for cleaning of the transformers and the switching cabinet in front of the kicker room until 31.08. to not to interfere with H=2-Cavity tests
  very low formaldehyde concentration measured (below legal limit), so R. Becker approved the continuation of work in the room
  Construction work needs to be finished urgently. After intervention by N. Pyka, the completion deadline was set to Friday, 2.10.2020.
TVS no progress since July  working UNILAC access system at risk
  ACO and BEA are waiting for a risk analysis and the strategy document by T. Radon
  Meeting with T. Radon after Machine Meeting
  T. Radon declared, he will take care an will contact ACO and BEA.
  Currently T. Radon is on sick leave.
Downtime of main electricity supply =AC in KW45
  necessary for maintenance
  power supply for BG, SIS and everything downstream
  power supply for vacuum and cryogenics will be substituted
  needs careful planning. A separate meeting with the users will be scheduled.