## Slide 1
PANDA meeting
Status production PANDA solenoid
E.Pyata, S.Pivovarov, M.Kholopov, M.Azimbaev BINP, Novosibirsk

## Slide 2
The main milestones of production of the PANDA solenoid magnet
The scope of delivery includes:
Magnetic and engineering design of the magnet including tools and support;
Production and delivery of the magnet (consisting of yoke, cold mass and cryostat, alignment components, proximity cryogenics, support frame and platform beams) and all tools;
Power converter and quench protection and instrumentation.
Item | Date
Start contract | 03/2017
Control assembling of the Yoke of solenoid at the BINP site | 09/2020
Magnetic tests of the PANDA solenoid including safety system and electrical components at BINP (additional contract) | 12/2021 - 05/2022
Assembling and tests at the FAIR site | 
Assembling of the magnet at Darmstadt | 06/2022
Acceptant tests at FAIR | 08/2022
Installation of the PANDA solenoid magnet at worked position and final acceptance tests | 01-05/2023

## Slide 3
PANDA solenoid magnet, BINP responsibility
Power supply and energy extraction system
Cable channel
Control Dewar box
Solenoid and yoke
Frame of Yoke
Dump resistor
Energy Extraction Rack
Power Supply

## Slide 4: 3D model of the Magnet and Control Dewar.
Control Dewar box
Cryostat and Coil

## Slide 5
Development of the PANDA solenoid magnet
Name of item | Status of work
Yoke and frame | Final machining 5 July 2020 Start control assembling July 2020
Cryostat of solenoid & Cold mass | Design is ready, technological development, purchasing raw materials Contract production 01.09.2020
Conductor purchasing | Development work, Contract production 18.08.2020
Control Dewar box | Preliminary design October 2020 - OK
PANDA solenoid power cabling | Design is ready, production
Power supply and energy extraction system | Detail design is ready, purchasing power convertors & components. Production
Magnet safety system | in process

## Slide 6
Status of the PANDA cryostat and cold mass production

## Slide 7
The main milestones of the Cryostat production
Name of milestone |  | Date 2017/10
FDR of the Cryostat |  | 08/02/2019
FDR of the Cold Mass |  | 17/04/2019
Status production |  | 
Cryostat stands for assembling solenoid and magnet Cold Mass | Contract production 18.08.2020 | 
 | Purchasing raw material 10/2020 – 95% Delivery raw material to subcontractor – 12/2020 | 
 | Manufacturing Technical documentation 11/2021 | 
 | Contract: delivery to BINP 09/2021 | 

## Slide 8
Status of the PANDA yoke production

## Slide 9: 3D model of the Yoke and Frame.
Control assembling
1st - 09/2020
2nd - 11/2020
Frame
Yoke

## Slide 10
The main milestones of the yoke production
Name of milestone |  | Date 2017/10 | Comments
Production of the all barrel octants |  | 04/2020 | Ready
Production of the frame and beams |  | 04/2020 | Ready
Production of the doors | Upstream | 05/2020 | Ready
 | Downstream | 06/2020 | June 2020
Control assembling at SET |  | 07– 09/2020 | 
Finalization of the parts |  | 08 - 10/2020 | 
Assembling of the Yoke at BINP |  | ? | 

## Slide 11: Production of the parts of the Yoke

## Slide 12: Assembling of the Yoke

## Slide 13: Assembling of the Yoke

## Slide 14: Assembling of the Yoke

## Slide 15: Assembling of the Yoke

## Slide 16: Assembling of the Yoke
Installed 10 support for detectors of a laser tracker.
Built an axis of the yoke and 3D map of elements by a laser tracker.
Measuring surfaces of the octants and wings we can do correction each part of the frames and barrel part of the yoke.
We plan to install about 30 the same support to do assembly of the yoke more quickly and suitable/

## Slide 17
Status of the PANDA conductor development/ procurement

## Slide 18
Conductor.
Status of the PANDA conductor development/ procurement
BINP/ VNIINM Bochvar/ VNIIKP/ Saransk cable optic (SarKO)
Rutherford cable co-extrusion/ conklad in a pure Al
Production1000m Cu Rutherford cable for tests in SARKO - 03-04/ 2020 (in BINP)
Tests in SARKO, 1000m Cu Rutherford cable - 09-12/ 2020
Preparation contracts for PANDA NbTi strands production, VNIINM - 03/ 2020
Production strands VNIINM for central coil - 02/2021
Production strands VNIINM for up/downstream coils - 09/2021
PANDA Rutherford cables production, VNIIKP - 03-10/ 2021
Production PANDA conductor BINP/SARKO - 03 - 11/ 2021

## Slide 19
Main risks
Longitudinal section of the cryostat with cold mass.
Cold mass cross-section.
Cross-section of the conductor.
Conductor mechanical and electrical parameters.
Thickness (after cold work) at 300 K | mm | 7.93 | ± 0.03
Width (after cold work) at 300 K | mm | 10.95 | ± 0.03
Critical current (at 4.2 K, 5 T) | A | > 14690 | 
Critical current (at 4.5 K, 3 T) | A | > 16750 | 
Overall Al/Cu/sc ratio |  | 10.5/1.0/1.0 | 
Aluminum RRR (at 4.2 K, 0 T) |  | > 1000 | 
Al 0.2% yield strength at 300 K | MPa | > 30 | 
Purchasing super conductive conductor - lack of a manufacturers
Rutherford cable, 8 strands, extruded in Al matrix

## Slide 20
8 pieces of the samples of PANDA conductor produced with different tools were tested for a shear strength. Results are 62,5 – 85,3 MPa. Specified value of a shear strength is ≥20 Mpa.
Status of the PANDA conductor development/ procurement
Photo of the samples of PANDA conductor
Scheme of shear strength measurement

## Slide 21
Development works with a prototype Rutherford cable (Cu or NbTi) to co-extrusion/ conklad in a pure Al 995 and Aluminum A95
Oven for preheating a Rutherford cable.
Temperature - 200 ÷ 450°C;
Shielding gas – N2
Preparation a contract BINP/SARKO to development a technology production a conductor with preheating and creating intermetallic connection Al/Cu.
Status of the PANDA conductor development/ procurement

## Slide 22
Status of the PANDA coils production

## Slide 23
The main milestones of the coils production
Status production | 
Cryostat and stands for assembling solenoid and magnet | Design is ready, technological development, Call for tender
Cold Mass | Design is ready, technological development, Call for tender
First Prototype of the Coil | 11/2019
Second Prototype of the Coil | 03/2020
Third Prototype of the Coil | 08/2020
Tooling for winding Coil (and Prototype) | 11/2019
Tooling for impregnation of Coil (and Prototype)/modified | 11.2019/03.2020
Prepress prototype coil into cold mass | 10/2020
Tooling for winding and impregnation of PANDA Coil | Design is ready, technological development, Call for tender

## Slide 24: The Prototype of the Coil (3pcs.)
OD = 1m,
h=180 mm
Conductor:Al
10,85 мм x 7.93 мм,
6 layers
16 turns
Design is ready, 2 prototype produced

## Slide 25: The Prototype of the Coil (3pcs.)
Preparation prestress procedure of coil
to an aluminum shell
For prototype heater:
Length - 17m;
Power - 3,5 kW;
Cross section - 24 x 3 mm;
Quantity - 1 pc.
For PANDA coil
Length - 36m;
Power - 3,0 kW;
Cross section - 24 x 3 mm;
Quantity - 8-9 pc.
Design is ready, preparation heat system

## Slide 26
Production of the coil prototype

## Slide 27
Development works with a prototype Rutherford conductor.
Material is Aluminum A95
Third prototype
Electrical tests 3rd prototype - OK;
Procedure heating Al shell with control uniformity distribution of temperature, temperature rate, shell expansion measurement - OK;
Assembling coil and Al shell with prestress - OK;
Mechanical test coil assembling – OK, ≥2500 kg shear strength;
Destroy tests;
Thermal shock tests LN2;
Checking quality of an epoxy penetration, mechanical tests;
Analysis of the manufacturing quality of the third prototype;
Preparation production of the 4th prototype
Status of the PANDA coil development/ production

## Slide 28
Status of the PANDA coil development/ production
Номер катушки/ Coil | Дата/Date | R изм кат/ R coil | t катушки, оС / Temperature of coil | R привед. кат/ R at 20оС | Индуктивность / Inductance of the coil | кз виток 1000/ Short circuit | Rиз 10000/ R insulation to shell
 |  |  |  |  | 100/1000Гц/Hz |  | 10kV
 |  | мОм/mOhm |  | мОм/mOhm | мГн/mH |  | 
3 | 25.09.2020 | 98,39 | 20,0 | 98,39 | 12,60/11,93 | нет/No | >100Мом/MOhm
No. испытаний / test | No. катушки / coil | Дата/ Date | Импульсное напряжение/ Pulse voltage, V | КЗ виток / Short circuit interturn insulation
1 | 3 | 25.09.2020 | 1000 | нет/No
2 | 3 | 28.09.2020 | 500 | нет/No
3 | 3 | 28.09.2020 | 1000 | нет/No
4 | 3 | 28.09.2020 | 1500 | нет/No
5 | 3 | 28.09.2020 | 2000 | нет/No
Results of measurements 3rd coil.
Tests interturn insulation of the coil.

## Slide 29
Status of the PANDA coil development/ production
Results of measurements 3rd coil with Al shell.
No. испытаний / test | No. катушки / coil | Дата/ Date | Время выдержки/ Time | Постоянное напряжение/ Constant voltage, V | КЗ виток / Short circuit interturn insulation
1 | 3 | 15.10.2020 | 1 min | 1000 | нет/No
2 | 3 | 15.10.2020 | 1 min | 2000 | нет/No
3 | 3 | 15.10.2020 | 1 min | 3000 | нет/No
4 | 3 | 15.10.2020 | 1 min | 4000 | нет/No
5 | 3 | 15.10.2020 | 6 sec | 5000 | да/Yes
Prepress 3rd coil to Al shell – 1mm per diameter.

## Slide 30: Drawing of the Devices for winding coil (scheme).
Design is ready, production until 06/2021

## Slide 31
Status Control Dewar and Transfer Line production

## Slide 32
3D model of Control Dewar
The PANDA control Dewar is designed to ensure helium delivery to the user in accordance with the flow scheme.
Chimney
- transfer line (Chimney) connecting the vacuum vessels of cryostat and control Dewar
Technologic volume
Vacuum barrier
Pamp station

## Slide 33
3D model of Control Dewar

## Slide 34
Flexible bus bar between cable way and current leads

## Slide 35
Power supply and energy extraction system

## Slide 36
Power Supply (Current Source – TDK-Lambda, Genesys+, 10V, 1500A)
New power supply

## Slide 37
Dump resistor sections assembling

## Slide 38
Dump resistor sections assembling
R insulation 2,5kV - ≥ 100 MOhm;
∑ R - 0, 09 Ohm;
Weight - 1020 kg.

## Slide 39
Preparation tests in BINP

## Slide 40
PANDA magnet, bld. 13. Area for cryogenic and coils tests and measurements of a magnetic field

## Slide 41
Thank you for your attention