## Slide 1: Accelerator Operations – 10.11.2020
Beam Time 2021
Shift Planning ongoing
on-call planning ongoing (56% finished, deadline for tech departments: Nov. 13th)
Shutdown
Cryring-Bake-out period ongoing without issues (HKR manned continuously until Nov. 27th)
generally going on as planned – exceptions:
  µ-Spill-Cavity - delayed at least till Jan.
  IPM ready for test mid December
  Faraday cups in transfer line ESR-Cryring are on critical path, completion is not secured
  oil leak in Q-kicker will be repaired after Dry-Run
General Device-Tests & cw-Demonstrator-Test starting next week, Dry-Runs starting subsequently
HKR-Roof renovation starts directly after Dry-Run  Exceptionally Cryring operation will be carried out from local control room and offices