## Slide 1: Unilac – 10.11.2020
Machine experiments with uranium beam, with pulsed gas stripper with hydrogen, desired for 7th to 12th April 2021. Possible? Accepted/confirmed?
Tunnel Septum UT2MUZ Repair: ongoing,
  Z-coil has still a ground fault after assembly, thicker Kapton foil ordered with delay, delivery appr. 20th Nov.
  X-coil repair ongoing (thin baffle plate to be exchanged, material delivered and milled)
A3DR8 new DT re-assembled inside tank (aligned, magnetic polarity checked), re-opened due to vacuum leak, closed again.
Gas stripper valve unit: after second time re-assembly another leakage, apparently the nitrogen feed hose vacuum under operation conditions will be checked during test period from 16th November on.
Leakage in UZA: beam diagnostics repaired and re-installed, pumped via bypass (stripping foils!), another leakage detected  to be fixed next.
Water in UZC vacuum, leakage of dipole baffle plate, to be repaired soon, like UZA
HLI bunker closed. RF tests started, but now again strange interlock errors.
TK4BB11: all assembly finished, TK closed. RF tests started. Frequency control unit new, needs commissioning.
TK/BK smoke shielding work 5.-16.10.2020 (GA) finished? Interrupted, residual work will be done in December (not in summer 2021).
RF topics
Rinsing HSI-RFQ de-ionised water cooling circuit (RF coupling loop and plungers) done, almost no dirt found, water flow okay.