## Slide 1: cw-LINAC, 17.11.2020
      CH2 @ IAP Frankfurt (optimisticaly scheduled for November 2020)
      Advanced demonstrator and CM2/delivery status:
        superconducting solenoids: Q4/2020!
        22 rf-windows for high power couplers: Budget 2020 and 2021 (prelim.) - ordering process started
      CH3-5 tendering shifted by another 6 months
      Prepration for further test (bath) cryostat at GSI
      Beam line set up@SH4 commissioning started at 16.11.2020
        dry commissioning (chopper controls, external interlock at UN6-FC, BB1-conditioning, …)
        beam commissioning
        beam test program (BSM vs. FFC, acceptance scan applying newly installed collimation system)
      APF-DTL design still ongoing
        Improved beam dynamics layout of IH1 - intertank section – IH2
        Preparation of technical specification