## Slide 1: Accelerator Operations – 17.11.2020
Beam Time 2021
Shift Planning ongoing
on-call planning ongoing (84% finished, 4 departments outstanding)
Covid-Lessons Learned workshop will take place in Dec. - invitation will be sent by OPE to department heads and experiment spokespersons
Shutdown
General Device-Tests & cw-Demonstrator-Test started (HKR manned continuously until Nov. 27th)
  §88 rad. safety check progressing well
  General Problems with UNILAC controls: HSI- und HLI-Chopper control unreliable, UNILAC Software Applications and Poti-boards are unstable
  temporarily strong noise due to renovation in surrounding buildings  H. Reckziegel and G. Stephan are requested to take care –> no feedback yet.
generally going on as planned – exceptions:
  µ-Spill-Cavity - cancelled  shifted towards 2021
  IPM ready for test mid December
  Faraday cups in transfer line ESR-Cryring are on critical path, completion is not secured
  oil leak in Q-kicker will be repaired after Dry-Run
Dry-Runs starting next week