## Slide 1: cw-LINAC, 08.12.2020
      CH2-test @ IAP Frankfurt postponed (earliest January 2020)
      Preparation of advanced test campaign with CM1-CH-cavities at HI-mainz (scheduled for Q1/2021)
      Advanced demonstrator and CM2/delivery status:
        superconducting solenoids: Q1/2020 (postponed)
        22 rf-windows for high power couplers ordered
        CH3-5 tendering shifted by another 6 months
      Prepration for further test (bath) cryostat at GSI
      Beam line set up@SH4 successfully commissioned, commissioning report in preparation
      BSM SAT scheduled for May/June 2021
      APF-DTL
        beam dynamics layout close to be finished
        techn. spec in preparation
        preliminary cost estimation requested