## Slide 1: cw-LINAC, 12.01.2021
      CH2-test @ Goethe Univ. Frankfurt again postponed due to (quasi) emergency operation
      Preparation of advanced test campaign with CM1-CH-cavities at HI-Mainz (scheduled for Q1/2021 => posponed due to (quasi) emergency operation
      Advanced demonstrator and CM2/delivery status:
        superconducting solenoids: Q1/2020 (postponed)
        22 rf-windows for high power couplers ordered 
        CH3-5 tendering shifted by another 6 months
        2 sc-rebunchers postponed 
        rf-amplifiers (CM1) not yet postponed 
      Prepration for further test (bath) cryostat at GSI
      Beam line set up@SH4 successfully commissioned, report in preparation
      BSM SAT scheduled for May/June 2021
      APF-DTL
        beam dynamics layout close to be finished
        techn. spec
        preliminary cost estimations requested
        tender process should start in February 2021
        high power rf test of IH-cavities (mid of 2022) in discussion
New test cryostat (CRYOWORLD Co.)