## Slide 1: Unilac – 19.1.2021
UNILAC tunnel closed since Friday 8th January, TK closed on Monday 11th January.
HSI-RFQ “re-calibration” by software before beam commissioning: ordered on Monday 18th.
Tunnel Septum UT2MUZ/MUX:
  Installation finished incl. commissioning.
  New coil spare part ordering started.
Leakage in ZE-branch: all re-assembled, pumping after transformer exchange in Experimental Hall EH.
A4 / 10 Hz problem: new software version checked on Thursday 14th January. Okay!
RF Topics:
  Commissioning ongoing
    A1 working, Alvarez 6…7 Volt, HIS-RFQ 7.04 Volt reached