## Slide 1: cw-LINAC, 26.01.2021
      CH2-test @ Goethe Univ. Frankfurt again postponed due to (quasi) emergency operation
      Preparation of advanced test campaign with CM1-CH-cavities at HI-Mainz scheduled for Feb. 2021
      Advanced demonstrator and CM2/delivery status:
        superconducting solenoids: Q1/2021 
        25 rf-windows for high power couplers delivery in Q3/21 
        CH3-5 tendering shifted by another 6 months
        2 sc-rebunchers: * Rf-test 04_21 
        * high power Rf-testing w/o He-mantel 08_21 
        * final delivery 10_21 
        cryostat 1: Q2/2021 
        cryostat 2: Q3/2021 
        rf-amplifiers (CM1): * FOS: Q1/2021 
        * series: Q2/2021 
      Preparation for a further test (bath) cryostat at GSI
      BSM SAT scheduled for May/June 2021
      Cryostat 1 (including sc-solennoids) commissioning with beam in June 2021?
      APF-DTL
        recently: final beam dynamics layout for IH2, techn. spec, preliminary cost estimations
        Q1/2021 planned: start of tender process
        high power rf test of IH-cavities (mid of 2022) in discussion
      Rf-test of 6kW-cw-quarter wave buncher cavity in preparation