## Slide 1: and HITRAP
Frank Herfurth
CRYRING@ESR
Feb-02, 2021
CRYRING@ESR
  ECooler - cool down of magnet started
  Vacuum controls hiccup being solved still this week
    need discussion on roles: MK - Shutdown Planning - Expert Groups
  apart from small (normal) issues ready for commissioning with beam starting now
  Operator training scheduled for Thu/Fri this week
  preparation of experiments installations ongoing, scheduling and planning difficult (communication and COVID)
  weak spots for upcoming operation period:
    archiving not ready to use (vacuum, cryo, rings signals etc.) – workaround: Grafana, InfluxDB on own IT server, but no 24/7 support possible
    digitizer not supported 24/7 (kicker, bumper, magnet PS) – workaround: network enabled scopes, beam diagnostics tools
HITRAP
  Electron/Ion transmission/storage test at the cooling Penning trap ongoing, increased # of electrons slightly
  refit work started (IH in-coupling loop will be repaired) ! not all resource issues solved yet ! (MSP Schedule lasts 1.5 years after all resources made available)
  untimed and unprepared GSI power cuts caused weeks! of additional effort in the last 6 months