## Slide 1
PANDA Collaboration Meeting 21/1
Status production PANDA solenoid
E.Pyata, S.Pivovarov, M.Kholopov, M.Azimbaev BINP, Novosibirsk

## Slide 2
The main milestones of production of the PANDA solenoid magnet
The scope of delivery includes:
Magnetic and engineering design of the magnet including tools and support;
Production and delivery of the magnet (consisting of yoke, cold mass and cryostat, alignment components, proximity cryogenics, support frame and platform beams) and all tools;
Power converter and quench protection and instrumentation.
Item | Date
Start contract | 03/2017
Control assembling of the Yoke of solenoid at the BINP site | 09/2020
Magnetic tests of the PANDA solenoid including safety system and electrical components at BINP (additional contract) | 12/2021 - 05/2022
Assembling and tests at the FAIR site | 
Assembling of the magnet at Darmstadt | 06/2024
Acceptant tests at FAIR | 11/2024
Installation of the PANDA solenoid magnet at worked position and final acceptance tests | 01-05/2025

## Slide 3
PANDA solenoid magnet, BINP responsibility
Power supply and energy extraction system
Cable channel
Control Dewar box
Solenoid and yoke
Frame of Yoke
Dump resistor
Energy Extraction Rack
Power Supply

## Slide 4: 3D model of the Magnet and Control Dewar.
Control Dewar box
Cryostat and Coil

## Slide 5
Development of the PANDA solenoid magnet
Name of item | Status of work
Yoke and frame | Final machining 5 July 2020 1st control assembling 09/2020 2st control assembling and FAT 12/2020
Cryostat of solenoid & Cold mass | Design and technological development are ready, delivery raw materials from BINP to the plant 03/2021 Start production 04/2021 Delivery Cryostat of solenoid & Cold mass to BINP 09/2021
Conductor purchasing | Development work, Contract production of strands singned 18.08.2020
Control Dewar box | Preliminary design October 2020 – OK, FDR – 05/2021
PANDA solenoid power cabling | Design is ready, production
Power supply and energy extraction system | Detail design is ready, purchasing power convertors & components. Production
Magnet safety system | in process

## Slide 6
Status of the PANDA cryostat and cold mass production

## Slide 7
The main milestones of the Cryostat production
Name of milestone |  | Date 2017/10
FDR of the Cryostat |  | 08/02/2019
FDR of the Cold Mass |  | 17/04/2019
Status production |  | 
Cryostat stands for assembling solenoid and magnet Cold Mass | Contract production was signed 18.08.2020 | 
 | Purchasing raw material 03/2021 – 99% Delivery raw material to subcontractor – 03/2021 | 
 | Contract: delivery to BINP 09/2021 | 

## Slide 8
Status of the PANDA yoke production

## Slide 9: 3D model of the Yoke and Frame.
Control assembling
1st - 09/2020
2nd - 11-12/2020
Frame
Yoke

## Slide 10
The main milestones of the yoke production
Name of milestone |  | Date 2017/10 | Comments
Production of the all barrel octants |  | 04/2020 | Ready
Production of the frame and beams |  | 04/2020 | Ready
Production of the doors | Upstream | 05/2020 | Ready
 | Downstream | 06/2020 | Ready
Control assembling at SET |  | 07– 09/2020 | Ready
Finalization of the parts |  | 08 - 10/2020 | Ready
Control assembling at SET second |  | 11– 12/2020 | Ready
Assembling of the Yoke at BINP |  | ? | Estimated 11/2021

## Slide 11: Assembling of the Yoke 09/2020

## Slide 12: Assembling of the Yoke 09/2020

## Slide 13: Assembling of the Yoke

## Slide 14: Assembling of the Yoke 11-12/2020

## Slide 15: Assembling of the Yoke 11-12/2020

## Slide 16: Assembling of the Yoke
Installed 10 support for detectors of a laser tracker.
Built an axis of the yoke and 3D map of elements by a laser tracker.
Measuring surfaces of the octants and wings we can do correction each part of the frames and barrel part of the yoke.
We plan to install about 30 the same support to do assembly of the yoke more quickly and suitable/

## Slide 17: Disassembling of the Yoke and delivery to BINP

## Slide 18
Status of the PANDA conductor development/ procurement

## Slide 19
Conductor.
Status of the PANDA conductor development/ procurement
BINP/ VNIINM Bochvar/ VNIIKP/ Saransk cable optic (SarKO)
Rutherford cable co-extrusion/ conklad in a pure Al
Production1000m Cu Rutherford cable for tests in SARKO - 03-04/ 2020 (in BINP)
Tests in SARKO, 1000m Cu Rutherford cable - 04-05/ 2021
Contracts for PANDA NbTi strands production, VNIINM - signed 09/ 2020
Production strands VNIINM for central coil - 09/2021
Production strands VNIINM for up/downstream coils - 12/2021
PANDA Rutherford cables production, VNIIKP
for central coil - 12/2021
for up/downstream coils - 03/2022
Production PANDA conductor BINP/SARKO - 01 - 05/ 2022

## Slide 20
PANDA conductor
Longitudinal section of the cryostat with cold mass.
Cold mass cross-section.
Cross-section of the conductor.
Conductor mechanical and electrical parameters.
Thickness (after cold work) at 300 K | mm | 7.93 | ± 0.03
Width (after cold work) at 300 K | mm | 10.95 | ± 0.03
Critical current (at 4.2 K, 5 T) | A | > 14690 | 
Critical current (at 4.5 K, 3 T) | A | > 16750 | 
Overall Al/Cu/sc ratio |  | 10.5/1.0/1.0 | 
Aluminum RRR (at 4.2 K, 0 T) |  | > 1000 | 
Al 0.2% yield strength at 300 K | MPa | > 30 | 
Rutherford cable, 8 strands, extruded in Al matrix

## Slide 21
8 pieces of the samples of PANDA conductor produced with different tools were tested for a shear strength. Results are 62,5 – 85,3 MPa. Specified value of a shear strength is ≥20 Mpa.
Status of the PANDA conductor development/ procurement
Photo of the samples of PANDA conductor
Scheme of shear strength measurement

## Slide 22
Development works with a prototype Rutherford cable (Cu or NbTi) to co-extrusion/ conklad in a pure Al 995 and Aluminum A95
Oven for preheating a Rutherford cable.
Temperature - 200 ÷ 450°C;
Shielding gas – N2
Preparation a contract BINP/SARKO to development a technology production a conductor with preheating and creating intermetallic connection Al/Cu.
Status of the PANDA conductor development/ procurement

## Slide 23
Status of the PANDA coils production

## Slide 24
The main milestones of the coils production
Status production | 
Cryostat and stands for assembling solenoid and magnet | Design is ready, technological development, Call for tender
Cold Mass | Design is ready, technological development, Call for tender
First Prototype of the Coil | 11/2019
Second Prototype of the Coil | 03/2020
Third Prototype of the Coil | 08/2020
Tooling for winding Coil (and Prototype) | 11/2019
Tooling for impregnation of Coil (and Prototype)/modified | 11.2019/03.2020
Prepress prototype coil into cold mass | 10/2020
Tooling for winding and impregnation of PANDA Coil | Design and technological development are ready, Call for tender 03/2021

## Slide 25: The Prototype of the Coil (3pcs.)
OD = 1m,
h=180 mm
Conductor:Al
10,85 мм x 7.93 мм,
6 layers
16 turns
Design is ready, 2 prototype produced

## Slide 26: The Prototype of the Coil (3pcs.)
Preparation prestress procedure of coil
to an aluminum shell
For prototype heater:
Length - 17m;
Power - 3,5 kW;
Cross section - 24 x 3 mm;
Quantity - 1 pc.
For PANDA coil
Length - 36m;
Power - 3,0 kW;
Cross section - 24 x 3 mm;
Quantity - 8-9 pc.

## Slide 27
Production of the coil prototype

## Slide 28
Development works with a prototype Rutherford conductor.
Material is Aluminum A95
Third prototype
Electrical tests 3rd prototype - OK;
Procedure heating Al shell with control uniformity distribution of temperature, temperature rate, shell expansion measurement - OK;
Assembling coil and Al shell with prestress - OK;
Mechanical test coil assembling – OK, ≥2500 kg shear strength;
Destroy tests;
Thermal shock tests LN2;
Checking quality of an epoxy penetration, mechanical tests;
Analysis of the manufacturing quality of the third prototype;
Preparation production of the 4th prototype
Status of the PANDA coil development/ production

## Slide 29: Drawing of the Devices for winding coil (scheme).
Design is ready, production until 09/2021

## Slide 30
Status Control Dewar and Transfer Line production

## Slide 31
3D model of Control Dewar
The PANDA control Dewar is designed to ensure helium delivery to the user in accordance with the flow scheme.
Chimney
- transfer line (Chimney) connecting the vacuum vessels of cryostat and control Dewar
Technologic volume
Vacuum barrier
Pamp station

## Slide 32
3D model of Control Dewar

## Slide 33
Power supply and energy extraction system

## Slide 34
Power Supply (Current Source – TDK-Lambda, Genesys+, 10V, 1500A)
New power supply

## Slide 35
Dump resistor sections assembling

## Slide 36
Dump resistor sections assembling
R insulation 2,5kV - ≥ 100 MOhm;
∑ R - 0, 1 Ohm;
Weight - 1020 kg.

## Slide 37
Preparation tests in BINP

## Slide 38
Flow scheme KEDR and PANDA cryogenic system

## Slide 39
PANDA magnet, bld. 13. Area for cryogenic and coils tests and measurements of a magnetic field

## Slide 40
Thank you for your attention