## Slide 1: Schedule for the pbar Installation 28.4.2021 K. Knie

## Slide 2: Access to Building 6c
From Building 4 along the beamline: long way, to narrow for dipole if HEBT is installed already
From Building 50 (APPA) 60 cm step, 2 beamlines to cross
From elevator in Building 6c limited to 15 t
From Building 7 (CR) beamlines to cross, building 7 not constructed at start of installation

## Slide 3: Access to Building 6c
From Building 4 along the beamline: long way, to narrow for dipole if HEBT is installed already
From Building 50 (APPA) 60 cm step, 2 beamlines to cross
From elevator in Building 6c limited to 15 t
From Building 7 (CR) beamlines to cross, building 7 not constructed at start of installation

## Slide 4: 2-Step-Installation
Step 1 using elevator in 6c: Targetstation, Horn, Dump
Step 2 from building 7 PS01 beamline
Commissioning w. beam:
Dipole needed, otherwise dump will be missed! Where to put neg. pions?

## Slide 5
Horn needs to be tested with full current (400 kA) for 105-106 pulses to detect failures due to fatigue. Rep. rate is 0.1 Hz, i.e. the testing phase will last weeks to months.
Operation with beam is strongly recommended only after these tests, because activation does not allow hands-on maintenance.
During these test the tunnel will be not accessible, i.e. no installation of the beamline will be possible.
Schedule for installation

## Slide 6
Horn needs to be tested with full current (400 kA) for 105-106 pulses to detect failures due to fatigue. Rep. rate is 0.1 Hz, i.e. the testing phase will last weeks to months.
Operation with beam is strongly recommended only after these tests, because activation does not allow hands-on maintenance.
During these test the tunnel will be not accessible, i.e. no installation of the beamline will be possible.
Schedule for installation

## Slide 7
Summary
Installation of target, horn and dump via elevator in 6c.
Commissioning of these components without beam after installation.
During commissioning period of horn (at least 6 months) access to tunnel is restricted.
As soon as access from building 7 is possible, installation of pbar separator (PS01 + TCR1 beamlines) from target to CR.
Components should be made available according to the installation order.
Commissioning with beam after installation of whole pbar separator.
If commissioning of magnetic horn is delayed and building 7 is early, this planning has to be reconsidered!