## Slide 1
PANDA Collaboration Meeting 21/1
Status production PANDA solenoid
E.Pyata, S.Pivovarov, M.Kholopov, M.Azimbaev BINP, Novosibirsk

## Slide 2
The main milestones of production of the PANDA solenoid magnet
The scope of delivery includes:
Magnetic and engineering design of the magnet including tools and support;
Production and delivery of the magnet (consisting of yoke, cold mass and cryostat, alignment components, proximity cryogenics, support frame and platform beams) and all tools;
Power converter and quench protection and instrumentation.
Item | Date
Start contract | 03/2017
Control assembling of the Yoke of solenoid at the Novosibirsk plant site | 09/2020
Magnetic tests of the PANDA solenoid including safety system and electrical components at BINP (additional contract) | 06/2023 - 05/2024
Assembling and tests at the FAIR site | 
Assembling of the magnet at Darmstadt | 06/2024
Acceptant tests at FAIR assembling area | 11/2024
Installation of the PANDA solenoid magnet at worked position and final acceptance tests | 01-05/2025

## Slide 3
PANDA solenoid magnet, BINP responsibility
Power supply and energy extraction system
Cable channel
Control Dewar box
Solenoid and yoke
Frame of Yoke
Dump resistor
Energy Extraction Rack
Power Supply

## Slide 4: 3D model of the Magnet and Control Dewar.
Control Dewar box
Cryostat and Coil

## Slide 5
Development of the PANDA solenoid magnet
Name of item | Status of work
Yoke and frame | Produced, FAT 12/2020, now all parts in BINP
Cryostat of solenoid & Cold mass | Design and technological development are ready, delivery raw materials from BINP to the plant 03/2021 – OK; Start production 19/04/2021 Delivery Cryostat of solenoid & Cold mass to BINP 09/2021
Conductor purchasing | Development work, Contract production of strands singned 18.08.2020
Control Dewar box | Preliminary design October 2020 – OK, FDR – 05-08/2021
PANDA solenoid power cabling | Design is ready, production
Power supply and energy extraction system | Detail design is ready, purchasing components. Power convertors 1kA in BINP. Production racks.
Magnet safety system | in process

## Slide 6
Status of the PANDA cryostat and cold mass production

## Slide 7
The main milestones of the Cryostat production
Name of milestone |  | Date 2017/10
FDR of the Cryostat |  | 08/02/2019
FDR of the Cold Mass |  | 17/04/2019
Status production |  | 
Cryostat stands for assembling solenoid and magnet Cold Mass | Contract production was signed 18.08.2020 | 
 | Purchasing raw material 03/2021 – 99% Delivery raw material to subcontractor – 03/2021 Start production – 04/2021 | 
 | Acceptance at the plant – 08/2021 | 
 | Contract: delivery to BINP 09/2021 | 

## Slide 8
Status of the PANDA yoke production

## Slide 9: 3D model of the Yoke and Frame.
Control assembling
1st - 09/2020
2nd - 11-12/2020
Frame
Yoke

## Slide 10: Assembling of the Yoke
Installed 10 support for detectors of a laser tracker.
Built an axis of the yoke and 3D map of elements by a laser tracker.
Measuring surfaces of the octants and wings we can do correction each part of the frames and barrel part of the yoke.
We plan to install about 30 the same support to do assembly of the yoke more quickly and suitable
provide control dimension tests after delivery parts of the Yoke to BINP.

## Slide 11: Disassembling of the Yoke and delivery to BINP 01-02/2021

## Slide 12
Status of the PANDA conductor development/ procurement

## Slide 13
Conductor.
Status of the PANDA conductor development/ procurement
BINP/ VNIINM Bochvar/ VNIIKP/ Saransk cable optic (SarKO)
Plan works with Saransk cable- optic
Production1000m Cu Rutherford cable for tests in SARKO - 03-04/2020 (in BINP storage)
1000m Cu Rutherford cable, Aluminum A95 and preheating Cu cable 200-250°C - 06-07/ 2021
600m Cu Rutherford cable, Aluminum A995 and preheating Cu cable 200-250°C - 10-12/ 2021
80m Nb/Ti/Cu Rutherford cable, Aluminum A995 and preheating Cu cable 200-250°C - 10-12/ 2021
Production strands
Contracts for PANDA NbTi strands production, VNIINM - signed 09/ 2020
Production strands for technologic works in VNIIKP - 30/05/2021
Production strands VNIINM for central coil - 09/2021
Production strands VNIINM for up/downstream coils - 12/2021
Tests samples of Nb/Ti/Cu Rutherford cable in Aluminum A995 matrix (and in CERN) - 12/ 2021-01/2022
PANDA Rutherford cables production, VNIIKP
technologic works in VNIIKP with PANDA strands to produce PANDA Rutherford cable – 09-11/2021
for central coil - 12/2021
for up/downstream coils - 03/2022
Production PANDA conductor BINP/SARKO - 01 - 05/ 2022

## Slide 14
PANDA conductor
Longitudinal section of the cryostat with cold mass.
Cold mass cross-section.
Cross-section of the conductor.
Conductor mechanical and electrical parameters.
Thickness (after cold work) at 300 K | mm | 7.93 | ± 0.03
Width (after cold work) at 300 K | mm | 10.95 | ± 0.03
Critical current (at 4.2 K, 5 T) | A | > 14690 | 
Critical current (at 4.5 K, 3 T) | A | > 16750 | 
Overall Al/Cu/sc ratio |  | 10.5/1.0/1.0 | 
Aluminum RRR (at 4.2 K, 0 T) |  | > 1000 | 
Al 0.2% yield strength at 300 K | MPa | > 30 | 
Rutherford cable, 8 strands, extruded in Al matrix

## Slide 15
Development works with a prototype Rutherford cable to co-extrusion/ conklad in a pure Al 995 and Aluminum A95
Oven for preheating a Rutherford cable was produced and tests with a prototype Rutherford cable are carried out.
Temperature oven - 250 ÷ 450°C;
Temperature of a prototype Rutherford cable with 2m/min velocity of the cable during crossing the oven - 170 ÷ 250°C;
Shielding gas – N2 / Ar
Technical Specification and conditions of the contract with SARKO are agreed. Preparation SARKO extrusion line to development of technology production of the PANDA conductor with preheating and creating intermetallic connections Al/Cu.
Status of the PANDA conductor development/ procurement

## Slide 16
Status of the PANDA coils production

## Slide 17
The main milestones of the coils production
Status production | 
Cryostat, Cold mass and stands for assembling solenoid and magnet | Design and technological development are ready Production from 19/04/2021 Delivery to BINP – 09/2021
Second Prototype of the Coil | 03/2020
Third Prototype of the Coil | 08/2020
4th Prototype of the Coil | 05-06/2021
Tooling for winding Coil (and Prototype) | Used from 11/2019
Tooling for impregnation of Coil (and Prototype)/modified | Used from 03.2020
Prepress prototype coil into cold mass | tested 10/2020
Tooling for winding and impregnation of PANDA Coil | Design and technological development are ready, Call for tender 04/2021 Delivery to BINP according to contract – 10/2021

## Slide 18: The Prototype of the Coil (3pcs.)
OD = 1m,
h=180 mm
Conductor:Al
10,85 мм x 7.93 мм,
6 layers
16 turns
Design is ready, 3 prototype produced

## Slide 19: The Prototype of the Coil (3pcs.)
Preparation prestress procedure of coil
to an aluminum shell
For prototype heater:
Length - 17m;
Power - 3,5 kW;
Cross section - 24 x 3 mm;
Quantity - 1 pc.
For PANDA coil
Length - 36m;
Power - 3,0 kW;
Cross section - 24 x 3 mm;
Quantity - 8-9 pc.

## Slide 20
Production of the coil prototype

## Slide 21
Development works with a prototype Rutherford conductor.
Material is Aluminum A95
Third prototype
Electrical tests 3rd prototype - OK;
Procedure heating Al shell with control uniformity distribution of temperature, temperature rate, shell expansion measurement - OK;
Assembling coil and Al shell with prestress - OK;
Mechanical test coil assembling – OK, ≥2500 kg shear strength;
Destroy tests;
Thermal shock tests LN2 - OK;
Checking quality of an epoxy penetration, mechanical tests;
Analysis of the manufacturing quality of the third prototype;
Preparation production of the 4th prototype
Status of the PANDA coil development/ production

## Slide 22: Drawing of the Devices for winding coil (scheme).
Design is ready, production until 10/2021

## Slide 23
Status Control Dewar and Transfer Line production

## Slide 24
3D model of Control Dewar
The PANDA control Dewar is designed to ensure helium delivery to the user in accordance with the flow scheme.
Chimney
- transfer line (Chimney) connecting the vacuum vessels of cryostat and control Dewar
Technologic volume
Vacuum barrier
Pamp station

## Slide 25
3D model of Control Dewar

## Slide 26
Preparation tests in BINP

## Slide 27
Flow scheme KEDR and PANDA cryogenic system

## Slide 28
PANDA magnet, bld. 13. Area for cryogenic and coils tests and measurements of a magnetic field

## Slide 29
Thank you for your attention