## Slide 1: Collector Ring express status report
Dmitry Shwartz
on behalf of the BINP team
7th BINP-FAIR Collaboration Coordination Workshop, online, 9 Nov 2021

## Slide 2: Collector Ring: huge work, low priority
Beam from
p_bar & SFRS
Extraction to HESR
RF debunchers
Inj/Extr kickers
Stochastic cooling
pickups
Stochastic cooling
kickers
ToF detector
Inj septa
Extr septa
Dipole
NQ
EWQ
SWQ
WQ
Sextupole
Pickup
CR
HESR
Beam scraper
Scintillating screen

## Slide 3: FoS Dipole: FAT ongoing, SAT on the horizon
Dipole @ magnetic measurements
Field quality: (preliminary) within spec
Transport
frames: production ongoing
QPC Prototype-1, working very well routinely at magnetic measurements stand
QPC Prototype-2, assembly is ongoing, 1st section under testing.
To be delivered for FoS dipole SAT at GSI/FAIR site
FAT has been started, a dozen of non-critical remarks were obtained
Talks by
A.Starostenko, Wed, 16:00
D.Senkov, Thu, 14:20

## Slide 4: Magnet and vacuum systems
CR/TCR1/pbar sextupole: test laminas stamped; all the tooling is ready; we expect to get FoS magnet by the end of 2021
Wide quadrupole stamping tooling assembly
Serial (2nd) dipole parts production
Narrow quadrupole test laminas stamped, CDR ongoing, FDR underway
Reworked vacuum chambers prototypes, waiting for final vacuum testing

## Slide 5: Other highlights
Injection septa: CDR ongoing, FDR underway (talk by P.Shatunov, Wed, 16:30)
Kickers: HV PS, ferrites and feedthroughs delivered to Novosibirsk; Power Supply – new concept (talk by A.Kasaev, I.Koop, Wed, 17:00)
Diagnostics: Scrapers and Stoppers FDRs released (talk by Yu.Rogovsky, Thu, 14:40)
Power converters: Dipoles PC nearly tendered via FAIR (talk by D.Senkov, Thu, 14:20)
Infrastructure: water distribution concept proposed by M.Chilikin & A.Rahimov (talk by T.Ziglasch, Thu, 15:00)
ITEP, Moscow: Schottky Pick-Up CDR released

## Slide 6: GSI in-kind: good progress
SC Kicker: CDR and contract with FZJ
are underway
RF debuncher:
All 5 RF systems
delivered to GSI
SC Pick-Up: components production
ongoing (vacuum tanks, Ag-coated
foils, slotline electrodes, etc)

## Slide 7
Thank you
for your attention!