## Tabelle1
Drawing number | Type | Action required by | Status
FHTQS056AS | 3D Model | BINP | GSI informed about ECR0469 on 08.04.2020
FHTQS157AS | 3D Model | BINP | GSI informed about ECR0469 on 08.04.2020
FHTKV030AS | 3D Model | BINP | GSI sent comments on 09.09.2019 (stand is longer and wider than specified)
FHTKV010AS | 3D Model | Nobody | Was rejected by GSI, the version uploaded on 20.08.2019 remains released
FHTQS360AS | 3D Model | Nobody | Approved by GSI
FHTMV010AS | technical drawings | GSI | BINP sent response on 05.10.
FHTMV066AS | technical drawings | GSI | BINP sent response on 05.10.
FHTMV062AS | technical drawings | GSI | BINP sent response on 05.10.
FHTMV064AS | technical drawings | GSI | BINP sent response on 05.10.
FHTMH160AS | technical drawings | GSI | BINP sent response on 05.10.
FHTMV068AS | technical drawings | GSI | BINP sent response on 05.10.
FHTMV034AS | technical drawings | GSI | BINP sent response on 05.10.
FHTMH065AS | technical drawings | GSI | BINP sent response on 05.10.
FHTQS217AS | technical drawings | BINP | GSI sent response on 05.08.2021
FHTQS044AS | technical drawings | BINP | GSI sent response on 05.08.2021
FHTQS212AS | technical drawings | BINP | GSI sent response on 05.08.2021
FHTKH015AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTKV030AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTKV020AS | technical drawings | BINP | GSI sent response on 09.02.2021
FHTKH032AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTKH060AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTKV010AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTKH034AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTKH039AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTKH049AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTKH047AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTDI041AS | technical drawings | BINP | GSI sent response on 09.02.2021
FHTDI037AS | technical drawings | BINP | GSI sent response on 09.02.2021
FHTKH018AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTDI061AS | technical drawings | BINP | GSI sent response on 09.02.2021
FHTKV014AS | technical drawings | BINP | Drawings need to be adjusted for shifted connection box
FHTDI038AS | technical drawings | BINP | GSI sent response on 09.02.2021
FHTDI039AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTKH038AS | technical drawings | BINP | GSI sent response on 09.02.2021
FHTKH142AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTKV012AS | technical drawings | BINP | GSI sent response on 20.07.2020
FHTKH001AS | technical drawings | BINP | GSI accepted drawings of steerer, but did not receive drawings of stand
FHTDI009AS | technical drawings | BINP | GSI sent response on 05.08.2021
FHTMH037AS | technical drawings | GSI | BINP sent response on 14.09.2021
FHTMH033AS | technical drawings | GSI | BINP sent response on 14.09.2021
FHTDI472AS | technical drawings | BINP | GSI sent response on 09.02.2021
FHTDI454AS | technical drawings | BINP | GSI accepted Model version E, latest received set of drawings is B
FHTKH026AS | technical drawings | BINP and GSI | There is exchange on six-strut
FHTKV022AS | technical drawings | BINP | GSI sent response on 09.02.2021
FHTQS137AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS139AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS133AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS135AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS141AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS047AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS049AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS051AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS053AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS056AS | technical drawings | BINP and GSI | GSI needs to receive and approve 3D Model first
FHTQS155AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS120AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS157AS | technical drawings | BINP and GSI | GSI needs to receive and approve 3D Model first
FHTQS158AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS160AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS162AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS165AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS323AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS146AS | technical drawings | BINP | GSI accepted drawings quad11 general design, but did not receive drawings of stand
FHTQS109AS | technical drawings | BINP | GSI only received drawings of version A, the current model is B
FHTQS008AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTQS035AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTQS181AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTQS183AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTQS185AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTQS195AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTQS187AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTQS189AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTQS191AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTQS193AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTQS114AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTQS208AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTDI040AS | technical drawings | BINP | GSI accepted drawings of steerer, but did not receive drawings of stand
FHTKH036AS | technical drawings | BINP | GSI accepted drawings of steerer, but did not receive drawings of stand
FHTDI011AS | technical drawings | BINP | GSI responded on 27.09.2021
FHTKV001AS | technical drawings | BINP | GSI accepted drawings of steerer, but did not receive drawings of stand
FHTKH002AS | technical drawings | BINP | GSI responded on 27.09.2021
FHTKH012AS | technical drawings | BINP | GSI responded on 27.09.2021
FHTKH014AS | technical drawings | BINP | GSI responded on 27.09.2021
FHTKH011AS | technical drawings | BINP | GSI accepted drawings of steerer, but did not receive drawings of stand
FHTDI089AS | technical drawings | BINP | GSI responded on 27.09.2021
FHTVA214AS | technical drawings | BINP | GSI accepted drawings of steerer, but did not receive drawings of stand
FHTQS363AS | technical drawings | BINP | BINP needs to update the drawings of the general Quad2 design and send drawings of the stand
FHTKH157AS | technical drawings | BINP | GSI responded on 27.09.2021
FHTDI436AS | technical drawings | BINP | GSI responded on 27.09.2021
FHTDI440AS | technical drawings | BINP | GSI responded on 27.09.2021
FHTQS360AS | technical drawings | BINP | GSI approved 3D Model on 17.08.2021
S13 steerers | 3D Model | GSI | GSI needs to write ECR to use CR model