## Slide 1
CBM SC magnet Nov. 2021
Status:
 Official confirmation of delivery date 04/23 
Production of yoke ongoing 
Production of power supply ongoing 
Layout of cryogenic system almost final
Preparation of mockup coil production (?)
Detailed calculations and test of support strut (?)
Magnet control system: discussion started
1
Peter Senger, 7th BINP-FAIR Workshop, Nov. 7 – 12, 2021

## Slide 2
Cryogenic system
Some of the open questions:
Calculation of safety valves
Number of safety valves
Supports of the transfer line
Number of sensors
Finalization of instrumentation list
Dimensioning and fixation of the 3 heaters
…

## Slide 3
Mockup coils
Production of 2 prototype coils with insulated copper wire in order to test:
Winding tools and winding procedure
Impregnation: epoxy compound, temperature, size of channels, isolation layers, …

## Slide 4
CBM SC magnet: Coil design

## Slide 5
FEM model of the single ring coil strut (J. Lühning)
coil
inner GFRP cylinder
BINP copper ring
warm plate
stress peaks in GFRP cylinders
inner GFRP cylinder
vM-stress > 80 MPa
warm plate
vM-stress > 80 MPa
radial degree-of-freedom constrained (no relative movement)
Important parameter is the thickness t of the GFPR cylinder:
Critical load ≈ t3
Heat flow ≈ t
Present design:
t =12 mm

## Slide 6
Delivery to GSI 04/23
FDR Cryogenics ?
FDR coils 12/21 ?
Coil construction
time critical
CBM SC magnet time line

## Slide 7
CBM SC magnet: Crucial next steps
Preparation of the FDR of the cryogenic system
(branch box, transfer line, and cryostat).
Impregnation tests with a realistic mockup coil
Single ring support strut (GFRP):
- confirmation of the buckling stress calculations
- stability test with a 1000 t press
- if required: improving stability
Magnet control system to be linked to the GSI
control systems for cryogenics and vacuum.
Risk: Stability of GFPR coil support
Critical path: Coil production