## Slide 1
PANDA Collaboration Meeting 21/3 27/11/2021
Status production PANDA solenoid
E.Pyata, S.Pivovarov, M.Kholopov, M.Azimbaev BINP, Novosibirsk

## Slide 2
The main milestones of production of the PANDA solenoid magnet
The scope of delivery includes:
Magnetic and engineering design of the magnet including tools and support;
Production and delivery of the magnet (consisting of yoke, cold mass and cryostat, alignment components, proximity cryogenics, support frame and platform beams) and all tools;
Power converter and quench protection and instrumentation.
Item | Date
Start contract | 03/2017
Control assembling of the Yoke of solenoid at the Novosibirsk plant site | 09/2020
Magnetic tests of the PANDA solenoid including safety system and electrical components at BINP (additional contract) | 06/2023 - 05/2024
Assembling and tests at the FAIR site | 
Assembling of the magnet at Darmstadt | 06/2024
Acceptant tests at FAIR assembling area | 11/2024
Installation of the PANDA solenoid magnet at worked position and final acceptance tests | 01-05/2025

## Slide 3
PANDA solenoid magnet, BINP responsibility
Power supply and energy extraction system
Cable channel
Control Dewar box
Solenoid and yoke
Frame of Yoke
Dump resistor
Energy Extraction Rack
Power Supply

## Slide 4: 3D model of the Magnet and Control Dewar.
Control Dewar box
Cryostat and Coil

## Slide 5
Development of the PANDA solenoid magnet
Name of item | Status of work
Yoke and frame | Produced, FAT 12/2020, now all parts in BINP
Cryostat of solenoid & Cold mass | in production Delivery Cryostat of solenoid & Cold mass to BINP 03/2022
Conductor purchasing | Development work, Contract production of strands singned 18.08.2020 Preparation contract for a Rutherford cable production 11/2021
Control Dewar box | Preliminary design October 2020 – OK, FDR – Q1/2022
PANDA solenoid power cabling | Design is ready, production
Power supply and energy extraction system | Detail design is ready, purchasing components. Power convertors 1kA in BINP. Production racks.
Magnet safety system | in process

## Slide 6
Status of the PANDA cryostat and cold mass production

## Slide 7
The main milestones of the Cryostat production
Name of milestone |  | Date 2017/10
FDR of the Cryostat |  | 08/02/2019
FDR of the Cold Mass |  | 17/04/2019
Status production |  | 
Cryostat stands for assembling solenoid and magnet Cold Mass | Contract production was signed 18.08.2020 | 
 | Purchasing raw material 05/2021 – OK Delivery raw material to subcontractor – 03/2021 Start production – 04/2021 | 
 | Acceptance at the plant – 12/2021- 03/2022 | 
 | Contract: delivery to BINP 03/2022 | 

## Slide 8
Status of the PANDA conductor development/ procurement

## Slide 9
PANDA conductor
Longitudinal section of the cryostat with cold mass.
Cold mass cross-section.
Cross-section of the conductor.
Conductor mechanical and electrical parameters.
Thickness (after cold work) at 300 K | mm | 7.93 | ± 0.03
Width (after cold work) at 300 K | mm | 10.95 | ± 0.03
Critical current (at 4.2 K, 5 T) | A | > 14690 | 
Critical current (at 4.5 K, 3 T) | A | > 16750 | 
Overall Al/Cu/sc ratio |  | 10.5/1.0/1.0 | 
Aluminum RRR (at 4.2 K, 0 T) |  | > 1000 | 
Al 0.2% yield strength at 300 K | MPa | > 30 | 
Rutherford cable, 8 strands, extruded in Al matrix

## Slide 10
Conductor.
Status of the PANDA conductor development/ procurement
BINP/ VNIINM Bochvar/ VNIIKP/ Saransk cable optic (SarKO)
Production strands
VNIINM
Contracts for PANDA NbTiCu strands production - signed 09/ 2020
Production strand for technologic works in VNIIKP, 1600m length - 30/05/2021
  Production stopped before final operation - 24/05/2021
  Control tests cut simples of the prefinished strand - in process up to 28/06/2021
  correction ?? of the prefinished strand - 1/07/2021
  Production 1600 m strand for technologic works
  and part for strands for central coil - 20/07/2021
Production strands for central coil - 12/2021
Production strands for up/downstream coils - 03/2022

## Slide 11
Conductor.
Production strands
Producer: “A.A. Bochvar High-technology Research Institute of Inorganic Materials” (JSC "VNIINM").
Protocol measurements 01-400/423 from 29.09.2021/18.10.2021
Superconductive NbTi strand PANDA solenoid
Strand cross section
Parameter | Unit | Certified |  | 1-C2-1P-1-21/1 > 1400 m | 1-C2-1P-1-21/2-1-1-2 > 200 m
 |  | Value | Tolerance |  | 
Diameter filament | µm | < 20 | - |  | 
Diameter strand | mm | 1.400 | ± 0.005 |  | 
Cu/SC ratio | - | .50/.50 | ± 0.05 | /0.5187 | /0.5132
Surface coating | - | none | - | none | none
NbTi Jc (at 4.2 K, 5 T) | A/mm2 | > 2800 | - |  | 
Critical current (at 4.2 K, 5 T) | A | > 2160 | - | 2220 | 2175
n-value (at 4.2 K, 5 T) | - | > 30 | - | 71* | 70*
Conductor RRR | - | > 100 | - | 196 | 191
Twist direction | - | left | - | left | left
Twist pitch | mm | 25 | ± 5 | 22 | 21
*Magnetic field value is 6 T
Table 1 NbTi/Cu strand mechanical and electrical specifications.

## Slide 12
Conductor.
Production strands
Batch number / strand piece number | Diameter, mm (1,400 ± 0,005 mm) | Cu/SC ratio NbTi, % | Twist pitch |  | RRR
 |  |  | begin | end | 
1-C2-1P-1-21/1 | 1,4 | 0,5187 | 22 | 22 | 196
1-C2-1P-1-21/2-1-1-1 | 1,4 | 0,5140 | 21 | 22 | 207
1-C2-1P-1-21/2-1-1-2 | 1,4 | 0,5132 | 21 | 21 | 191
1-C2-1P-1-21/2-1-2 | 1,4 | 0,5126 | 22 | 22 | 205
1-C2-1P-1-21/2-2 | 1,4 | 0,5122 | 22 | 24 | 205
Table 2 Technical parameters
Batch number / strand piece number | Sample | Measurement | Mechanical properties | 
 |  |  | Ultimate resistance, MPa | Yield strength, MPa
1-C2-1P-1-21/1 | 1n | 1 | 903 | 838
 |  | 2 | 897 | 836
 |  | 3 | 909 | 845
Batch number / strand piece number | Field, T | Ic, A (4,2 К; 0,1 mkV/sm) | n-value
1-C2-1P-1-21/1 | 8 | 789 | 35
 | 7 | 1253 | 52
 | 6 | 1746 | 71
 | 5 | 2220 (calc.) | -
1-C2-1P-1-21/2-1-1-1 | 8 | 750 | 35
 | 7 | 1208 | 53
 | 6 | 1694 | 71
 | 5 | 2175 (calc.) | -
1-C2-1P-1-21/2-2 | 8 | 750 | 36
 | 7 | 1200 | 50
 | 6 | - | -
 | 5 | 2165 (calc.) | -
Table 3 Mechanical properties
Table 4 Critical current (at 4.2 K) and n-value (at 4.2 K) vs magnetic field.

## Slide 13
Conductor.
Status of the PANDA conductor development/ procurement
BINP/ VNIINM Bochvar/ VNIIKP/ Saransk cable optic (SarKO)
Plan works with NanoElectro (in VNIINM named Bochvar) for Production wires Aluminum A995 Ø9,5mm
Defined conditions of a contract between BINP and Nanoelectro, preparation of the call for tender
PANDA Rutherford cables prototype, VNIIKP
Technical specification for technologic works in VNIIKP with PANDA strands to produce a sample 100m length of the PANDA Rutherford cable - ready
technologic works in VNIIKP with PANDA strands to produce PANDA Rutherford cable
Call for tender/ Contract signed –11-12/2021
Tests samples of the PANDA Rutherford cable according to PANDA specification - 11-12/2021
Production PANDA Rutherford cable
for central coil 1600m - 02/2022
for up/downstream coils 2*3350 - 04/2022
Tests samples of the PANDA Rutherford cable
according to PANDA specification - for each PANDA Rutherford cable piece

## Slide 14
Conductor.
Status of the PANDA conductor development/ procurement
BINP/ VNIINM Bochvar/ VNIIKP/ Saransk cable optic (SarKO)
Plan works with Saransk cable- optic
Production1000m Cu Rutherford cable for tests in SARKO - 03-04/2020 (in BINP storage)
Development works with a prototype Rutherford cable to co-extrusion/ conklad in a pure Al 995 and Aluminum A95
Oven for preheating a Rutherford cable was produced and tests with a prototype Rutherford cable are carried out.
Temperature oven - 250 ÷ 450°C;
Temperature of a prototype Rutherford cable with 2m/min velocity of the cable during crossing the oven - 170 ÷ 250°C;
Shielding gas – N2 / Ar
Technical Specification and conditions of the contract with SARKO are agreed. Preparation SARKO extrusion line to development of technology production of the PANDA conductor with preheating and creating intermetallic connections Al/Cu.
Preparation call for tender.
1000m Cu Rutherford cable, Aluminum A95 and preheating Cu cable 200-250°C - 11-12/ 2021
600m Cu Rutherford cable, Aluminum A995 and preheating Cu cable 200-250°C - Q1/ 2022
80m Nb/Ti/Cu Rutherford cable, Aluminum A995 and preheating Cu cable 200-250°C Q1/ 2022
Production PANDA conductor BINP/SARKO - 03 - 05/ 2022

## Slide 15
Conductor.
Status of the PANDA conductor development/ procurement
BINP/ VNIINM Bochvar/ VNIIKP/ Saransk cable optic (SarKO)
Worked range of high purity Aluminum is 350 – 380 °C

## Slide 16
Status of the PANDA coils production

## Slide 17
The main milestones of the coils production
Status production | 
Cryostat, Cold mass and stands for assembling solenoid and magnet | Design and technological development are ready Production from 19/04/2021 Delivery to BINP – 09/2021
Second Prototype of the Coil | 03/2020
Third Prototype of the Coil | 08/2020
4th Prototype of the Coil | Q1/2022
Prepress prototype coil into cold mass | tested 10/2020
Tooling for winding and impregnation of PANDA Coil | Production FAT – 10/2021 – OK Delivery to BINP – 12/2021

## Slide 18: Drawing of the Devices for winding coil (scheme).
Design is ready, production until 10/2021

## Slide 19: Photos of the tolling production

## Slide 20
Status Control Dewar and Transfer Line production

## Slide 21
3D model of Control Dewar
The PANDA control Dewar is designed to ensure helium delivery to the user in accordance with the flow scheme.
Chimney
- transfer line (Chimney) connecting the vacuum vessels of cryostat and control Dewar
Technologic volume
Vacuum barrier
Pamp station

## Slide 22
3D model of Control Dewar

## Slide 23
Preparation tests in BINP

## Slide 24
Flow scheme KEDR and PANDA cryogenic system

## Slide 25
Flow scheme PANDA cryogenic system

## Slide 26
Thank you for your attention