## Slide 1
Project Description |  | Subprojects / Tasks | 
Development of a digital potentiometer board control for FCC - Focus: UNILAC operation - But also generally as an option for other linear accelerators or any parameters, where a rotating controller makes sense. The project includes the incremental encoder hardware and the software application. |  | Specify the system ✔ Specification approval -> open technology decision for incremental encoder -> in progress technology decision software stack -> in progress (FESA, LSA or else) general decision on UI -> open (existing or new app + developing group) build hardware prototype -> open build software prototype -> open FAT  serial production -> open | 
Project Goals |  | Ressource Profile | 
Replace the outdated UNILAC Potiboard control with a modern version compatible with fully digital control room (FCC) Full control system integration Be ready on time for the move to FCC Production of relevant spare parts |  |  | 
Major Milestones |  | Risks, Boundary Conditions and Comments | 
Q3/2022 | Specification revision and approval | Major Risks: turnaround time too slow for adequate UNILAC control | Concerned departments: ACO (FE, AP, IN) OPE (APS)
Q4/2022 | technology decision – incremental encoder hardware and communication protocol |  | 
Q4/2022 | decision regarding use of control system stack (FESA or LSA or else) to be able to ensure the required performance |  | 
Q3/2023 | Hardware prototype ready | Boundary Condition: must be functional before move from HKR to FCC existing potiboard must kept functional until move to FCC is complete | Comments: to be clarified: Responsible group for hardware maintenance
Q1/2024 | Software prototype ready |  | 
Q3/2024 | Live test in HKR (e.g. for HEST magnets) |  | 
Year | Estimated costs [k€] | Personnel [person months]
2022 | 1 | 2
2023 | 4 | 12
2024 | 15 (inital equipment) | 3
2025 | 10 (spare parts) | 3
2026 | 0 | 0
Sum | 30.000 Euro | 20 person months
Project | FCC Digital Potiboard
Project Lead | S. Reimann
Status Date | 08.07.2022